## CDC 3-4 Build
Name | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Elapsed | Executing Party | Party Contact | Customizable Field | Status | Predecessor | Dependency | Ext. Dependency | Comments | Deliverable [Yes/No] | Deliverable Name | Deliverable Type | Deliverable Owner | Client Sign off | Penalties [Yes/No] | Key Contractual Milestones | Domain | SPOC Planning | Workstream | Workstream PM | Contractual Milestone [Yes/No] | Last Updated
''MR2.9 - Location Selection'' | 2021-08-06 05:30 | 2021-08-30 05:30 | 2021-08-06 05:30 | 2021-08-30 05:30 | 19 | 1&1 |  |  | Completed |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network |  | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3 - CDC3 Rollout Steps to be ready for Y23_1.5M'' | 2021-12-01 05:30 | 2023-01-31 05:30 | 2021-12-01 05:30 | 2023-01-31 05:30 | 305 | Rakuten |  |  | In Progress |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.1 - Planning & Dimensioning'' | 2021-12-01 05:30 | 2022-03-31 05:30 | 2021-12-01 05:30 | 2022-03-31 05:30 | 87 | Rakuten |  |  | In Progress |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.2 - HW Orders '' | 2022-02-01 05:30 | 2022-02-28 05:30 | 2022-02-01 05:30 | 2022-02-28 05:30 | 20 | Rakuten |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.3 - HW Delivery '' | 2022-03-01 05:30 | 2022-06-30 05:30 | 2022-03-01 05:30 | 2022-06-30 05:30 | 88 | Rakuten |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.4 - DCN Setup'' | 2022-07-01 05:30 | 2022-07-30 05:30 | 2022-07-01 05:30 | 2022-07-30 05:30 | 21 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.5 - Basic Security Setup'' | 2022-08-01 05:30 | 2022-08-15 05:30 | 2022-08-01 05:30 | 2022-08-15 05:30 | 11 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.6 - Cloud Setup'' | 2022-08-15 05:30 | 2022-09-30 05:30 | 2022-08-15 05:30 | 2022-09-30 05:30 | 35 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.7 - Core Deployment'' | 2022-10-01 05:30 | 2022-11-30 05:30 | 2022-10-01 05:30 | 2022-11-30 05:30 | 44 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.8 - Applications Deployment'' | 2022-10-01 05:30 | 2022-11-30 05:30 | 2022-10-01 05:30 | 2022-11-30 05:30 | 44 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.9 - E2E Testing & Acceptance'' | 2022-12-01 05:30 | 2023-01-31 05:30 | 2022-12-01 05:30 | 2023-01-31 05:30 | 46 | Rakuten |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.4 - CDC4 Rollout Steps to be ready for Y23_1.5M'' | 2021-12-01 05:30 | 2023-01-31 05:30 | 2021-12-01 05:30 | 2023-01-31 05:30 | 305 | Rakuten |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.4.1 - Planning & Dimensioning'' | 2021-12-01 05:30 | 2022-03-31 05:30 | 2021-12-01 05:30 | 2022-03-31 05:30 | 87 | Rakuten |  |  | In Progress |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.4.2 - HW Orders '' | 2022-02-01 05:30 | 2022-02-28 05:30 | 2022-02-01 05:30 | 2022-02-28 05:30 | 20 | Rakuten |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.4.3 - HW Delivery '' | 2022-03-01 05:30 | 2022-06-30 05:30 | 2022-03-01 05:30 | 2022-06-30 05:30 | 88 | Rakuten |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.4.4 - DCN Setup'' | 2022-07-01 05:30 | 2022-07-30 05:30 | 2022-07-01 05:30 | 2022-07-30 05:30 | 21 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.4.5 - Basic Security Setup'' | 2022-08-01 05:30 | 2022-08-15 05:30 | 2022-08-01 05:30 | 2022-08-15 05:30 | 11 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 03-Feb 02:08 AM'
''Y23.4.6 - Cloud Setup'' | 2022-08-15 05:30 | 2022-09-30 05:30 | 2022-08-15 05:30 | 2022-09-30 05:30 | 35 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 03-Feb 02:08 AM'
''Y23.4.7 - Core Deployment'' | 2022-10-01 05:30 | 2022-11-30 05:30 | 2022-10-01 05:30 | 2022-11-30 05:30 | 44 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 03-Feb 02:08 AM'
''Y23.4.7 - Applications Deployment'' | 2022-10-01 05:30 | 2022-11-30 05:30 | 2022-10-01 05:30 | 2022-11-30 05:30 | 44 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.4.8 - E2E Testing & Acceptance'' | 2022-12-01 05:30 | 2023-01-31 05:30 | 2022-12-01 05:30 | 2023-01-31 05:30 | 46 | Rakuten |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'