## CDC 1-2-3-4 Design and Planning
Name | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Elapsed | Executing Party | Party Contact | Customizable field | Status | Predecessor | Dependency | Ext. Dependencies | Comments | Deliverable [Yes/No] | Deliverable Name | Deliverable Type | Deliverable Owner | Client Sign off | Penalties [Yes/No] | Key Contractual Milestones | Domain | SPOC Planning | Workstream | Workstream PM | Contractual Milestone [Yes/No] | Last Updated
''MR2.0.6.13 - contribution to MR6.2.23.1.1 - M2c - Service Incident - Low Level Design CORE''' | 2021-09-16 05:30 | 2021-09-16 05:30 | 2021-11-17 05:30 | 2021-11-17 05:30 | 1 | Rakuten |  |  | Completed |  |  |  |  | Yes | Low Level Design CORE | Low Level Design CORE |  | No |  | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | No | 'sawan.kumar@sourcefuse.com on 03-Feb 04:59 PM'
''MR2.0.6.8 - contribution to MR6.2.18.5.1 - M2c - Einbindung 5G CPE (Fritzbox) konfig. iMBA Netz - Low Level Design CORE''' | 2021-09-16 05:30 | 2021-09-16 05:30 | 2021-11-17 05:30 | 2021-11-17 05:30 | 1 | Rakuten |  |  | Completed |  |  |  |  | Yes | Low Level Design CORE | Low Level Design CORE |  | No |  | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | No | 'sawan.kumar@sourcefuse.com on 03-Feb 04:59 PM'
''MR2.0.6.10 - contribution to MR6.2.20.6.3 - M2c - 1&1 HD TV bei eineMBA 5G Subscriber - Low Level Design CORE''' | 2021-09-16 05:30 | 2021-09-16 05:30 | 2021-12-06 05:30 | 2021-12-06 05:30 | 1 | Rakuten |  |  | Completed |  |  |  |  | Yes | Low Level Design CORE | Low Level Design CORE |  | No |  | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | No | 'sawan.kumar@sourcefuse.com on 03-Feb 04:59 PM'
''MR2.0.6.7 - contribution to MR6.2.15.6.4 - M2c - Quality of Service (QoS) - Low Level Design CORE''' | 2021-09-16 05:30 | 2021-09-16 05:30 | 2021-11-17 05:30 | 2021-11-17 05:30 | 1 | Rakuten |  |  | Completed |  |  |  |  | Yes | Low Level Design CORE | Low Level Design CORE |  | No |  | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | No | 'sawan.kumar@sourcefuse.com on 03-Feb 04:59 PM'
''MR2.0.6.11 - contribution to MR6.2.21.6.4 - M2c - GEO Cell ID (stationary product) - Low Level Design CORE''' | 2021-09-16 05:30 | 2021-09-16 05:30 | 2021-11-17 05:30 | 2021-11-17 05:30 | 1 | Rakuten |  |  | Completed |  |  | Provider |  | Yes | Low Level Design CORE | Low Level Design CORE |  | No |  | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | No | 'sawan.kumar@sourcefuse.com on 03-Feb 04:59 PM'
''MR2.0.6.1 - contribution to MR6.2.2.6.6 - M2a - General Data - Low Level Design CORE''' | 2021-09-16 05:30 | 2021-09-16 05:30 | 2021-11-17 05:30 | 2021-11-17 05:30 | 1 | Rakuten |  |  | Completed |  |  | Provider |  | Yes | Low Level Design CORE | Low Level Design CORE |  | No |  | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | No | 'sawan.kumar@sourcefuse.com on 03-Feb 04:59 PM'
''MR2.0.6.4 - contribution to MR6.2.9.6.4 - M2b - General Proposition - Low Level Design CORE''' | 2021-09-16 05:30 | 2021-09-16 05:30 | 2021-11-17 05:30 | 2021-11-17 05:30 | 1 | Rakuten |  |  | Completed |  |  |  |  | Yes | Low Level Design CORE | Low Level Design CORE |  | No |  | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | No | 'sawan.kumar@sourcefuse.com on 03-Feb 04:59 PM'
''MR2.0.6.2 - contribution to MR6.2.3.6.6 - M2a - Data Packages - Parameterization FWA - Low Level Design CORE''' | 2021-09-16 05:30 | 2021-09-16 05:30 | 2021-11-17 13:30 | 2021-11-17 13:30 | 1 | Rakuten |  |  | Completed |  |  | Provider |  | Yes | Low Level Design CORE | Low Level Design CORE |  | No |  | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | No | 'sawan.kumar@sourcefuse.com on 03-Feb 04:59 PM'
''MR2.0.6.5 - contribution to MR6.2.10.4.4 - M2b - SIMBA Change - Breakout Sesssion incl. Open Issues CORE''' | 2021-09-16 05:30 | 2021-09-16 05:30 | 2021-11-17 05:30 | 2021-11-17 05:30 | 1 | Rakuten |  |  | Completed |  |  |  |  | Yes | Low Level Design CORE | Low Level Design CORE |  | No |  | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | No | 'sawan.kumar@sourcefuse.com on 03-Feb 04:59 PM'
''MR2.0.6.12 - contribution to MR6.2.22.1.1 - M2c - Coverage Check - Low Level Design CORE''' | 2021-09-16 05:30 | 2021-09-16 05:30 | 2021-11-17 05:30 | 2021-11-17 05:30 | 1 | Rakuten |  |  | Completed |  |  |  |  | Yes | Low Level Design CORE | Low Level Design CORE |  | No |  | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | No | 'sawan.kumar@sourcefuse.com on 03-Feb 04:59 PM'
''MR2.0.6.6 - contribution to MR6.2.14.6.4 - M2c - IPV6 - Low Level Design CORE''' | 2021-09-16 05:30 | 2021-09-16 05:30 | 2021-11-17 05:30 | 2021-11-17 05:30 | 1 | Rakuten |  |  | Completed |  |  |  |  | Yes | Low Level Design CORE | Low Level Design CORE |  | No |  | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | No | 'sawan.kumar@sourcefuse.com on 03-Feb 04:59 PM'
'''MR2.0 - Central Data Centers Design and Planning''' | 2021-08-01 05:30 | 2022-12-31 05:30 | 2021-08-01 05:30 | 2022-12-31 05:30 | 370 | Rakuten |  |  | In progress |  |  |  |  | No | [5 empty] | All | CDC & Core Network | Marius Andrei |  | Wissam Haddad | No | 'sawan.kumar@sourcefuse.com on 03-Feb 04:59 PM'
''MR2.0.1 - Technical Solution Document for Contract''' | 2021-05-01 05:30 | 2021-08-06 05:30 | 2021-05-01 05:30 | 2021-08-06 05:30 | 70 | Rakuten |  |  | In progress |  |  |  |  | Yes | Technical Solution Document | Document |  | Signed off as part of the contract |  | All | CDC & Core Network | Marius Andrei |  | Fausto Grazioli | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'''MR2.0.2 - High Level Designs''' | 2021-09-01 05:30 | 2021-12-30 05:30 | 2021-10-04 05:30 | 2022-03-31 05:30 | 129 | Rakuten |  |  | In progress | MR2.0.1 |  |  |  | No | [5 empty] | All | CDC & Core Network | Marius Andrei |  |  | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'''MR2.0.2.1 - HLD Compute''' | 2021-09-01 05:30 | 2021-10-30 05:30 | 2021-11-18 05:30 | 2021-12-17 05:30 | 22 | Rakuten |  |  | In progress |  |  |  |  | Yes | RCP Cloud HLD for CDC1/2 | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.2.2 - HLD Core''' | 2021-10-04 05:30 | 2021-12-12 05:30 | 2021-10-04 05:30 | 2022-02-07 05:30 | 91 | Rakuten | Mavenir |  | In progress |  |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.2.2.1 - HLD Packet Core ''' | 2021-10-04 05:30 | 2021-12-12 05:30 | 2021-10-04 05:30 | 2022-02-07 05:30 | 91 | Rakuten | Mavenir |  | In progress | MR2.0.2.2 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.2.2.1.1 - HLD Packet Core Acceptance by Rakuten''' | 2021-10-04 05:30 | 2021-12-12 05:30 | 2021-10-04 05:30 | 2022-01-03 05:30 | 66 | Rakuten | Mavenir |  | In progress | MR2.0.2.2.1 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.2.2.1.2 - HLD Packet Core Acceptance by 1&1''' | 2021-10-04 05:30 | 2021-12-12 05:30 | 2021-10-04 05:30 | 2022-02-07 05:30 | 91 | Rakuten | Mavenir |  | In progress | MR2.0.2.2.1.2 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.2.2.2 - HLD Voice and Messaging''' | 2021-10-04 05:30 | 2021-12-12 05:30 | 2021-10-04 05:30 | 2022-02-07 05:30 | 91 | Rakuten | Mavenir |  | In progress | MR2.0.2.2 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.2.2.2.1 - HLD Voice and Messaging Acceptance by Rakuten''' | 2021-10-04 05:30 | 2021-12-12 05:30 | 2021-10-04 05:30 | 2022-01-03 05:30 | 66 | Rakuten | Mavenir |  | In progress | MR2.0.2.2.2 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.2.2.2.2 - HLD Voice and Messaging Acceptance by 1&1''' | 2021-10-04 05:30 | 2021-12-12 05:30 | 2021-10-04 05:30 | 2022-02-07 05:30 | 91 | Rakuten | Mavenir |  | In progress | MR2.0.2.2.2.1 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.2.2.3 - HLD National Roaming and Interconnect ''' | 2021-10-04 05:30 | 2021-12-12 05:30 | 2021-10-04 05:30 | 2022-02-07 05:30 | 91 | Rakuten | Mavenir |  | In progress | MR2.0.2.2 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.2.2.3.1 - HLD National Roaming and Interconnect Acceptance by Rakuten''' | 2021-10-04 05:30 | 2021-12-12 05:30 | 2021-10-04 05:30 | 2022-01-03 05:30 | 66 | Rakuten | Mavenir |  | In progress | MR2.0.2.2.3 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.2.2.3.2 - HLD National Roaming and Interconnect Acceptance by 1&1''' | 2021-10-04 05:30 | 2021-12-12 05:30 | 2021-10-04 05:30 | 2022-02-07 05:30 | 91 | Rakuten | Mavenir |  | In progress | MR2.0.2.2.3.1 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'''MR2.0.2.3 - HLD DC Network''' | 2021-10-04 05:30 | 2021-11-30 05:30 | 2021-10-04 05:30 | 2021-11-30 05:30 | 42 | Rakuten |  |  | In progress |  |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Transport | Christoph Reichl | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'''MR2.0.2.4 - External Dependency: HLD Security''' | 2021-10-15 05:30 | 2021-12-15 05:30 | 2021-12-06 05:30 | 2022-03-31 05:30 | 84 | Rakuten |  |  | In progress | 'MR 2.0.2.3 + Check ID from Security Plan' |  | Consumer |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Security | Mario Goller | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'''MR2.0.3 - Low Level Designs''' | 2021-10-01 05:30 | 2022-01-31 05:30 | 2021-10-11 05:30 | 2022-04-29 05:30 | 145 | Rakuten |  |  | In progress |  |  |  |  | No | [5 empty] | All | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'''MR2.0.3.1 - LLD Compute Template''' | 2021-10-01 05:30 | 2021-10-30 05:30 | 2021-12-13 05:30 | 2021-12-31 05:30 | 15 | Rakuten |  |  | In progress | MR2.0.2.1 |  |  |  | Yes | RCP Cloud LLD for CDC1/2 | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.3.2 - LLD Core Template''' | 2021-12-01 05:30 | 2021-12-31 05:30 | 2021-10-11 05:30 | 2022-03-15 05:30 | 112 | Rakuten |  |  | In progress | MR2.0.2.2 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.3.2.1 - LLD Packet Core ''' | 2021-12-01 05:30 | 2021-12-31 05:30 | 2021-10-11 05:30 | 2022-03-15 05:30 | 112 | Rakuten | Mavenir |  | Not started | MR2.0.3.2 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.3.2.1.1 - LLD Packet Core Acceptance by Rakuten''' | 2021-12-01 05:30 | 2021-12-31 05:30 | 2021-10-11 05:30 | 2022-02-15 05:30 | 92 | Rakuten | Mavenir |  | Not started | MR2.0.3.2.1 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.3.2.1.2 - LLD Packet Core Acceptance by 1&1''' | 2021-12-01 05:30 | 2021-12-31 05:30 | 2021-10-11 05:30 | 2022-03-15 05:30 | 112 | Rakuten | Mavenir |  | Not started | ''MR2.0.3.2.1.1' |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.3.2.2 - LLD Voice and Messaging''' | 2021-12-01 05:30 | 2021-12-31 05:30 | 2021-10-11 05:30 | 2022-03-15 05:30 | 112 | Rakuten | Mavenir |  | Not started | MR2.0.3.2 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.3.2.2.1 - LLD Voice and Messaging Acceptance by Rakuten''' | 2021-12-01 05:30 | 2021-12-31 05:30 | 2021-10-11 05:30 | 2022-02-15 05:30 | 92 | Rakuten | Mavenir |  | Not started | MR2.0.3.2.2 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.3.2.2.2 - LLD Voice and Messaging Acceptance by 1&1''' | 2021-12-01 05:30 | 2021-12-31 05:30 | 2021-10-11 05:30 | 2022-03-15 05:30 | 112 | Rakuten | Mavenir |  | Not started | MR2.0.3.2.2.1 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.3.2.3 - LLD National Roaming and Interconnect ''' | 2021-12-01 05:30 | 2021-12-31 05:30 | 2021-10-11 05:30 | 2022-03-15 05:30 | 112 | Rakuten | Mavenir |  | Not started | MR2.0.3.2 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.3.2.3.1 - LLD National Roaming and Interconnect Acceptance by Rakuten''' | 2021-12-01 05:30 | 2021-12-31 05:30 | 2021-10-11 05:30 | 2022-02-15 05:30 | 92 | Rakuten | Mavenir |  | Not started | MR2.0.3.2.3 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.3.2.3.2 - LLD National Roaming and Interconnect Acceptance by 1&1''' | 2021-12-01 05:30 | 2021-12-31 05:30 | 2021-10-11 05:30 | 2022-03-15 05:30 | 112 | Rakuten | Mavenir |  | Not started | MR2.0.3.2.3.1 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'''MR2.0.3.3 - LLD DC Network Template''' | 2021-12-01 05:30 | 2021-12-31 05:30 | 2021-11-08 05:30 | 2021-12-31 05:30 | 40 | Rakuten |  |  | In progress | MR2.0.2.3 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Transport | Christoph Reichl | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'''MR2.0.3.4 - LLD Security Template''' | 2021-12-01 05:30 | 2021-12-31 05:30 | 2022-03-25 05:30 | 2022-04-29 05:30 | 26 | Rakuten |  |  | Not started | MR2.0.2.4 |  |  |  | Yes |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Security | Mario Goller | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'''MR2.0.4 - HW Dimensioning (servers, switches, storage)''' | 2021-08-01 05:30 | 2022-01-31 05:30 | 2021-08-01 05:30 | 2022-01-31 05:30 | 131 | Rakuten |  |  | In progress | MR2.0.1 |  |  |  | No | [5 empty] | All | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'''MR2.0.4.1 - Initial HW Dimensioning (MVP/50k/10Gbps)''' | 2021-08-01 05:30 | 2021-10-30 05:30 | 2021-08-01 05:30 | 2021-09-23 05:30 | 39 | Rakuten |  |  | Completed |  |  |  |  | Yes | RCP Cloud BoM for CDC1/2 | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'''MR2.0.4.2 - HW Dimensioning as per Traffic Forcast for Y23_1.5M''' | 2021-12-01 05:30 | 2021-12-31 05:30 | 2021-12-06 05:30 | 2021-12-31 05:30 | 20 | Rakuten |  |  | Delayed |  |  |  |  | No |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'''MR2.0.4.3 - HW Dimensioning as per Traffic Forcast for Y24_12M''' | 2022-01-01 05:30 | 2022-01-31 05:30 | 2021-12-06 05:30 | 2022-01-31 05:30 | 41 | Rakuten |  |  | Delayed |  |  |  |  | No |  | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'''MR2.0.5 - Supplement Documentation/Deliverables''' | 2021-09-01 05:30 | 2021-11-30 05:30 | 2021-09-01 05:30 | 2021-11-30 05:30 | 65 | Rakuten |  |  | Not started |  |  |  |  | No | [5 empty] | All | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.5.1 - Monitoring concept design & OBF Integration for Dell HW''' | 2021-09-01 05:30 | 2021-09-30 05:30 | 2021-09-01 05:30 | 2021-09-30 05:30 | 22 | Rakuten |  |  | Not started |  |  |  |  | Yes | Monitoring concept design & OBF Integration for Dell HW | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.5.2 - Staging and SW commissioning procedures''' | 2021-11-01 05:30 | 2021-11-30 05:30 | 2021-11-01 05:30 | 2021-11-30 05:30 | 22 | Rakuten |  |  | Not started |  |  |  |  | Yes | Staging and SW commissioning procedures | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.5.3 - VNF/CNF & NS onboarding support''' | 2021-10-01 05:30 | 2022-12-31 05:30 | 2021-10-01 05:30 | 2022-12-31 05:30 | 326 | Rakuten |  |  | In progress |  |  |  |  | Yes | VNF/CNF & NS onboarding support | Activity |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.5.4 - RCP Cloud Test Strategy''' | 2021-10-01 05:30 | 2021-10-30 05:30 | 2021-10-01 05:30 | 2021-10-30 05:30 | 21 | Rakuten |  |  | Not started |  |  |  |  | Yes | RCP Cloud Test Strategy | Document |  |  |  | All | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.6 - Core contribution for BSS design'' | [5 empty] | Rakuten |  |  | Not started |  |  |  |  | No | [5 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.6.9 - contribution to MR6.2.19.5.2 - M2c - Fixed Line Number with 1&1 VoIP - Low Level Design CORE''' | 2021-09-16 05:30 | 2021-09-16 05:30 | 2021-11-17 05:30 | 2021-11-17 05:30 | 1 | Rakuten |  |  | Completed |  |  |  |  | Yes | Low Level Design CORE | Low Level Design CORE |  | No |  | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''MR2.0.6.3 - contribution to MR6.2.8.5.2 - M2b - Charging incl Special Rate - Low Level Design CORE''' | 2021-09-16 05:30 | 2021-09-16 05:30 | 2021-11-17 05:30 | 2021-11-17 05:30 | 1 | Rakuten |  |  | Completed |  |  |  |  | Yes | Low Level Design CORE | Low Level Design CORE |  | No |  | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'

## CDC 1-2 Build
Name | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Elapsed | Executing Party | Party Contact | Customizable Field | Status | Predecessor | Dependency | Ext. Dependency | Comments | Deliverable [Yes/NO] | Deliverable Name | Deliverable Type | Deliverable Owner | Client Sign off | Penalties [Yes/No] | Key Contractual Milestones | Domain | SPOC Planning | Workstream | Workstream PM | Contractual Milestone [Yes/No]
''MR2.1 - Steps Contributing to Milestone Facility Readiness''' | 2021-09-01 05:30 | 2021-12-15 05:30 | 2021-09-01 05:30 | 2021-12-15 05:30 | 105 | Rakuten |  |  | In progress | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
'''MR2.1.2 - CDC1 Facility Readiness''' | 2021-08-30 05:30 | 2021-12-15 05:30 | 2021-08-31 05:30 | 2022-06-01 05:30 | 274 | Rakuten |  |  | In progress | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.1.2.0 - CDC1 Site Selection''' | 2021-08-30 05:30 | 2021-08-30 05:30 | 2021-08-31 05:30 | 2021-08-31 05:30 | 0 | 1&1 |  |  | Completed | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.1.2.1 - CDC1 Site Survey''' | 2021-09-01 05:30 | 2021-09-30 05:30 | 2021-10-18 05:30 | 2021-10-18 05:30 | 0 | Rakuten/Versatel |  |  | Completed | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
'''MR2.1.2.2 - CDC1 Facility Dimensioning (floor space, power, cooling)''' | 2021-09-01 05:30 | 2021-09-30 05:30 | 2021-09-30 05:30 | 2021-10-07 05:30 | 7 | Versatel |  |  | Completed | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.1.2.3 - CDC1 Rental Order from 1&1 to Versatel''' | 2021-09-01 05:30 | 2021-09-03 05:30 | 2021-08-31 05:30 | 2021-09-06 05:30 | 6 | 1&1 |  |  | Completed | MR2.1.2.0 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.1.2.4 - CDC1 Transport Rental Order from 1&1 to Versatel''' | 2021-09-01 05:30 | 2021-09-03 05:30 | 2021-08-31 05:30 | 2021-09-06 05:30 | 6 | 1&1 |  |  | Completed | MR2.1.2.0 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Mario Catalan | No
''MR2.1.2.5 - CDC1 Space and racks available''' | 2021-09-06 05:30 | 2021-12-15 05:30 | 2021-09-07 05:30 | 2021-12-23 05:30 | 107 | Versatel |  |  | In progress | MR2.1.2.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.1.2.6 - CDC1 Power & cooling, no redundant - 150KW''' | 2021-09-06 05:30 | 2021-12-15 05:30 | 2021-09-07 05:30 | 2021-12-31 05:30 | 115 | Versatel |  |  | Completed | MR2.1.2.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
'''MR2.1.2.7 - CDC1 Power & cooling, no redundant - 350KW''' | 2021-09-06 05:30 | 2021-12-15 05:30 | 2021-10-04 05:30 | 2022-03-23 05:30 | 170 | Versatel |  |  | In progress | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.1.2.8 - CDC1 Internet connectivity''' | 2021-09-06 05:30 | 2021-12-15 05:30 | 2021-12-13 05:30 | 2022-01-20 05:30 | 38 | Versatel |  |  | In progress | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Mario Catalan | No
'MR2.1.2.9 - CDC1 Operational readiness, full power,cooling including redundancy''' | 2021-09-06 05:30 | 2021-12-15 05:30 | 2021-12-31 05:30 | 2022-06-01 05:30 | 152 | Versatel |  |  | Not started | MR2.1.2.6 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
'''MR2.1.3 - CDC2 Facility Readiness''' | 2021-09-01 05:30 | 2022-06-01 05:30 | 2021-08-31 05:30 | 2022-08-31 05:30 | 365 | Rakuten |  |  | In progress | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.1.3.1 - CDC2 Site Survey''' | 2021-09-01 05:30 | 2021-09-30 05:30 | 2021-10-18 05:30 | 2021-10-18 05:30 | 0 | Rakuten/Versatel |  |  | Completed | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
'''MR2.1.3.2 - CDC2 Facility Dimensioning (floor space, power, cooling)''' | 2021-09-01 05:30 | 2021-09-30 05:30 | 2021-09-30 05:30 | 2021-10-07 05:30 | 7 | Versatel |  |  | Completed | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.1.3.3 - CDC2 Rental Order from 1&1 to Versatel''' | 2021-09-01 05:30 | 2021-09-03 05:30 | 2021-08-31 05:30 | 2021-09-06 05:30 | 6 | 1&1 |  |  | Completed | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.1.3.4 - CDC2 Transport Rental Order from 1&1 to Versatel''' | 2021-09-01 05:30 | 2021-09-03 05:30 | 2021-08-31 05:30 | 2021-09-06 05:30 | 6 | 1&1 |  |  | Completed | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Mario Catalan | No
''MR2.1.3.5 - CDC2 Space and racks available''' | 2021-09-06 05:30 | 2021-12-15 05:30 | 2021-09-07 05:30 | 2022-02-21 05:30 | 167 | Versatel |  |  | In progress | MR2.1.3.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.1.3.6 - CDC2 Power & cooling, no redundant''' | 2021-09-06 05:30 | 2021-12-15 05:30 | 2021-09-07 05:30 | 2022-02-21 05:30 | 167 | Versatel |  |  | In progress | MR2.1.3.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.1.3.7 - CDC2 Internet connectivity''' | 2021-09-06 05:30 | 2021-12-15 05:30 | 2021-12-13 05:30 | 2022-02-21 05:30 | 70 | Rakuten |  |  | In progress | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Mario Catalan | No
'MR2.1.3.8 - CDC2 Operational readiness, full power,cooling including redundancy''' | 2021-09-06 05:30 | 2022-06-01 05:30 | 2022-02-21 05:30 | 2022-08-31 05:30 | 191 | Versatel |  |  | Not started | MR2.1.3.6 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.1.4 - Interconnect CDC1 to CDC2' | 2021-09-06 05:30 | 2022-06-01 05:30 | 2022-01-26 05:30 | 2022-11-03 05:30 | 281 | Rakuten |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.1 - Facility Readiness'' | 2021-12-15 05:30 | 2021-12-15 05:30 | 2021-12-15 05:30 | 2021-12-15 13:30 | 0 | Rakuten |  |  | Delayed | MR2.1.2.10, MR2.1.3.9 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.2 - Steps Contributing to Milestone HW Delivery''' | 2021-09-01 05:30 | 2021-12-31 05:30 | 2021-09-01 05:30 | 2022-12-31 05:30 | 486 | Rakuten |  |  | In progress | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.2.1 - Bill of Materials for Initial Order''' | 2021-09-01 05:30 | 2021-09-30 05:30 | 2021-09-01 05:30 | 2021-09-24 05:30 | 23 | Rakuten |  |  | Completed | MR2.0.4.1 |  |  |  |  | RCP Cloud BoM for CDC1/2 | Document |  |  |  | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Saravana | No
''MR2.2.2 - Initial Purchase Orders''' | 2021-10-01 05:30 | 2021-10-05 05:30 | 2022-10-28 05:30 | 2022-12-31 05:30 | 64 | Rakuten |  |  | In progress | MR2.2.1 |  |  | Cables not ordered yet, shall be ordered EOY. | [6 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Saravana | No
''MR2.2.2.1 - Dell Order''' | 2021-10-01 05:30 | 2021-10-05 05:30 | 2021-10-08 05:30 | 2021-11-10 05:30 | 33 | Rakuten |  |  | Completed | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Saravana | No
''MR2.2.2.2 - Cisco Order''' | 2021-10-01 05:30 | 2021-10-05 05:30 | 2021-10-08 05:30 | 2021-12-02 05:30 | 55 | Rakuten |  |  | Completed | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Saravana | No
''MR2.2.2.3 - Power Cables Order''' | 2021-10-01 05:30 | 2021-11-30 05:30 | 2021-10-08 05:30 | 2021-12-14 05:30 | 67 | Rakuten |  |  | Completed | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Saravana | No
''MR2.2.3 - Hardware Delivery of initial orders''' | 2021-10-06 05:30 | 2021-12-15 05:30 | 2021-10-29 05:30 | 2022-03-04 05:30 | 126 | Rakuten |  |  | In progress | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Supply Chain | Longlong Wang a.i. | No
''MR2.2.3.1 - Dell Delivery''' | 2021-10-06 05:30 | 2021-12-15 05:30 | 2021-11-11 05:30 | 2022-01-21 05:30 | 71 | Dell |  |  | In progress | MR2.2.2.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Supply Chain | Longlong Wang a.i. | No
''MR2.2.3.2 - Cisco Delivery''' | 2021-10-06 05:30 | 2021-12-15 05:30 | 2021-10-29 05:30 | 2022-03-04 05:30 | 126 | Cisco |  |  | In progress | MR2.2.2.2 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Supply Chain | Longlong Wang a.i. | No
''MR2.2.3.3 - Power Cables Delivery''' | 2021-10-06 05:30 | 2021-12-15 05:30 | 2021-12-15 05:30 | 2022-01-19 05:30 | 35 | Rakuten |  |  | Not started | MR2.2.2.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Supply Chain | Longlong Wang a.i. | No
'''MR2.2.4 - Equipment at warehouse, delivery acceptance (Invoice 30%)''' | 2021-12-01 05:30 | 2021-12-15 05:30 | 2022-01-07 05:30 | 2022-05-06 05:30 | 119 | Rakuten |  |  | Not started | MR2.2.3 |  |  | Equipment might go actually either to warehouse or directly to CDC if space and racks available. | [6 empty] | FWA | CDC & Core Network | Marius Andrei | Supply Chain | Longlong Wang a.i. | No
'''MR2.2.5 - Payment Equipment at Warehouse ''' | 2021-12-15 05:30 | 2021-12-31 05:30 | 2022-05-09 05:30 | 2022-06-17 05:30 | 39 | 1&1 |  |  | Not started | MR2.2.4 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Procurement | Yamada Tomomichi a.i. | No
'MR2.2 - HW Delivery' | 2021-09-01 05:30 | 2021-12-31 05:30 | 2021-09-01 05:30 | 2022-12-31 05:30 | 486 | Rakuten |  |  | Delayed | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Procurement | Yamada Tomomichi a.i. | No
''MR2.3 - Steps Contributing to CDC1-2 Build Start''' | 2021-12-15 05:30 | 2021-12-31 05:30 | 2022-01-12 05:30 | 2022-07-18 05:30 | 187 | Rakuten | TechM |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Procurement | Yamada Tomomichi a.i. | No
''MR2.3.1 - CDC 1 Build Start''' | 2021-12-15 05:30 | 2021-12-31 05:30 | 2022-01-12 05:30 | 2022-04-20 05:30 | 98 | Rakuten | TechM |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.3.1.1 - Racking & Stacking''' | 2021-12-15 05:30 | 2021-12-25 05:30 | 2022-01-12 05:30 | 2022-04-07 05:30 | 85 | Rakuten |  |  | Delayed | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.3.1.2 - Cabling & Labeling ''' | 2021-12-15 05:30 | 2021-12-25 05:30 | 2022-01-13 05:30 | 2022-04-08 05:30 | 85 | Rakuten |  |  | Delayed | MR2.3.1.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.3.1.3 - Hardware acceptance (physical installation)''' | 2021-12-27 05:30 | 2021-12-27 05:30 | 2022-04-11 05:30 | 2022-04-15 05:30 | 4 | Rakuten |  |  | Not started | MR2.3.1.2 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.3.1.4 - Hardware power on (initial build)''' | 2021-12-28 05:30 | 2021-12-31 05:30 | 2022-04-18 05:30 | 2022-04-20 05:30 | 2 | Rakuten |  |  | Not started | MR2.3.1.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
'''MR2.3.2 - CDC 2 Build Start''' | 2021-12-15 05:30 | 2021-12-31 05:30 | 2022-06-08 05:30 | 2022-07-18 05:30 | 40 | Rakuten | TechM |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.3.2.1 - Racking & Stacking''' | 2021-12-15 05:30 | 2021-12-25 05:30 | 2022-06-08 05:30 | 2022-07-05 05:30 | 27 | Rakuten |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.3.2.2 - Cabling & Labeling ''' | 2021-12-15 05:30 | 2021-12-25 05:30 | 2022-06-09 05:30 | 2022-07-06 05:30 | 27 | Rakuten |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.3.2.3 - Hardware acceptance (phyTechMcal installation)''' | 2021-12-27 05:30 | 2021-12-27 05:30 | 2022-07-07 05:30 | 2022-07-13 05:30 | 6 | Rakuten |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.3.2.4 - Hardware power on (initial build)''' | 2021-12-28 05:30 | 2021-12-31 05:30 | 2022-07-14 05:30 | 2022-07-18 05:30 | 4 | Rakuten |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
''MR2.3 - CDC1-2 Build Start >> Milestone Date''' | 2021-12-15 05:30 | 2021-12-31 05:30 | 2022-01-12 05:30 | 2022-07-18 05:30 | 187 | Rakuten |  |  | Delayed | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.4 - Steps Contributing to Cloud Readiness''' | 2022-01-01 05:30 | 2022-02-15 05:30 | 2022-04-21 05:30 | 2022-10-26 05:30 | 188 | Rakuten | TechM |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
'''MR2.4.1 - CDC 1 Building Network & Cloud''' | 2022-01-01 05:30 | 2022-02-15 05:30 | 2022-04-21 05:30 | 2022-07-29 05:30 | 99 | Rakuten | TechM |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
'''MR2.4.1.1 - DC Network Rollout (internal DC networking)''' | 2022-01-01 05:30 | 2022-01-10 05:30 | 2022-04-21 05:30 | 2022-05-18 05:30 | 27 | Rakuten |  |  | Not started | MR2.3.1.4 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Mario Catalan | No
'''MR2.4.1.3 - Baremetal Servers Provisioning, OS installation & Hardening''' | 2022-01-11 05:30 | 2022-02-15 05:30 | 2022-05-19 05:30 | 2022-05-25 05:30 | 6 | Tech Mahindra |  |  | Not started | MR2.4.1.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
'''MR2.4.1.4 - Cloud Clusters Deployment, Configuration & Integration''' | 2022-01-11 05:30 | 2022-02-15 05:30 | 2022-06-06 05:30 | 2022-07-29 05:30 | 53 | Tech Mahindra |  |  | Not started | MR2.4.1.3.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
'''MR2.4.1.4.1 - Secu Cluster Deployment, Configuration & Sanity testing''' | 2022-01-11 05:30 | 2022-01-21 05:30 | 2022-06-06 05:30 | 2022-06-17 05:30 | 11 | Tech Mahindra |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka; Mahshid Mansourian | No
'''MR2.4.1.4.2 - Platform Cluster Deployment, Configuration & Sanity testing''' | 2022-01-16 05:30 | 2022-01-26 05:30 | 2022-06-13 05:30 | 2022-06-24 05:30 | 11 | Tech Mahindra |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka; Mahshid Mansourian | No
'''MR2.4.1.4.3 - Auto+Orch Cluster Deployment, Configuration & Sanity testing''' | 2022-01-21 05:30 | 2022-02-03 05:30 | 2022-06-20 05:30 | 2022-07-18 05:30 | 28 | Tech Mahindra |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka; Mahshid Mansourian | No
'''MR2.4.1.4.4 - OBF Cluster Deployment, Configuration & Sanity testing''' | 2022-02-04 05:30 | 2022-02-15 05:30 | 2022-07-06 05:30 | 2022-07-28 05:30 | 22 | Tech Mahindra |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka; Mahshid Mansourian | No
'''MR2.4.1.4.5 - Mavenir Core Cluster Deployment, Configuration & Sanity testing''' | 2022-02-04 05:30 | 2022-02-15 05:30 | 2022-07-06 05:30 | 2022-07-29 05:30 | 23 | Tech Mahindra |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka; Mahshid Mansourian | No
'''MR2.4.1.4.6 - CU Backup Cluster Deployment, Configuration & Sanity testing''' | 2022-02-04 05:30 | 2022-02-15 05:30 | 2022-07-06 05:30 | 2022-07-29 05:30 | 23 | Tech Mahindra |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka; Mahshid Mansourian | No
'''MR2.4.2 - CDC 2 Building Network & Cloud''' | 2022-01-01 05:30 | 2022-02-15 05:30 | 2022-07-19 05:30 | 2022-10-26 05:30 | 99 | Rakuten | TechM |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Mario Catalan | No
''MR2.4.2.1 - DC Network Rollout (internal DC networking)''' | 2022-01-01 05:30 | 2022-01-10 05:30 | 2022-07-19 05:30 | 2022-08-15 05:30 | 27 | Rakuten |  |  | Not started | MR2.3.2.4 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Mario Catalan | No
''MR2.4.2.3 - Baremetal Servers Provisioning, OS installation & Hardening''' | 2022-01-11 05:30 | 2022-02-15 05:30 | 2022-08-16 05:30 | 2022-08-22 05:30 | 6 | Tech Mahindra |  |  | Not started | MR2.4.2.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
'''MR2.4.2.4 - Cloud Clusters Deployment, Configuration & Integration''' | 2022-01-11 05:30 | 2022-02-15 05:30 | 2022-09-01 05:30 | 2022-10-26 05:30 | 55 | Tech Mahindra |  |  | Not started | MR2.4.2.3.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No
'''MR2.4.2.4.1 - Secu Cluster Deployment, Configuration & Sanity testing''' | 2022-01-11 05:30 | 2022-01-21 05:30 | 2022-09-01 05:30 | 2022-09-14 05:30 | 13 | Tech Mahindra |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka; Mahshid Mansourian | No
'''MR2.4.2.4.2 - Platform Cluster Deployment, Configuration & Sanity testing''' | 2022-01-16 05:30 | 2022-01-26 05:30 | 2022-09-08 05:30 | 2022-09-21 05:30 | 13 | Tech Mahindra |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka; Mahshid Mansourian | No
'''MR2.4.2.4.3 - Auto+Orch Cluster Deployment, Configuration & Sanity testing''' | 2022-01-21 05:30 | 2022-02-03 05:30 | 2022-09-15 05:30 | 2022-10-13 05:30 | 28 | Tech Mahindra |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka; Mahshid Mansourian | No
'''MR2.4.2.4.4 - OBF Cluster Deployment, Configuration & Sanity testing''' | 2022-02-04 05:30 | 2022-02-15 05:30 | 2022-10-03 05:30 | 2022-10-25 05:30 | 22 | Tech Mahindra |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka; Mahshid Mansourian | No
'''MR2.4.2.4.5 - Mavenir Core Cluster Deployment, Configuration & Sanity testing''' | 2022-02-04 05:30 | 2022-02-15 05:30 | 2022-10-03 05:30 | 2022-10-26 05:30 | 23 | Tech Mahindra |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka; Mahshid Mansourian | No
'''MR2.4.2.4.6 - CU Backup Cluster Deployment, Configuration & Sanity testing''' | 2022-02-04 05:30 | 2022-02-15 05:30 | 2022-10-03 05:30 | 2022-10-26 05:30 | 23 | Tech Mahindra |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka; Mahshid Mansourian | No
''MR2.4 - Cloud Ready >> Milestone Date''' | 2022-01-01 05:30 | 2022-02-15 05:30 | 2022-04-21 05:30 | 2022-10-26 05:30 | 188 | Rakuten |  |  | Delayed | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Cloud | Renata Bilecka; Mahshid Mansourian | Yes
''MR2.5 - Steps Contributing to App onboarding start''' | 2022-02-15 05:30 | 2022-05-01 05:30 | 2022-05-30 05:30 | 2023-01-13 05:30 | 228 | Rakuten | Mavenir |  | Not started | '''.RAN 5G SA core pre-intgeration Test in Mainz for FWA .Cloud Ready''''''.RAN 5G SA core pre-intgeration Test in Mainz for FWA .Cloud Ready''''''.RAN 5G SA core pre-intgeration Test in Mainz for FWA .Cloud Ready''''''.RAN 5G SA core pre-intgeration Test in Mainz for FWA .Cloud Ready''''''.RAN 5G SA core pre-intgeration Test in Mainz for FWA .Cloud Ready''''''.RAN 5G SA core pre-intgeration Test in Mainz for FWA .Cloud Ready''''''.RAN 5G SA core pre-intgeration Test in Mainz for FWA .Cloud Ready''''''.RAN 5G SA core pre-intgeration Test in Mainz for FWA .Cloud Ready''''''.RAN 5G SA core pre-intgeration Test in Mainz for FWA .Cloud Ready''''''.RAN 5G SA core pre-intgeration Test in Mainz for FWA .Cloud Ready''''''.RAN 5G SA core pre-intgeration Test in Mainz for FWA .Cloud Ready''''''.RAN 5G SA core pre-intgeration Test in Mainz for FWA .Cloud Ready''''''.RAN 5G SA core pre-intgeration Test in Mainz for FWA .Cloud Ready''''''.RAN 5G SA core pre-intgeration Test in Mainz for FWA .Cloud Ready''''''.RAN 5G SA core pre-intgeration Test in Mainz for FWA .Cloud Ready''''''.RAN 5G SA core pre-intgeration Test in Mainz for FWA .Cloud Ready''' | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1 - CDC1 Core Onboarding & Testing'' | 2022-02-16 05:30 | 2022-08-03 05:30 | 2022-05-30 05:30 | 2022-11-14 05:30 | 168 | Mavenir | Rakuten |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.1 - Readiness for FWA testing (EPC + 5GC) ''' | 2022-02-16 05:30 | 2022-04-19 05:30 | 2022-05-30 05:30 | 2022-07-29 05:30 | 60 | Mavenir | Rakuten |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.1.1- Application group wise onboarding and configuration (RFI) >4G/5G Combo Core >SDM/DNS''' | 2022-02-16 05:30 | 2022-03-15 05:30 | 2022-05-30 05:30 | 2022-06-24 05:30 | 25 | Mavenir | Rakuten |  | Not started | MR2.4.1.4.5 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.1.2 - RAN & Network integration and baTechMc testing /focus on 5G SA''' | 2022-03-16 05:30 | 2022-04-05 05:30 | 2022-06-27 05:30 | 2022-07-15 05:30 | 18 | Mavenir | Rakuten |  | Not started | MR2.5.1.1.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.1.3 - Testing & Mavenir RFA''' | 2022-04-06 05:30 | 2022-04-19 05:30 | 2022-07-18 05:30 | 2022-07-29 05:30 | 11 | Mavenir | Rakuten |  | Not started | MR2.5.1.1.2 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.1.2 - RFP for FWA ATP (including basic FCAPS etc.)/RFP''' | 2022-04-20 05:30 | 2022-06-17 05:30 | 2022-08-01 05:30 | 2022-09-28 05:30 | 58 | Rakuten | QA |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.2.1 - RFP for FWA FUT only''' | 2022-04-20 05:30 | 2022-05-17 05:30 | 2022-08-01 05:30 | 2022-08-26 05:30 | 25 | Rakuten | QA |  | Not started | MR2.5.1.1.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.2.2 - Remaining RFP for overall features for FWA, IPTV , 4G Services''' | 2022-05-18 05:30 | 2022-06-17 05:30 | 2022-08-29 05:30 | 2022-09-28 05:30 | 30 | Rakuten | QA |  | Not started | MR2.5.1.2.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.3 - Readiness for FWA LIMS (other parties involved)''' | 2022-03-16 05:30 | 2022-06-07 05:30 | 2022-06-27 05:30 | 2022-09-16 05:30 | 81 | Rakuten | Mavenir |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.3.1 - LIMS Installation and Onboarding''' | 2022-03-16 05:30 | 2022-04-05 05:30 | 2022-06-27 05:30 | 2022-07-15 05:30 | 18 | Mavenir | Rakuten |  | Not started | MR2.5.1.1.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.3.2 - LIMS Integration''' | 2022-04-06 05:30 | 2022-05-17 05:30 | 2022-07-18 05:30 | 2022-08-26 05:30 | 39 | Mavenir | Rakuten |  | Not started | MR2.5.1.3.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.3.3 - Testing & Mavenir RFA''' | 2022-05-18 05:30 | 2022-06-07 05:30 | 2022-08-29 05:30 | 2022-09-16 05:30 | 18 | Mavenir | Rakuten |  | Not started | MR2.5.1.3.2 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.3.4 - RFP for FWA LIMS Testing/RFP''' | 2022-06-08 05:30 | 2022-07-19 05:30 | 2022-09-19 05:30 | 2022-10-28 05:30 | 39 | Rakuten | QA |  | Not started | MR2.5.1.3.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.4 - Readiness for eMBB Services (EPC /remaining use cases + IMS + messaging+ 3rd parties)''' | 2022-03-16 05:30 | 2022-05-31 05:30 | 2022-06-27 05:30 | 2022-09-09 05:30 | 74 | Mavenir | Rakuten |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.4.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding'''''MR2.5.1.4.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding'''''MR2.5.1.4.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding'''''MR2.5.1.4.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding'''''MR2.5.1.4.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding'''''MR2.5.1.4.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding'''''MR2.5.1.4.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding'''''MR2.5.1.4.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding'''''MR2.5.1.4.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding'''''MR2.5.1.4.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding'''''MR2.5.1.4.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding'''''MR2.5.1.4.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding'''''MR2.5.1.4.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding'''''MR2.5.1.4.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding'''''MR2.5.1.4.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding''' | 2022-03-16 05:30 | 2022-04-12 05:30 | 2022-06-27 05:30 | 2022-07-22 05:30 | 25 | Mavenir | Rakuten |  | Not started | MR2.5.1.1.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.4.2 - Network integration and baTechMc testing ''' | 2022-04-13 05:30 | 2022-04-26 05:30 | 2022-07-25 05:30 | 2022-08-05 05:30 | 11 | Mavenir | Rakuten |  | Not started | MR2.5.1.4.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.4.3 - Testing & Mavenir RFA''' | 2022-04-27 05:30 | 2022-05-31 05:30 | 2022-08-08 05:30 | 2022-09-09 05:30 | 32 | Mavenir | Rakuten |  | Not started | MR2.5.1.4.2 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.5 - RFP for eMBB ATP (including baTechMc FCAPS etc.) /RFP''' | 2022-04-27 05:30 | 2022-08-03 05:30 | 2022-09-12 05:30 | 2022-11-14 05:30 | 63 | Rakuten | QA |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.1.5.1 - RFP for eMBB FUT only''' | 2022-06-01 05:30 | 2022-06-30 05:30 | 2022-09-12 05:30 | 2022-10-11 05:30 | 29 | Rakuten | QA |  | Not started | MR2.5.1.4.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.1.5.2 - Remaining RFP for overall features for eMBB services''' | 2022-07-01 05:30 | 2022-08-03 05:30 | 2022-10-12 05:30 | 2022-11-14 05:30 | 33 | Rakuten | QA |  | Not started | MR2.5.1.5.2 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.1.6 - Readiness for eMBB LIMS (other parties involved)''' | 2022-04-27 05:30 | 2022-06-14 05:30 | 2022-08-08 05:30 | 2022-09-23 05:30 |  | Rakuten | Mavenir |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.1.6.1 - LIMS Integration''' | 2022-04-27 05:30 | 2022-05-17 05:30 | 2022-08-08 05:30 | 2022-08-26 05:30 |  | Mavenir | Rakuten |  | Not started | MR2.5.1.4.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.1.6.2 - Testing & Mavenir RFA''' | 2022-05-18 05:30 | 2022-06-14 05:30 | 2022-08-29 05:30 | 2022-09-23 05:30 |  | Mavenir | Rakuten |  | Not started | MR2.5.1.6.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.1.6.3 - RFP for eMBB LIMS Testing/RFP''' | 2022-06-15 05:30 | 2022-07-26 05:30 | 2022-09-26 05:30 | 2022-11-04 05:30 |  | Rakuten | QA |  | Not started | MR2.5.1.6.2 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.1.7 - Readiness for NR & IC / RFI''' | 2022-05-06 05:30 | 2022-06-02 05:30 | 2022-08-17 05:30 | 2022-09-13 05:30 | 27 | Rakuten | Mavenir |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.1.7.1 - NR nodes installation + internal integration and basic sanity testing''' | 2022-05-06 05:30 | 2022-06-02 05:30 | 2022-08-17 05:30 | 2022-09-13 05:30 | 0 | Mavenir | Rakuten |  | Not started | 'MR2.5.1.1.3 - 18 working days' | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.2 - CDC2 Core Onboarding & Testing'' | 2022-02-16 05:30 | 2022-08-03 05:30 | 2022-08-01 05:30 | 2023-01-20 05:30 | 184 | Rakuten | Mavenir |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'''MR2.5.2.1 - Readiness for FWA testing (EPC + 5GC) ''' | 2022-02-16 05:30 | 2022-04-19 05:30 | 2022-08-01 05:30 | 2022-09-23 05:30 | 55 | Mavenir | Rakuten |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.2.1.1 - Application group wise onboarding and configuration (RFI) >4G/5G Combo Core >SDM/DNS'''''MR2.5.2.1.1 - Application group wise onboarding and configuration (RFI) >4G/5G Combo Core >SDM/DNS'''''MR2.5.2.1.1 - Application group wise onboarding and configuration (RFI) >4G/5G Combo Core >SDM/DNS'''''MR2.5.2.1.1 - Application group wise onboarding and configuration (RFI) >4G/5G Combo Core >SDM/DNS'''''MR2.5.2.1.1 - Application group wise onboarding and configuration (RFI) >4G/5G Combo Core >SDM/DNS'''''MR2.5.2.1.1 - Application group wise onboarding and configuration (RFI) >4G/5G Combo Core >SDM/DNS'''''MR2.5.2.1.1 - Application group wise onboarding and configuration (RFI) >4G/5G Combo Core >SDM/DNS'''''MR2.5.2.1.1 - Application group wise onboarding and configuration (RFI) >4G/5G Combo Core >SDM/DNS'''''MR2.5.2.1.1 - Application group wise onboarding and configuration (RFI) >4G/5G Combo Core >SDM/DNS'''''MR2.5.2.1.1 - Application group wise onboarding and configuration (RFI) >4G/5G Combo Core >SDM/DNS'''''MR2.5.2.1.1 - Application group wise onboarding and configuration (RFI) >4G/5G Combo Core >SDM/DNS'''''MR2.5.2.1.1 - Application group wise onboarding and configuration (RFI) >4G/5G Combo Core >SDM/DNS'''''MR2.5.2.1.1 - Application group wise onboarding and configuration (RFI) >4G/5G Combo Core >SDM/DNS'''''MR2.5.2.1.1 - Application group wise onboarding and configuration (RFI) >4G/5G Combo Core >SDM/DNS''' | 2022-02-16 05:30 | 2022-03-15 05:30 | 2022-08-01 05:30 | 2022-08-12 05:30 | 0 | Mavenir | Rakuten |  | Not started | 'MR2.4.2.4.5 + MR2.5.1.1.3' | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.2.1.2 - RAN & Network integration and baTechMc testing /focus on 5G SA''' | 2022-03-16 05:30 | 2022-04-05 05:30 | 2022-08-15 05:30 | 2022-08-26 05:30 | 0 | Mavenir | Rakuten |  | Not started | MR2.5.2.1.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.2.1.3 - Mavenir internal testing and Sanity check ''' | 2022-04-06 05:30 | 2022-04-19 05:30 | 2022-08-29 05:30 | 2022-09-23 05:30 | 0 | Mavenir | Rakuten |  | Not started | MR2.5.2.1.2 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.2.2 - RFA for FWA ATP (including baTechMc FCAPS etc.)/RFS''' | 2022-04-20 05:30 | 2022-06-17 05:30 | 2022-09-26 05:30 | 2022-11-18 05:30 | 55 | Rakuten | QA |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.2.2.1 Functional testing + Geo-redundancy & interworking between 2 CDCs (only FWA)'' | 2022-04-20 05:30 | 2022-05-17 05:30 | 2022-09-26 05:30 | 2022-10-21 05:30 | 0 | Rakuten | QA |  | Not started | MR2.5.2.1.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.2.2.2 Non Functional Testing'' | 2022-05-18 05:30 | 2022-06-17 05:30 | 2022-10-24 05:30 | 2022-11-18 05:30 |  | Rakuten | QA |  | Not started | MR2.5.2.1.4 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.2.3 - Readiness for FWA LIMS (other parties involved)''' | 2022-03-16 05:30 | 2022-06-07 05:30 | 2022-09-19 05:30 | 2022-11-08 05:30 | 50 | Rakuten | Mavenir |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.2.3.1 - LIMS Installation and Onboarding''' | 2022-03-16 05:30 | 2022-04-05 05:30 | 2022-09-19 05:30 | 2022-10-07 05:30 | 0 | Mavenir | Rakuten |  | Not started | MR2.5.1.3.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.2.3.2 - LIMS Integration''' | 2022-04-06 05:30 | 2022-05-17 05:30 | 2022-10-10 05:30 | 2022-10-25 05:30 | 0 | Mavenir | Rakuten |  | Not started | MR2.5.2.3.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.2.3.3 - Testing & Mavenir RFA''' | 2022-05-18 05:30 | 2022-06-07 05:30 | 2022-10-26 05:30 | 2022-11-08 05:30 | 0 | Mavenir | Rakuten |  | Not started | MR2.5.2.3.2 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.2.4 - RFP for FWA LIMS Testing/RFP''' | 2022-06-08 05:30 | 2022-07-19 05:30 | 2022-11-09 05:30 | 2022-12-06 05:30 | 27 | Rakuten | QA |  | Not started | MR2.5.2.3.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.2.5 - Readiness for eMBB Services (EPC /remaining use cases + IMS + messaging+ 3rd parties)''' | 2022-03-16 05:30 | 2022-05-31 05:30 | 2022-09-12 05:30 | 2022-11-18 05:30 | 67 | Mavenir | Rakuten |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.2.5.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding''''MR2.5.2.5.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding''''MR2.5.2.5.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding''''MR2.5.2.5.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding''''MR2.5.2.5.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding''''MR2.5.2.5.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding''''MR2.5.2.5.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding''''MR2.5.2.5.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding''''MR2.5.2.5.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding''''MR2.5.2.5.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding''''MR2.5.2.5.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding''''MR2.5.2.5.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding''''MR2.5.2.5.1 - Application group wise onboarding and configuration (RFI) >EPC /remaining use cases (configuration changes only) >IMS >messaging >Third parties on boarding''' | 2022-03-16 05:30 | 2022-04-12 05:30 | 2022-09-12 05:30 | 2022-09-30 05:30 | 0 | Mavenir | Rakuten |  | Not started | MR2.5.1.4.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5.2.5.2 - Network integration and baTechMc testing ''' | 2022-04-13 05:30 | 2022-04-26 05:30 | 2022-10-03 05:30 | 2022-10-21 05:30 | 0 | Mavenir | Rakuten |  | Not started | MR2.5.2.5.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.2.5.3 - Mavenir internal testing and Sanity check /RFA''' | 2022-04-27 05:30 | 2022-05-31 05:30 | 2022-10-24 05:30 | 2022-11-18 05:30 | 0 | Mavenir | Rakuten |  | Not started | MR2.5.2.5.2 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.2.6 - RFA for eMBB ATP (including baTechMc FCAPS etc.) /RFS ''' | 2022-04-27 05:30 | 2022-08-03 05:30 | 2022-11-21 05:30 | 2023-01-13 05:30 | 53 | Rakuten | QA |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.2.6.1 - Functional testing + Geo-redundancy & interworking between 2 CDCs (only eMBB)'' | 2022-06-01 05:30 | 2022-06-30 05:30 | 2022-11-21 05:30 | 2022-12-16 05:30 | 0 | Rakuten | QA |  | Not started | MR2.5.2.5.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.2.6.2 - Non Functional Testing'' | 2022-07-01 05:30 | 2022-08-03 05:30 | 2022-12-19 05:30 | 2023-01-13 05:30 |  | Rakuten | QA |  | Not started | MR2.5.2.6.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.2.7 - Readiness for eMBB LIMS (other parties involved)''' | 2022-04-27 05:30 | 2022-06-14 05:30 | 2022-10-24 05:30 | 2022-12-09 05:30 |  | Rakuten | Mavenir |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.2.7.1 - LIMS Integration''' | 2022-04-27 05:30 | 2022-05-17 05:30 | 2022-10-24 05:30 | 2022-11-11 05:30 |  | Mavenir | Rakuten |  | Not started | MR2.5.2.5.2 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.2.7.2 - Testing & Mavenir RFA''' | 2022-05-18 05:30 | 2022-06-14 05:30 | 2022-11-14 05:30 | 2022-12-09 05:30 |  | Mavenir | Rakuten |  | Not started | MR2.5.2.7.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.2.7.3 - RFP for eMBB LIMS Testing/RFP''' | 2022-06-15 05:30 | 2022-07-26 05:30 | 2022-12-12 05:30 | 2023-01-20 05:30 |  | Rakuten | QA |  | Not started | MR2.5.2.7.2 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.2.8 - Readiness for NR & IC / RFI''' | 2022-05-06 05:30 | 2022-06-02 05:30 | 2022-11-21 05:30 | 2022-12-16 05:30 | 25 | Rakuten | Mavenir |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MR2.5.2.8.1 - NR nodes installation + internal integration and basic sanity testing''' | 2022-05-06 05:30 | 2022-06-02 05:30 | 2022-11-21 05:30 | 2022-12-16 05:30 | 0 | Mavenir | Rakuten |  | Not started | MR2.5.2.5.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
''MR2.5 - App onboarding start >> Milestone Date''' | 2022-05-01 05:30 | 2022-05-01 05:30 | 2022-05-01 05:30 | 2022-05-01 05:30 | 0 | Rakuten |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.6 - Steps Contributing CDC1&2 readiness small scale''' | 2022-01-01 05:30 | 2022-01-11 05:30 | 2022-05-26 05:30 | 2022-06-08 05:30 | 155 | Rakuten |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
'''MR2.6.1 - CDC 1 readiness small scale''' | 2022-01-01 05:30 | 2022-07-01 05:30 | 2022-05-26 05:30 | 2023-02-20 05:30 | 155 | Rakuten |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.6.1.1 - Infrastructure E2E Integration, Testing and Acceptance''' | 2022-01-01 05:30 | 2022-01-11 05:30 | 2022-05-26 05:30 | 2022-06-08 05:30 | 13 | Rakuten |  |  | Not started | MR2.4.1.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.6.1.2 - E2E Testing + CDC RFS (testing & acceptance)''' | 2022-04-08 05:30 | 2022-07-01 05:30 | 2023-01-17 05:30 | 2023-02-20 05:30 | 53 | Rakuten |  |  | Not started | MR2.5.1.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
'''MR2.6.2 - CDC 2 readiness small scale''' | 2022-01-01 05:30 | 2022-07-01 05:30 | 2022-08-10 05:30 | 2022-10-04 05:30 | 148 | Rakuten |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.6.2.1 - Infrastructure E2E Integration, Testing and Acceptance''' | 2022-01-01 05:30 | 2022-01-11 05:30 | 2022-08-23 05:30 | 2022-09-05 05:30 | 11 | Rakuten |  |  | Not started | MR2.4.2.3 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.6.2.2 - E2E Testing + CDC RFS (testing & acceptance)''' | 2022-04-08 05:30 | 2022-07-01 05:30 | 2022-08-10 05:30 | 2022-10-04 05:30 | 55 | Rakuten |  |  | Not started | MR2.5.2.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.6 - CDC1&2 readiness small scale >> Milestone Date''' | 2022-01-01 05:30 | 2022-01-11 05:30 | 2022-05-26 05:30 | 2022-06-08 05:30 | 0 | Rakuten |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.7 - Steps Contributing CDC1&2 readiness FWA scale''' | 2022-07-01 05:30 | 2022-12-31 05:30 | 2023-02-21 05:30 | 2023-05-12 05:30 | 106 | Rakuten |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.7.2 - CDC 1 confirmation of readiness for FWA'' | 2022-07-01 05:30 | 2022-12-31 05:30 | 2023-02-21 05:30 | 2023-05-01 05:30 | 67 | Rakuten |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.7.2.1 - KPI measurement (for infrastructure)''' | 2022-07-01 05:30 | 2022-11-30 05:30 | 2023-02-21 05:30 | 2023-03-20 05:30 | 25 | Rakuten |  |  | Not started | MR2.6.1.2 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.7.2.2 - CDC Services go into Operations after acceptance''' | 2022-07-01 05:30 | 2022-11-30 05:30 | 2023-02-21 05:30 | 2023-02-27 05:30 | 4 | Rakuten |  |  | Not started | MR2.6.1.2 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.7.2.3 - CDC Payment Equipment at Final Acceptance''' | 2022-12-01 05:30 | 2022-12-31 05:30 | 2023-03-21 05:30 | 2023-05-01 05:30 | 39 | 1&1 |  |  | Not started | MR2.7.2.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.7.3 - CDC 2 confirmation of readiness for FWA'' | 2022-07-01 05:30 | 2022-12-31 05:30 | 2023-03-06 05:30 | 2023-05-12 05:30 | 69 | Rakuten |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.7.3.1 - KPI measurement (for infrastructure)''' | 2022-07-01 05:30 | 2022-11-30 05:30 | 2023-03-06 05:30 | 2023-03-31 05:30 | 27 | Rakuten |  |  | Not started | MR2.6.2.2 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.7.3.2 - CDC Services go into Operations after acceptance''' | 2022-07-01 05:30 | 2022-11-30 05:30 | 2023-03-06 05:30 | 2023-03-10 05:30 | 6 | Rakuten |  |  | Not started | MR2.6.2.2 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.7.3.3 - CDC Payment Equipment at Final Acceptance''' | 2022-12-01 05:30 | 2022-12-31 05:30 | 2023-04-03 05:30 | 2023-05-12 05:30 | 41 | 1&1 |  |  | Not started | MR2.7.3.1 | [9 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.7 - CDC1&2 readiness FWA scale >> Milestone Date''' | 2022-07-01 05:30 | 2022-12-31 05:30 | 2023-02-21 05:30 | 2023-05-12 05:30 | 0 | Rakuten |  |  | Not started | [10 empty] | FWA | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.8 - CDC1&2 readiness scale 1M users per CDC >> Milestone Date''' | 2023-08-30 05:30 | 2023-08-30 05:30 | 2023-08-30 05:30 | 2023-08-30 05:30 | 0 | Rakuten |  |  | Not started | ''Y23.1 - CDC1 Expansion Steps for Y23, Y23.2 - CDC2 Expansion Steps for Y23''' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MRR - Interconnects National & International Roaming '' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MRR1.1 - CDC1 Interconnects'' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
MR2.1.2.9.4 Order Versatel fixed line interconnection |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.1.2.9.5 Versatel fixed line interconnection - Destination: Versatel (x1)'' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.1.2.9.6 DTAG fixed line interconnection - Destination: DTAG (x1) - delivery completed'' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
MR2.1.2.9.7 Telefonica Order date (to Versatel) |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.1.2.9.8 Telefonica - national roaming - Destination: Telefonica (x2)'' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
MR2.1.2.9.9 Vodafone Order date |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.1.2.9.10 Vodafone - mobile interconnect - Destination: Vodafone (x1)'' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
MR2.1.2.9.11 Deutsche Telekom Order date |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.1.2.9.12 Deutsche Telekom - mobile interconnect - Destination: DTAG (x1)'' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
MR2.1.2.9.13 International Roaming Broker Order date |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.1.2.9.14 International Roaming (Broker) - Destination: Roaming Partner (x1)'' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.1.2.9.15 SMS hub - Destination: SMS Partner (x1)'' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MRR1.2 - CDC2 Interconnects'' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
MR2.1.2.9.4 Order Versatel fixed line interconnection |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.1.2.9.5 Versatel fixed line interconnection - Destination: Versatel (x1)'' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.1.2.9.6 DTAG fixed line interconnection - Destination: DTAG (x1) - delivery completed'' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
MR2.1.2.9.7 Telefonica Order date (to Versatel) |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.1.2.9.8 Telefonica - national roaming - Destination: Telefonica (x2)'' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
MR2.1.2.9.9 Vodafone Order date |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.1.2.9.10 Vodafone - mobile interconnect - Destination: Vodafone (x1)'' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
MR2.1.2.9.11 Deutsche Telekom Order date |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.1.2.9.12 Deutsche Telekom - mobile interconnect - Destination: DTAG (x1)'' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
MR2.1.2.9.13 International Roaming Broker Order date |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.1.2.9.14 International Roaming (Broker) - Destination: Roaming Partner (x1)'' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
''MR2.1.2.9.15 SMS hub - Destination: SMS Partner (x1)'' |  |  |  |  | 0 |  |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | Yes
'MRR1.3 - National Roaming & Interconnects''' | 2021-06-15 05:30 | 2024-01-04 05:30 | 2021-06-15 05:30 | 2024-01-04 05:30 | 0 | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1 - Telefonica NR IC- CDC 1/2/3/4''' | 2022-01-20 05:30 | 2024-01-04 05:30 | 2022-01-20 05:30 | 2024-01-04 05:30 | 40.04166667 | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.1 - Order Connectivity TEF/CDC 1"' | 2022-01-20 05:30 | 2022-01-20 05:30 | 2022-01-20 05:30 | 2022-01-20 05:30 | 40.04166667 | 1&1 | Ali Unlu |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.2 - Delivery Lead time (physical circuit 2x 100G)"' | 2022-01-21 05:30 | 2022-08-02 05:30 | 2022-01-21 05:30 | 2022-08-02 05:30 | 45 | VER Wholesale | VER Wholesale |  | Not started | MRR1.3.1.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.3 - [Versatel/TEF] (Offenbach vs. Mainz) - Physical and logical Integration' | 2022-08-03 05:30 | 2022-08-16 05:30 | 2022-08-03 05:30 | 2022-08-16 05:30 | 13 | Rakuten transport | VER Transport & RAK Transport & TEF |  | Not started | MRR1.3.1.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.4 - Test Connection' | 2022-08-17 05:30 | 2022-08-30 05:30 | 2022-08-17 05:30 | 2022-08-30 05:30 | 82.95833333 | Rakuten transport | VER Transport & RAK Transport & TEF |  | Not started | MRR1.3.1.3 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.5 - TEF Lab Intregration' | 2022-10-14 05:30 | 2022-10-27 05:30 | 2022-10-14 05:30 | 2022-10-27 05:30 | 13 | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.5.1 - Service Integration of Prod. CDC 1 to TEF LAB (including some TEF live components)' | 2022-07-05 05:30 | 2022-07-18 05:30 | 2022-10-14 05:30 | 2022-10-27 05:30 | 83.04166667 | Rakuten | 'RAK+Mavenir, TEF' |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.6 - [Internal Pre-test CDC 1 to Tef Lab] - Internal Testing , Acceptance and Sanity Check' | 2022-07-19 05:30 | 2022-08-29 05:30 | 2022-10-28 05:30 | 2022-12-08 05:30 | 0 | Rakuten | 'RAK+Mavenir, TEF (RAK in lead)' |  | Not started | MRR1.3.1.5.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.7 - [TEF Pre-test] Test readiness for TEF lab vs. DRI live (voice, data, sms)' | 2022-08-30 05:30 | 2022-09-26 05:30 | 2022-12-09 05:30 | 2023-01-05 05:30 | 0 | Telefonica | 'RAK+Mavenir, TEF (TEF in lead)' |  | Not started | MRR1.3.1.6 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.8 - [TEF LAB Testing] Test readiness for TEF lab vs. DRI live (voice, data, sms)' | 2022-09-27 05:30 | 2022-10-10 05:30 | 2023-01-06 05:30 | 2023-01-19 05:30 |  | Telefonica | 'RAK+Mavenir, TEF (TEF in lead)' |  | Not started | MRR1.3.1.7 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.9 - Live FOA integration' | 2022-08-30 05:30 | 2022-10-24 05:30 | 2022-11-25 05:30 | 2023-01-31 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.9.1 - [TEF FOA Live / DRI Live] - Logical connectivity' | 2022-08-30 05:30 | 2022-10-10 05:30 | 2022-11-25 05:30 | 2023-01-05 05:30 |  | Rakuten transport | VER Transport & RAK Transport & TEF |  | Not started | 'MRR1.3.1.2 + 72 working days' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.9.2 - Service Integration of Prod. CDC 1 to Prod. TEF live FOA' | 2022-10-11 05:30 | 2022-10-24 05:30 | 2023-01-18 05:30 | 2023-01-31 05:30 |  | Rakuten | 'RAK+Mavenir, TEF' |  | Not started | 'MRR1.3.1.9.1 + 8 working days' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.10 - [Pre-test CDC 1 to Tef FOA Live] - Internal Testing , Acceptance and Sanity Check' | 2022-10-25 05:30 | 2022-12-05 05:30 | 2023-02-01 05:30 | 2023-03-14 05:30 |  | Rakuten | 'RAK+Mavenir, TEF (RAK in lead)' |  | Not started | MRR1.3.1.9.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.11 - [Telefonica FOA LIVE Testing] - Test readiness for TEF live vs. DRI live' | 2022-12-06 05:30 | 2023-01-16 05:30 | 2023-03-15 05:30 | 2023-04-25 05:30 |  | Telefonica | 'RAK+Mavenir, TEF (TEF in lead)' |  | Not started | MRR1.3.1.10 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.12 - Order Connectivity TEF/CDC 2/3/4' | 2022-10-26 05:30 | 2022-10-26 05:30 | 2022-10-26 05:30 | 2022-10-26 05:30 |  | 1&1 | Ali Unlu |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.13 - Delivery Lead time TEF to CDC 2/3/4 (physical circuit)' | 2022-10-27 05:30 | 2023-04-25 05:30 | 2022-10-27 05:30 | 2023-04-25 05:30 |  | VER Wholesale | VER Wholesale |  | Not started | MRR1.3.1.12 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.14 - Circuits delivery TEF to CDC 2/3/4' | 2023-04-25 05:30 | 2023-04-25 05:30 | 2023-04-25 05:30 | 2023-04-25 05:30 |  | VER Wholesale | VER Wholesale |  | Not started | MRR1.3.1.13 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.15 - Live integration' | 2022-12-06 05:30 | 2023-01-16 05:30 | 2023-02-20 05:30 | 2023-03-23 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.15.1 - [1&1 E2E TEF LIVE ] Logical Connectivity from CDC1 to remaining Prod. TEF Sites' | 2022-12-06 05:30 | 2023-01-16 05:30 | 2023-02-20 05:30 | 2023-03-23 05:30 |  | Rakuten transport | VER Transport & RAK Transport & TEF |  | Not started | 'MRR1.3.1.2 + 133 working days' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.15.2 - Service Integrate Prod. CDC 1 to remaining Prod. TEF sites' | 2023-01-17 05:30 | 2023-01-30 05:30 | 2023-04-26 05:30 | 2023-05-09 05:30 |  | Rakuten | 'RAK+Mavenir, TEF' |  | Not started | 'MRR1.3.1.15.1 + 17 working days' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.16 - Rollout NR Config to CDC 2,3&4' | 2023-01-17 05:30 | 2023-01-30 05:30 | 2023-04-26 05:30 | 2023-05-09 05:30 |  | Rakuten | 'RAK+Mavenir, TEF' |  | Not started | MRR1.3.1.14 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.17 - [1&1 E2E Functional LIVE Testing] Testing , Acceptance and Sanity Check' | 2023-01-31 05:30 | 2023-03-27 05:30 | 2023-05-10 05:30 | 2023-07-04 05:30 |  | Rakuten | 'RAK + TEF (RAK in lead)' |  | Not started | MRR1.3.1.15.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.18 - Ops & Regression Test' | 2023-03-28 05:30 | 2023-04-24 05:30 | 2023-07-05 05:30 | 2023-08-01 05:30 |  | Rakuten | RAK |  | Not started | MRR1.3.1.17 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.19 - NR FUP (Friendly User Phase)' | 2023-04-25 05:30 | 2023-07-24 05:30 | 2023-08-02 05:30 | 2023-10-31 05:30 |  | 1&1 | '1&1 + RAK (1&1 in the lead)' |  | Not started | MRR1.3.1.18 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.20 - Migration Pre- Test' | 2023-04-25 05:30 | 2023-07-24 05:30 | 2023-08-02 05:30 | 2023-10-31 05:30 |  | to be defined | RAK, TEF, 1&1 (lead to be defined later) |  | Not started | MRR1.3.1.18 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.21 - NR / eMBB Launch' | 2023-07-25 05:30 | 2023-07-25 05:30 | 2023-11-01 05:30 | 2023-11-01 05:30 |  | 1&1 | 1&1 |  | Not started | 'MRR1.3.1.20 + 1 working day' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.22 - Stability phase' | 2023-07-26 05:30 | 2023-09-26 05:30 | 2023-11-02 05:30 | 2024-01-03 05:30 |  | Rakuten | RAK |  | Not started | MRR1.3.1.21 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.23 - Acceptance of stability and migration readiness' | 2023-09-26 05:30 | 2023-09-26 05:30 | 2024-01-03 05:30 | 2024-01-03 05:30 |  | 1&1 | 1&1 |  | Not started | MRR1.3.1.22 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.24 - Migration' | 2023-08-24 05:30 | 2023-09-27 05:30 | 2023-12-01 05:30 | 2024-01-03 05:30 |  | to be defined | '1&1 + RAK' |  | Not started | MRR1.3.1.23 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2 - IC - CDC 1''' | 2022-04-04 05:30 | 2023-08-15 05:30 | 2022-04-04 05:30 | 2023-08-15 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.1 - TEF Mobile IC - CDC 1"' | 2022-08-31 05:30 | 2023-05-23 05:30 | 2022-08-31 05:30 | 2023-05-23 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.1.1 - Lab integr.' | 2022-05-20 05:30 | 2022-07-07 05:30 | 2022-08-31 05:30 | 2022-10-18 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.1.1.1 - [TEF Lab / DRI Live] - Logical connectivity' | 2022-05-20 05:30 | 2022-06-02 05:30 | 2022-08-31 05:30 | 2022-09-13 05:30 |  | Rakuten transport | VER Transport & RAK Transport & TEF |  | Not started | 'MRR1.3.1.3 + 10 working days' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.1.1.2 - Service Integration of Prod. CDC 1 to TEF LAB' | 2022-06-03 05:30 | 2022-07-07 05:30 | 2022-09-14 05:30 | 2022-10-18 05:30 |  | Rakuten | 'RAK+Mavenir, TEF' |  | Not started | 'MRR1.3.2.1.1.1 + MR2.5.1.4.3 + MR2.5.1.7.1' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.1.2 - [Testing Lab] Testing , Acceptance and Sanity Check' | 2022-07-08 05:30 | 2022-09-22 05:30 | 2022-10-19 05:30 | 2023-01-03 05:30 |  | Rakuten | 'RAK + TEF' |  | Not started | 'MRR1.3.2.1.1.2 + MR2.5.1.5.2' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.1.3 - Live FOA integr.' | 2022-08-12 05:30 | 2022-10-06 05:30 | 2022-11-23 05:30 | 2023-01-17 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.1.3.1 - [TEF FOA Live / DRI Live] - Logical connectivity' | 2022-08-12 05:30 | 2022-09-22 05:30 | 2022-11-23 05:30 | 2023-01-03 05:30 |  | Rakuten transport | VER Transport & RAK Transport & TEF |  | Not started | 'MRR1.3.1.3 + 70 working days' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.1.1.3.2 - Service Integration of Prod. CDC 1 to TEF FOA Live' | 2022-09-23 05:30 | 2022-10-06 05:30 | 2023-01-03 05:30 | 2023-01-17 05:30 |  | Rakuten | 'RAK+Mavenir, TEF' |  | Not started | 'MRR1.3.2.1.3.1 + MR2.5.1.4.3 + MR2.5.1.7.1' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.1.4 - [Testing FOA Live] Testing , Acceptance and Sanity Check' | 2022-10-07 05:30 | 2022-12-01 05:30 | 2023-01-18 05:30 | 2023-03-14 05:30 |  | Rakuten | 'RAK + TEF' |  | Not started | 'MRR1.3.1.1.3.2 + MR2.5.1.5.2' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.1.5 - Live integr.' | 2022-12-02 05:30 | 2023-03-14 05:30 | 2023-02-01 05:30 | 2023-03-28 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.1.5.1 - [1&1 E2E TEF LIVE ] Logical Connectivity from CDC1 to remaining Prod. TEF Sites' | 2023-02-01 05:30 | 2023-03-14 05:30 | 2023-02-01 05:30 | 2023-03-14 05:30 |  | Rakuten transport | VER Transport & RAK Transport & TEF |  | Not started | 'MRR1.3.1.3 + 120 working days' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.1.5.2 - Service Integrate Prod. CDC 1 to remaining Prod. TEF sites' | 2022-12-02 05:30 | 2022-12-15 05:30 | 2023-03-15 05:30 | 2023-03-28 05:30 |  | Rakuten | 'RAK+Mavenir, TEF' |  | Not started | 'MRR1.3.2.1.5.1 + MR2.5.1.4.3 + MR2.5.1.7.1' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.1.6 - [Testing Live] Testing , Acceptance and Sanity Check' | 2022-12-16 05:30 | 2023-02-09 05:30 | 2023-03-29 05:30 | 2023-05-23 05:30 |  | Rakuten | 'RAK + TEF + 1&1' |  | Not started | 'MRR1.3.2.1.5.2 + MR2.5.1.5.2' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.1.7 - Telefonica Mobile IC (CDC 1) Readiness' | 2023-02-09 05:30 | 2023-02-09 05:30 | 2023-05-23 05:30 | 2023-05-23 05:30 |  | Rakuten |  |  | Not started | MRR1.3.2.1.6 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.2 - Versatel Fixed IC - CDC 1"' | 2022-04-04 05:30 | 2022-12-20 05:30 | 2022-04-04 05:30 | 2022-12-20 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.2.1 - Pre test' | 2022-04-04 05:30 | 2022-05-20 05:30 | 2022-04-04 05:30 | 2022-05-20 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.2.1.1 - Pre-test Configuration - Lab to Mainz Lab (internet links)' | 2022-04-04 05:30 | 2022-04-15 05:30 | 2022-04-04 05:30 | 2022-04-15 05:30 |  | Rakuten transport | VER Transport & RAK Transport |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.2.1.2 - Pre-Testing Lab-Lab' | 2022-04-18 05:30 | 2022-05-20 05:30 | 2022-04-18 05:30 | 2022-05-20 05:30 |  | Rakuten | 'RAK+Mavenir, Versatel' |  | Not started | MRR1.3.2.2.1.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.2.2 - Lab integr.' | 2022-06-03 05:30 | 2022-09-23 05:30 | 2022-09-12 05:30 | 2022-10-07 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.2.2.1 - [VSL Lab / DRI Live] Logical connectivity' | 2022-09-12 05:30 | 2022-09-23 05:30 | 2022-09-12 05:30 | 2022-09-23 05:30 |  | Rakuten transport | VER Transport & RAK Transport |  | Not started | 'MRR1.3.2.2.1.2 + 80 working days' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.2.2.2 - Service Integration of Prod. CDC 1 to Versatel' | 2022-06-03 05:30 | 2022-06-16 05:30 | 2022-09-26 05:30 | 2022-10-07 05:30 |  | Rakuten | 'RAK+Mavenir, Versatel' |  | Not started | 'MRR1.3.2.2.2.1 + MR2.5.1.4.3 + MR2.5.1.7.1' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.2.3 - [Testing Lab] Testing , Acceptance and Sanity Check' | 2022-06-17 05:30 | 2022-06-30 05:30 | 2022-10-12 05:30 | 2022-10-25 05:30 |  | Rakuten | 'RAK + Versatel + 1&1' |  | Not started | 'MRR1.3.2.2.2.2 + MR2.5.1.5.2' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.2.4 - Live integr.' | 2022-05-20 05:30 | 2022-07-14 05:30 | 2022-10-26 05:30 | 2022-12-06 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.2.4.1 - [VSL Live / DRI Live] Logical connectivity' | 2022-05-20 05:30 | 2022-06-30 05:30 | 2022-10-26 05:30 | 2022-12-06 05:30 |  | Rakuten transport | VER Transport & RAK Transport |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.2.4.2 - Service Integration Live to CDC 1' | 2022-07-01 05:30 | 2022-07-14 05:30 | 2022-10-26 05:30 | 2022-11-08 05:30 |  | Rakuten | 'RAK+Mavenir, Versatel' |  | Not started | MRR1.3.2.2.3 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.2.5 - [Testing Live] - Testing, Acceptance and Sanity Check' | 2022-07-15 05:30 | 2022-08-25 05:30 | 2022-11-09 05:30 | 2022-12-20 05:30 |  | Rakuten | 'RAK + Versatel + 1&1' |  | Not started | MRR1.3.2.2.4.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.2.6 - Versatel fixed line IC (CDC 1) readiness' | 2022-08-25 05:30 | 2022-08-25 05:30 | 2022-12-20 05:30 | 2022-12-20 05:30 |  | Rakuten |  |  | Not started | MRR1.3.2.2.5 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.3 - Deutsche Telekom Mobile IC - CDC 1"' | 2021-10-04 05:30 | 2023-03-07 05:30 | 2023-05-29 05:30 | 2023-06-16 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.3.1 - DTAG Live Intreg.' | 2021-10-04 05:30 | 2023-02-28 05:30 | 2023-05-29 05:30 | 2023-06-09 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.3.1.1 - [DTAG Live / DRI Live] - Logical Connectivity' | 2021-10-04 05:30 | 2023-02-21 05:30 | 2023-05-29 05:30 | 2023-06-02 05:30 |  | Rakuten transport | VER Transport & RAK Transport & DTAG |  | Not started | 'MRR1.3.4.3.4 + 40 working days' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.3.1.2 - Service Integration of Prod. CDC 1 to DTAG Live' | 2023-02-22 05:30 | 2023-02-28 05:30 | 2023-06-05 05:30 | 2023-06-09 05:30 |  | Rakuten | 'RAK+Mavenir, DTAG' |  | Not started | MRR1.3.2.3.1.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.3.2 - [Testing Live] Testing , Acceptance and Sanity Check' | 2023-03-01 05:30 | 2023-03-07 05:30 | 2023-06-12 05:30 | 2023-06-16 05:30 |  | Rakuten | 'RAK + DTAG + 1&1' |  | Not started | MRR1.3.2.3.1.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.3.3 - DTAG Mobile IC (CDC 1) readiness' | 2023-03-07 05:30 | 2023-03-07 05:30 | 2023-06-16 05:30 | 2023-06-16 05:30 |  | Rakuten |  |  | Not started | MRR1.3.2.3.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.4 - International Roaming IC - CDC 1"' | 2023-07-27 05:30 | 2023-08-16 05:30 | 2023-07-26 05:30 | 2023-08-15 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.4.1 - Broker Live Intreg.' | 2023-07-27 05:30 | 2023-08-09 05:30 | 2023-07-26 05:30 | 2023-08-08 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.4.1.1 - [Broker Live / DRI Live] Logical Connectivity' | 2023-07-27 05:30 | 2023-08-02 05:30 | 2023-07-26 05:30 | 2023-08-01 05:30 |  | Rakuten transport | VER Transport & RAK Transport & Broker |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.4.1.2 - Service Integration of Prod. CDC 1 to Broker Live' | 2023-08-03 05:30 | 2023-08-09 05:30 | 2023-08-02 05:30 | 2023-08-08 05:30 |  | Rakuten | 'RAK+Mavenir, Broker' |  | Not started | MRR1.3.2.4.1.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.4.2 - [Testing Live] Testing , Acceptance and Sanity Check' | 2023-08-10 05:30 | 2023-08-16 05:30 | 2023-08-09 05:30 | 2023-08-15 05:30 |  | Rakuten | 'RAK + Broker + 1&1' |  | Not started | MRR1.3.2.4.1.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.4.3 - Broker Mobile IC (CDC 1) readiness' | 2023-08-16 05:30 | 2023-08-16 05:30 | 2023-08-15 05:30 | 2023-08-15 05:30 |  | Rakuten |  |  | Not started | MRR1.3.2.4.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.5 - SMS Hub international - CDC 1"' | 2022-12-27 05:30 | 2023-01-13 05:30 | 2023-03-20 05:30 | 2023-04-07 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.5.1 - SMS Live Intreg.' | 2022-12-27 05:30 | 2023-01-06 05:30 | 2023-03-20 05:30 | 2023-03-31 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.5.1.1 - [SMS Live / DRI Live] - Logical connectivity' | 2022-12-27 05:30 | 2022-12-30 05:30 | 2023-03-20 05:30 | 2023-03-24 05:30 |  | Rakuten transport | VER Transport & RAK Transport & Broker |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.5.1.2 - Service Integration of Prod. CDC 1 to SMS Live' | 2023-01-02 05:30 | 2023-01-06 05:30 | 2023-03-27 05:30 | 2023-03-31 05:30 |  | Rakuten | 'RAK+Mavenir, Broker' |  | Not started | MRR1.3.2.5.1.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.5.2 - [Testing Live] Testing , Acceptance and Sanity Check' | 2023-01-09 05:30 | 2023-01-13 05:30 | 2023-04-03 05:30 | 2023-04-07 05:30 |  | Rakuten | 'RAK + Broker + 1&1' |  | Not started | MRR1.3.2.5.1.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.2.5.3 - SMS Mobile IC (CDC 1) readiness' | 2023-01-13 05:30 | 2023-01-13 05:30 | 2023-04-07 05:30 | 2023-04-07 05:30 |  | Rakuten |  |  | Not started | MRR1.3.2.5.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.3 - DTAG fixed line IC - CDC 1/2''' | 2021-06-15 05:30 | 2023-02-01 05:30 | 2021-06-15 05:30 | 2023-02-01 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.3.1 - Order Connectivity DTAG/Versatel' | 2021-06-15 05:30 | 2021-06-15 05:30 | 2021-06-15 05:30 | 2021-06-15 05:30 |  | 1&1 | Ali Unlu |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.3.2 - [Versatel/DTAG] Physical and logical Integration' | 2021-12-06 05:30 | 2022-01-05 05:30 | 2021-12-06 05:30 | 2022-01-05 05:30 |  | Rakuten transport | VER Transport & RAK Transport & DTAG |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.3.3 - Lab integr. (Lab DTAG/ Lab Versatel/ CDC 1)' | 2021-12-06 05:30 | 2022-01-05 05:30 | 2021-12-06 05:30 | 2022-01-05 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.3.3.1 - [Testing Lab] Testing , Acceptance and Sanity Check' | 2022-07-01 05:30 | 2022-08-11 05:30 | 2022-10-26 05:30 | 2022-12-06 05:30 |  | Rakuten | 'RAK + DTAG + 1&1' |  | Not started | MRR1.3.2.2.3 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.3.4 - Live integr. (Live DTAG/ Live Versatel/ CDC 1/2)' | 2022-08-12 05:30 | 2022-08-25 05:30 | 2022-12-07 05:30 | 2022-12-20 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.3.4.1 - [DTAG Live / DRI Live] Logical connectivity' | 2022-08-12 05:30 | 2022-08-25 05:30 | 2022-12-07 05:30 | 2022-12-20 05:30 |  | Rakuten transport | VER Transport & RAK Transport & DTAG |  | Not started | MRR1.3.3.3.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.3.5 - [Testing Live] - Testing, Acceptance and Sanity Check' | 2022-08-26 05:30 | 2022-10-07 05:30 | 2022-12-21 05:30 | 2023-02-01 05:30 |  | Rakuten | 'RAK + DTAG + 1&1' |  | Not started | MRR1.3.3.4.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.3.6 - DTAG Fixed line IC (CDC 1/2) readiness' | 2022-10-10 05:30 | 2023-02-02 05:30 | 2023-02-01 05:30 | 2023-02-01 05:30 |  | Rakuten |  |  | Not started | MRR1.3.3.5 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4 - IC - CDC 2''' | 2022-02-01 05:30 | 2023-08-15 05:30 | 2022-02-01 05:30 | 2023-08-15 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.1 - TEF Mobile IC - CDC 2"' | 2023-05-03 05:30 | 2023-05-23 05:30 | 2023-05-03 05:30 | 2023-05-23 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.1.1 - Live FOA integr.' | 2023-01-20 05:30 | 2023-02-02 05:30 | 2023-05-03 05:30 | 2023-05-16 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.1.1.1 - [TEF FOA Live / DRI Live] - Logical Connectivity' | 2023-01-20 05:30 | 2023-01-26 05:30 | 2023-05-03 05:30 | 2023-05-09 05:30 |  | Rakuten transport | VER Transport & RAK Transport & TEF |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.1.1.2 - Service Integration of Prod. CDC 2 to TEF FOA Live' | 2023-01-27 05:30 | 2023-02-02 05:30 | 2023-05-10 05:30 | 2023-05-16 05:30 |  | Rakuten | 'RAK+Mavenir, TEF' |  | Not started | MRR1.3.4.1.1.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.1.2 - [Testing FOA Live] Testing , Acceptance and Sanity Check' | 2023-02-03 05:30 | 2023-02-09 05:30 | 2023-05-17 05:30 | 2023-05-23 05:30 |  | Rakuten | 'RAK + TEF' |  | Not started | MRR1.3.4.1.1.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.1.3 - Telefonica Mobile IC (CDC 2) Readiness' | 2023-02-09 05:30 | 2023-02-09 05:30 | 2023-05-23 05:30 | 2023-05-23 05:30 |  | Rakuten |  |  | Not started | MRR1.3.4.1.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.2 - Versatel Fixed IC - CDC 2"' | 2022-08-08 05:30 | 2022-08-18 05:30 | 2022-11-17 05:30 | 2022-12-16 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.2.1 - Live integr.' | 2022-08-08 05:30 | 2022-08-18 05:30 | 2022-11-17 05:30 | 2022-11-30 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.2.1.1 - [VSL Live / DRI Live] Logical connectivity' | 2022-08-08 05:30 | 2022-08-11 05:30 | 2022-11-17 05:30 | 2022-11-23 05:30 |  | Rakuten transport | VER Transport & RAK Transport |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.2.1.2 - Service Integration Live to CDC 2' | 2022-08-12 05:30 | 2022-08-18 05:30 | 2022-11-24 05:30 | 2022-11-30 05:30 |  | Rakuten | 'RAK+Mavenir, Versatel' |  | Not started | MRR1.3.4.2.1.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.2.2 - [Testing Live] - Testing, Acceptance and Sanity Check' | 2022-08-19 05:30 | 2022-08-25 05:30 | 2022-12-12 05:30 | 2022-12-16 05:30 |  | Rakuten | 'RAK + Versatel + 1&1' |  | Not started | MRR1.3.4.2.1.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.2.3 - Versatel fixed line IC (CDC 2) readiness' | 2022-08-25 05:30 | 2022-08-25 05:30 | 2022-12-16 05:30 | 2022-12-16 05:30 |  | Rakuten |  |  | Not started | MRR1.3.4.2.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.3 - Deutsche Telekom Mobile IC - CDC 2"' | 2022-02-01 05:30 | 2023-06-16 05:30 | 2022-02-01 05:30 | 2023-06-16 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.3.1 - Order Connectivity DTAG/Versatel' | 2022-02-01 05:30 | 2022-02-01 05:30 | 2022-02-01 05:30 | 2022-02-01 05:30 |  | 1&1 | Ali Unlu |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.3.2 - Delivery lead time' | 2022-02-02 05:30 | 2022-11-29 05:30 | 2022-02-02 05:30 | 2022-11-29 05:30 |  | VER Wholesale | VER Wholesale |  | Not started | MRR1.3.4.3.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.3.3 - DTAG Lab Intreg.' | 2021-10-04 05:30 | 2022-10-04 05:30 | 2022-11-30 05:30 | 2023-01-13 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.3.3.1 - [Versatel/DTAG] Physical and logical Integration' | 2021-10-04 05:30 | 2022-09-06 05:30 | 2022-11-30 05:30 | 2022-12-13 05:30 |  | Rakuten transport | VER Transport & RAK Transport & DTAG |  | Not started | MRR1.3.4.3.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.3.3.2 - Service Integration of Prod. CDC 2 vs. DTAG Lab' | 2022-09-07 05:30 | 2022-10-04 05:30 | 2022-12-19 05:30 | 2023-01-13 05:30 |  | Rakuten | 'RAK+Mavenir, DTAG' |  | Not started | 'MRR1.3.4.3.3.1 + MR2.5.2.8.1' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.3.4 - [Testing Lab] Testing , Acceptance and Sanity Check' | 2022-10-05 05:30 | 2022-12-20 05:30 | 2023-01-16 05:30 | 2023-03-31 05:30 |  | Rakuten | 'RAK + DTAG + 1&1' |  | Not started | 'MRR1.3.4.3.3.2 + MR2.5.2.6.1 + MRR1.3.5.3.2' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.3.5 - DTAG Live Intreg.' | 2022-11-09 05:30 | 2023-01-03 05:30 | 2023-02-15 05:30 | 2023-04-14 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.3.5.1 - [DTAG Live / DRI Live] - Logical connectivity' | 2022-11-09 05:30 | 2022-12-20 05:30 | 2023-02-15 05:30 | 2023-03-28 05:30 |  | Rakuten transport | VER Transport & RAK Transport & DTAG |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.3.5.2 - Service Integration of Prod. CDC 2 to DTAG Live' | 2022-12-21 05:30 | 2023-01-03 05:30 | 2023-04-03 05:30 | 2023-04-14 05:30 |  | Rakuten | 'RAK+Mavenir, DTAG' |  | Not started | 'MRR1.3.4.3.3.2 + MR2.5.2.8.1' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.3.6 - [Testing Live] Testing , Acceptance and Sanity Check' | 2023-01-04 05:30 | 2023-03-07 05:30 | 2023-04-17 05:30 | 2023-06-16 05:30 |  | Rakuten | 'RAK + DTAG + 1&1' |  | Not started | 'MRR1.3.4.3.5.2 + MR2.5.2.6.1' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.3.7 - DTAG Mobile IC (CDC 2) readiness' | 2023-03-07 05:30 | 2023-03-07 05:30 | 2023-06-16 05:30 | 2023-06-16 05:30 |  | Rakuten |  |  | Not started | MRR1.3.4.3.6 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.4 - International Roaming IC - CDC 2"' | 2022-03-01 05:30 | 2023-08-15 05:30 | 2022-03-01 05:30 | 2023-08-15 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.4.1 - Order Connectivity Broker/Versatel' | 2022-03-01 05:30 | 2022-03-01 05:30 | 2022-03-01 05:30 | 2022-03-01 05:30 |  | 1&1 | Ali Unlu |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.4.2 - Delivery Lead time' | 2022-03-02 05:30 | 2022-12-30 05:30 | 2022-03-02 05:30 | 2022-12-30 05:30 |  | VER Wholesale | VER Wholesale |  | Not started | MRR1.3.4.4.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.4.3 - Broker Lab Intreg.' | 2022-10-07 05:30 | 2022-12-08 05:30 | 2023-01-02 05:30 | 2023-03-03 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.4.3.1 - [Versatel/Broker] Physical and logical Integration' | 2022-10-07 05:30 | 2022-10-20 05:30 | 2023-01-02 05:30 | 2023-01-13 05:30 |  | Rakuten transport | VER Transport & RAK Transport & Broker |  | Not started | MRR1.3.4.4.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.4.3.2 - Service Integration of Prod. CDC 2 vs. Broker Lab' | 2022-10-21 05:30 | 2022-12-08 05:30 | 2023-01-16 05:30 | 2023-03-03 05:30 |  | Rakuten | 'RAK+Mavenir, Broker' |  | Not started | MRR1.3.4.4.3.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.4.4 - [Testing Lab] Testing , Acceptance and Sanity Check' | 2022-12-09 05:30 | 2023-03-16 05:30 | 2023-03-06 05:30 | 2023-06-09 05:30 |  | Rakuten | 'RAK + Broker + 1&1' |  | Not started | MRR1.3.4.4.3.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.4.5 - Broker Live Intreg.' | 2023-02-06 05:30 | 2023-07-03 05:30 | 2023-05-02 05:30 | 2023-06-30 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.4.5.1 - [Broker Live / DRI Live] - Logical connectivity' | 2023-02-06 05:30 | 2023-03-16 05:30 | 2023-05-02 05:30 | 2023-06-12 05:30 |  | Rakuten transport | VER Transport & RAK Transport & Broker |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.4.5.2 - Service Integration of Prod. CDC 2 to Broker Live' | 2023-03-17 05:30 | 2023-07-03 05:30 | 2023-06-13 05:30 | 2023-06-30 05:30 |  | Rakuten | 'RAK+Mavenir, Broker' |  | Not started | MRR1.3.4.4.4 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.4.6 - [Testing Live] Testing , Acceptance and Sanity Check' | 2023-07-04 05:30 | 2023-08-16 05:30 | 2023-07-03 05:30 | 2023-08-15 05:30 |  | Rakuten | 'RAK + Broker + 1&1' |  | Not started | MRR1.3.4.4.5.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.4.7 - Broker Mobile IC (CDC 2) readiness' | 2023-08-16 05:30 | 2023-08-16 05:30 | 2023-08-15 05:30 | 2023-08-15 05:30 |  | Rakuten |  |  | Not started | MRR1.3.4.4.6 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.5 - SMS Hub international - CDC 2"' | 2022-03-01 05:30 | 2023-04-07 05:30 | 2022-03-01 05:30 | 2023-04-07 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.5.1 - Order Connectivity Broker/Versatel' | 2022-03-01 05:30 | 2022-03-01 05:30 | 2022-03-01 05:30 | 2022-03-01 05:30 |  | 1&1 | Ali Unlu |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.5.2 - Delivery Lead time' | 2022-03-02 05:30 | 2022-12-30 05:30 | 2022-03-02 05:30 | 2022-12-30 05:30 |  | VER Wholesale | VER Wholesale |  | Not started | MRR1.3.4.5.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.5.3 - SMS Lab Intreg.' | 2022-10-07 05:30 | 2022-11-03 05:30 | 2023-01-02 05:30 | 2023-01-27 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.5.3.1 - [Versatel/SMS] - Physical and logical Integration' | 2022-10-07 05:30 | 2022-10-20 05:30 | 2023-01-02 05:30 | 2023-01-13 05:30 |  | Rakuten transport | VER Transport & RAK Transport & Broker |  | Not started | MRR1.3.4.5.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.5.3.2 - Service Integration of Prod. CDC 2 vs. SMS Lab' | 2022-10-21 05:30 | 2022-11-03 05:30 | 2023-01-16 05:30 | 2023-01-27 05:30 |  | Rakuten | 'RAK+Mavenir, Broker' |  | Not started | MRR1.3.4.5.3.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.5.4 - [Testing Lab] Testing , Acceptance and Sanity Check' | 2022-11-04 05:30 | 2022-11-17 05:30 | 2023-01-30 05:30 | 2023-02-10 05:30 |  | Rakuten | 'RAK + Broker + 1&1' |  | Not started | MRR1.3.4.5.3.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.5.5 - SMS Live Intreg.' | 2022-11-04 05:30 | 2022-12-01 05:30 | 2023-01-27 05:30 | 2023-02-23 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.5.5.1 - [SMS Live / DRI Live] - Logical connectivity' | 2022-11-04 05:30 | 2022-11-17 05:30 | 2023-01-27 05:30 | 2023-02-09 05:30 |  | Rakuten transport | VER Transport & RAK Transport & Broker |  | Not started | MRR1.3.4.5.4 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.5.5.2 - Service Integration of Prod. CDC 2 to SMS Live' | 2022-11-18 05:30 | 2022-12-01 05:30 | 2023-02-10 05:30 | 2023-02-23 05:30 |  | Rakuten | 'RAK+Mavenir, Broker' |  | Not started | MRR1.3.4.5.5.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.5.6 - [Testing Live] Testing , Acceptance and Sanity Check' | 2022-12-02 05:30 | 2023-01-13 05:30 | 2023-02-24 05:30 | 2023-04-07 05:30 |  | Rakuten | 'RAK + Broker + 1&1' |  | Not started | MRR1.3.4.5.5.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.4.5.7 - SMS Mobile IC (CDC 2) readiness' | 2023-01-13 05:30 | 2023-01-13 05:30 | 2023-04-07 05:30 | 2023-04-07 05:30 |  | Rakuten |  |  | Not started | MRR1.3.4.5.6 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.5 - Vodafone Mobile IC - CDC 2/1''' | 2022-02-01 05:30 | 2023-06-09 05:30 | 2022-02-01 05:30 | 2023-06-09 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.5.1 - Order Connectivity VDF/Versatel' | 2022-02-01 05:30 | 2022-02-01 05:30 | 2022-02-01 05:30 | 2022-02-01 05:30 |  | 1&1 | Ali Unlu |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.5.2 - Delivery Lead time' | 2022-02-02 05:30 | 2022-11-01 05:30 | 2022-02-02 05:30 | 2022-11-01 05:30 |  | VER Wholesale | VER Wholesale |  | Not started | MRR1.3.5.1 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.5.3 - VDF Lab Intreg. (Lab VDF/ CDC 2)' | 2022-08-31 05:30 | 2022-10-11 05:30 | 2022-11-02 05:30 | 2023-01-13 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.5.3.1 - [Versatel/VDF] Physical and logical Integration' | 2022-08-31 05:30 | 2022-09-13 05:30 | 2022-11-02 05:30 | 2022-11-15 05:30 |  | Rakuten transport | VER Transport & RAK Transport & VDF |  | Not started | MRR1.3.5.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.5.3.2 - Service Integration of Prod. CDC 2 vs. VDF Lab' | 2022-09-14 05:30 | 2022-10-11 05:30 | 2022-12-19 05:30 | 2023-01-13 05:30 |  | Rakuten | 'RAK+Mavenir, VDF' |  | Not started | 'MRR1.3.5.3.1 + MR2.5.2.8.1' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.5.4 - [Testing Lab] Testing , Acceptance and Sanity Check' | 2022-10-12 05:30 | 2022-12-27 05:30 | 2023-01-16 05:30 | 2023-03-31 05:30 |  | Rakuten | 'RAK + VDF+ 1&1' |  | Not started | 'MRR1.3.5.3.2 + MR2.5.2.6.1' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.5.5 - VDF Live Intreg. (Live VDF/CDC 1/2)' | 2022-11-16 05:30 | 2023-01-10 05:30 | 2023-01-18 05:30 | 2023-04-14 05:30 |  | Rakuten |  |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.5.5.1 - [VDF Live / DRI Live] - Logical connectivity' | 2022-11-16 05:30 | 2022-12-27 05:30 | 2023-01-18 05:30 | 2023-02-28 05:30 |  | Rakuten transport | VER Transport & RAK Transport & VDF |  | Not started | [10 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.5.5.2 - Service Integration of Prod. CDC (1+2) to VDF Live' | 2022-12-28 05:30 | 2023-01-10 05:30 | 2023-04-03 05:30 | 2023-04-14 05:30 |  | Rakuten | 'RAK+Mavenir, VDF' |  | Not started | 'MRR1.3.5.5.1 + MRR1.3.5.4' | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.5.6 - [Testing Live] Testing , Acceptance and Sanity Check' | 2023-01-11 05:30 | 2023-03-07 05:30 | 2023-04-17 05:30 | 2023-06-09 05:30 |  | Rakuten | 'RAK + VDF+ 1&1' |  | Not started | MRR1.3.5.5.2 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes
'MRR1.3.5.7 - Vodafone Mobile IC (CDC 1/2) readiness' | 2023-03-07 05:30 | 2023-03-07 05:30 | 2023-06-09 05:30 | 2023-06-09 05:30 |  | Rakuten |  |  | Not started | MRR1.3.5.6 | [9 empty] | eMBB | CDC & Core Network | Marius Andrei | SE&I: Core and National Roaming | Simon Schaefer | Yes

## CDC 3-4 Build
Name | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Elapsed | Executing Party | Party Contact | Customizable Field | Status | Predecessor | Dependency | Ext. Dependency | Comments | Deliverable [Yes/No] | Deliverable Name | Deliverable Type | Deliverable Owner | Client Sign off | Penalties [Yes/No] | Key Contractual Milestones | Domain | SPOC Planning | Workstream | Workstream PM | Contractual Milestone [Yes/No] | Last Updated
''MR2.9 - Location Selection'' | 2021-08-06 05:30 | 2021-08-30 05:30 | 2021-08-06 05:30 | 2021-08-30 05:30 | 19 | 1&1 |  |  | Completed |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network |  | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3 - CDC3 Rollout Steps to be ready for Y23_1.5M'' | 2021-12-01 05:30 | 2023-01-31 05:30 | 2021-12-01 05:30 | 2023-01-31 05:30 | 305 | Rakuten |  |  | In Progress |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.1 - Planning & Dimensioning'' | 2021-12-01 05:30 | 2022-03-31 05:30 | 2021-12-01 05:30 | 2022-03-31 05:30 | 87 | Rakuten |  |  | In Progress |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.2 - HW Orders '' | 2022-02-01 05:30 | 2022-02-28 05:30 | 2022-02-01 05:30 | 2022-02-28 05:30 | 20 | Rakuten |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.3 - HW Delivery '' | 2022-03-01 05:30 | 2022-06-30 05:30 | 2022-03-01 05:30 | 2022-06-30 05:30 | 88 | Rakuten |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.4 - DCN Setup'' | 2022-07-01 05:30 | 2022-07-30 05:30 | 2022-07-01 05:30 | 2022-07-30 05:30 | 21 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.5 - Basic Security Setup'' | 2022-08-01 05:30 | 2022-08-15 05:30 | 2022-08-01 05:30 | 2022-08-15 05:30 | 11 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.6 - Cloud Setup'' | 2022-08-15 05:30 | 2022-09-30 05:30 | 2022-08-15 05:30 | 2022-09-30 05:30 | 35 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.7 - Core Deployment'' | 2022-10-01 05:30 | 2022-11-30 05:30 | 2022-10-01 05:30 | 2022-11-30 05:30 | 44 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.8 - Applications Deployment'' | 2022-10-01 05:30 | 2022-11-30 05:30 | 2022-10-01 05:30 | 2022-11-30 05:30 | 44 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.3.9 - E2E Testing & Acceptance'' | 2022-12-01 05:30 | 2023-01-31 05:30 | 2022-12-01 05:30 | 2023-01-31 05:30 | 46 | Rakuten |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.4 - CDC4 Rollout Steps to be ready for Y23_1.5M'' | 2021-12-01 05:30 | 2023-01-31 05:30 | 2021-12-01 05:30 | 2023-01-31 05:30 | 305 | Rakuten |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.4.1 - Planning & Dimensioning'' | 2021-12-01 05:30 | 2022-03-31 05:30 | 2021-12-01 05:30 | 2022-03-31 05:30 | 87 | Rakuten |  |  | In Progress |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.4.2 - HW Orders '' | 2022-02-01 05:30 | 2022-02-28 05:30 | 2022-02-01 05:30 | 2022-02-28 05:30 | 20 | Rakuten |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.4.3 - HW Delivery '' | 2022-03-01 05:30 | 2022-06-30 05:30 | 2022-03-01 05:30 | 2022-06-30 05:30 | 88 | Rakuten |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.4.4 - DCN Setup'' | 2022-07-01 05:30 | 2022-07-30 05:30 | 2022-07-01 05:30 | 2022-07-30 05:30 | 21 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.4.5 - Basic Security Setup'' | 2022-08-01 05:30 | 2022-08-15 05:30 | 2022-08-01 05:30 | 2022-08-15 05:30 | 11 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 03-Feb 02:08 AM'
''Y23.4.6 - Cloud Setup'' | 2022-08-15 05:30 | 2022-09-30 05:30 | 2022-08-15 05:30 | 2022-09-30 05:30 | 35 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 03-Feb 02:08 AM'
''Y23.4.7 - Core Deployment'' | 2022-10-01 05:30 | 2022-11-30 05:30 | 2022-10-01 05:30 | 2022-11-30 05:30 | 44 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 03-Feb 02:08 AM'
''Y23.4.7 - Applications Deployment'' | 2022-10-01 05:30 | 2022-11-30 05:30 | 2022-10-01 05:30 | 2022-11-30 05:30 | 44 | Tech Mahindra |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
''Y23.4.8 - E2E Testing & Acceptance'' | 2022-12-01 05:30 | 2023-01-31 05:30 | 2022-12-01 05:30 | 2023-01-31 05:30 | 46 | Rakuten |  |  | Not Started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network | Marius Andrei | Planning & Rollout | Marius Andrei | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'

## CDC 1 2023 expansion
Name | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Elapsed | Executing Party | Party Contact | Customizable field | Status | Predecessor | Dependency | Ext. Dependency | Comments | Deliverable [Yes/No] | Deliverable Name | Deliverable Type | Deliverable Owner | Client Sign off | Penalties [Yes/No] | Key Contractual Milestones | Domain | SPOC Planning | Workstream | Workstream PM | Contractual Milestone [Yes/No] | Last Updated
'Y23.1 - CDC1 Expansion Steps for Y23' | 2021-12-01 13:30 | 2022-07-31 12:30 |  |  |  | Rakuten |  |  | In progress |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network |  |  |  | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'Y23.1.1 - Planning & Dimensioning' | 2021-12-01 13:30 | 2022-03-31 12:30 |  |  |  | Rakuten |  |  | In progress |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network |  |  |  | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'Y23.1.2 - HW Orders ' | [5 empty] | Rakuten |  |  | Not started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network |  |  |  | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'Y23.1.3 - HW Delivery ' | [5 empty] | Rakuten |  |  | Not started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network |  |  |  | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'Y23.1.4 - DCN Expansion' | [5 empty] | Tech Mahindra |  |  | Not started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network |  |  |  | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'Y23.1.5 - Clusters Expansion' | [5 empty] | Tech Mahindra |  |  | Not started |  |  |  |  | No | [5 empty] | eMBB | CDC & Core Network |  |  |  | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'

## CDC 2 2023 Expansion
Name | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Elapsed | Executing Party | Party Contact | Customizable field | Status | Predecessor | Dependency | Ext. Dependency | Comments | Deliverable [Yes/No] | Deliverable Name | Deliverable Type | Deliverable Owner | Client Sign off | Penalties [Yes/No] | Key Contractual Milestones | Domain | SPOC Planning | Workstream | Workstream PM | Contractual Milestone [Yes/No] | Last Updated
'Y23.2 - CDC2 Expansion Steps for Y23' | 2021-12-01 13:30 |  | 2021-12-01 13:30 | 2022-07-31 12:30 | 174 | Rakuten | [7 empty] | No | [5 empty] | eMBB |  |  |  |  | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'Y23.2.1 - Planning & Dimensioning' | 2021-12-01 13:30 |  | 2021-12-01 13:30 | 2022-03-31 12:30 | 87 | Rakuten | [7 empty] | No | [5 empty] | eMBB |  |  |  |  | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'Y23.2.2 - HW Orders ' | [5 empty] | Rakuten | [7 empty] | No | [5 empty] | eMBB |  |  |  |  | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'Y23.2.3 - HW Delivery ' | [13 empty] | No | [5 empty] | eMBB |  |  |  |  | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'Y23.2.4 - DCN Expansion' | [5 empty] | Tech Mahindra | [7 empty] | No | [5 empty] | eMBB |  |  |  |  | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'
'Y23.2.5 - Clusters Expansion' | [5 empty] | Tech Mahindra | [7 empty] | No | [5 empty] | eMBB |  |  |  |  | No | 'aneet.cheema@sourcefuse.com on 02-Feb 11:16 PM'