## FWA - RCP Customizations
Name | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Duration | Executing Party | Party Contact | Customizable field | Status | Critical [Yes/No] | Predecessor | Dependency | Ext. Dependency | Comments | Deliverable [YES/NO] | Key Contractual Milestones | Workstream | Contractual Milestone [YES/NO] | Last Updated | Baseline Start | Baseline Finish | Variance
MC5.1 - RCP Continuous Customization' | 2022-06-29 | 2133-11-23 | 2021-12-17 |  | 29064d | [10 empty] | FWA | SE&I: OSS & Orchestration |  |  | 2022-06-29 | 2133-11-23 | 0
MC5.1.1 - Automator & Uplift Standard Features' | 2022-06-29 | 2027-02-12 | 2022-07-01 | 2024-01-23 | 1208d | [10 empty] | FWA | SE&I: OSS & Orchestration |  |  | 2022-06-29 | 2027-02-12 | 0
'MC5.1.1.1 - Workflow Studio Readiness'' | 2022-06-29 | 2022-08-01 |  |  | 24d | [10 empty] | FWA | SE&I: OSS & Orchestration | No |  | 2022-06-29 | 2022-08-01 | 0
'MC5.1.1.1.1 - Development - Workflow Studio feature Extension drop 1 - Q2 2022 feature list'' | 2022-06-29 | 2022-06-29 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2022-06-29 | 2022-06-29 | 0
'MC5.1.1.1.2 - Deployment on Mainz Lab for Workflow Studio feature Extension drop 1 - Q2 2022 feature list'' | 2022-06-30 | 2022-07-01 | 2022-06-06 | 2022-06-07 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 4 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2022-06-30 | 2022-07-01 | 0
'MC5.1.1.1.3 - External dependency on QA E2E Testing of Workflow Studio feature extension drop 1'' | 2022-07-04 | 2022-07-04 |  |  | 1d | [5 empty] | 5 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2022-07-04 | 2022-07-04 | 0
'MC5.1.1.1.4 - Deployment on Production for Workflow Studio feature Extension drop 1 - Q2 2022 feature list'' | 2022-07-05 | 2022-07-05 | 2021-12-24 |  | 1d | [5 empty] | 6 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2022-07-05 | 2022-07-05 | 0
'MC5.1.1.1.5 - Deployment on Mainz Lab for Workflow Studio feature Extension drop 2 - Q4 2022 feature list"' | 2022-07-06 | 2022-07-06 |  |  | 1d | [5 empty] | 7 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2022-07-06 | 2022-07-06 | 0
'MC5.1.1.1.6 - Workflow Studio feature Extension drop 2 - Q4 2022 feature list'' | 2022-07-07 | 2022-07-28 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 8 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2022-07-07 | 2022-07-28 | 0
'MC5.1.1.1.7 - External dependency on QA E2E Testing of Workflow Studio feature extension drop 2'' | 2022-07-29 | 2022-07-29 |  |  | 1d | [5 empty] | 9 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2022-07-29 | 2022-07-29 | 0
'MC5.1.1.1.8 - Deployment on Production for Workflow Studio feature Extension drop 2 - Q4 2022 feature list'' | 2022-08-01 | 2022-08-01 | 2021-12-31 |  | 1d | [5 empty] | 10 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2022-08-01 | 2022-08-01 | 0
'MC5.1.1.2 - Site Manager Readiness'' | 2022-08-02 | 2022-09-02 |  |  | 24d | [5 empty] | 11 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2022-08-02 | 2022-09-02 | 0
'MC5.1.1.2.1 - Development - Site Manager feature Extension drop 1 - Q2 2022 feature list'' | 2022-08-02 | 2022-08-02 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2022-08-02 | 2022-08-02 | 0
'MC5.1.1.2.2 - Deployment on Mainz Lab for Site Manager feature Extension drop 1 - Q2 2022 feature list'' | 2022-08-03 | 2022-08-04 | 2022-06-06 | 2022-06-07 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 13 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2022-08-03 | 2022-08-04 | 0
'MC5.1.1.2.3 - External dependency on QA E2E Testing Site Manager feature Extension drop 1'' | 2022-08-05 | 2022-08-05 |  |  | 1d | [5 empty] | 14 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2022-08-05 | 2022-08-05 | 0
'MC5.1.1.2.4 - Deployment on Production for Site Manager feature Extension drop 1 - Q2 2022 feature list'' | 2022-08-08 | 2022-08-08 | 2021-05-25 |  | 1d | [5 empty] | 15 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2022-08-08 | 2022-08-08 | 0
'MC5.1.1.2.5 - Development - Site Manager feature Extension drop 2 - Q4 2022 feature list'' | 2022-08-09 | 2022-08-09 |  |  | 1d | [5 empty] | 16 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2022-08-09 | 2022-08-09 | 0
'MC5.1.1.2.6 - Deployment on Mainz Lab for Site Manager feature Extension drop 2 - Q4 2022 feature list'' | 2022-08-10 | 2022-08-31 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 17 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2022-08-10 | 2022-08-31 | 0
'MC5.1.1.2.7 - External dependency on QA E2E Testing Site Manager feature Extension drop 2'' | 2022-09-01 | 2022-09-01 |  |  | 1d | [5 empty] | 18 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2022-09-01 | 2022-09-01 | 0
'MC5.1.1.2.8 - Deployment on Production for Site Manager feature Extension drop 2 - Q4 2022 feature list' ' | 2022-09-02 | 2022-09-02 |  |  | 1d | [5 empty] | 19 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2022-09-02 | 2022-09-02 | 0
'MC5.1.1.3 - Logistics Manager Readiness'' | 2022-09-05 | 2022-11-25 |  |  | 60d | [5 empty] | 20 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2022-09-05 | 2022-11-25 | 0
'MC5.1.1.3.1 - Development - Logistics Manager initial deployment - Q2 2022 feature list'' | 2022-09-05 | 2022-09-05 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2022-09-05 | 2022-09-05 | 0
'MC5.1.1.3.2 - Deployment on Mainz Lab for Logistics Manager initial deployment - Q2 2022 feature list'' | 2022-09-06 | 2022-10-03 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 22 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2022-09-06 | 2022-10-03 | 0
'MC5.1.1.3.3 - External dependency on QA E2E Testing'' | 2022-10-04 | 2022-10-04 |  |  | 1d | [5 empty] | 23 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2022-10-04 | 2022-10-04 | 0
'MC5.1.1.3.4 - Deployment on Production for Logistics Manager initial deployment - Q2 2022 feature list'' | 2022-10-05 | 2022-10-05 |  |  | 1d | [5 empty] | 24 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2022-10-05 | 2022-10-05 | 0
'MC5.1.1.3.5 - Development - Logistics Manager feature Extension drop 1 - Q4 2022 feature list'' | 2022-10-06 | 2022-10-06 |  |  | 1d | [5 empty] | 25 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2022-10-06 | 2022-10-06 | 0
'MC5.1.1.3.6 - Logistics Manager feature Extension drop 1 - Q4 2022 feature list'' | 2022-10-07 | 2022-10-28 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 26 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2022-10-07 | 2022-10-28 | 0
'MC5.1.1.3.7 - External dependency on QA E2E Testing Logistics Manager feature Extension drop 1'' | 2022-10-31 | 2022-10-31 |  |  | 1d | [5 empty] | 27 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2022-10-31 | 2022-10-31 | 0
'MC5.1.1.3.8 - Deployment on Production for Logistics Manager feature Extension drop 1 - Q4 2022 feature list'' | 2022-11-01 | 2022-11-01 |  |  | 1d | [5 empty] | 28 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2022-11-01 | 2022-11-01 | 0
'MC5.1.1.3.9 - Development - Logistics Manager feature Extension drop 2 - Q2 2023 feature list'' | 2022-11-02 | 2022-11-02 |  |  | 1d | [5 empty] | 29 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2022-11-02 | 2022-11-02 | 0
'MC5.1.1.3.10 - Logistics Manager feature Extension drop 2 - Q2 2023 feature list'' | 2022-11-03 | 2022-11-23 | 2022-06-06 | 2022-06-24 | 15d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 30 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2022-11-03 | 2022-11-23 | 0
'MC5.1.1.3.11 - External dependency on QA E2E Testing Logistics Manager feature Extension drop 2'' | 2022-11-24 | 2022-11-24 |  |  | 1d | [5 empty] | 31 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2022-11-24 | 2022-11-24 | 0
'MC5.1.1.3.12 - Deployment on Production for Logistics Manager feature Extension drop 2 - Q2 2023 feature list'' | 2022-11-25 | 2022-11-25 |  |  | 1d | [5 empty] | 32 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2022-11-25 | 2022-11-25 | 0
'MC5.1.1.4 - RAN Commander Readiness'' | 2022-11-28 | 2023-02-17 |  |  | 60d | [5 empty] | 33 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2022-11-28 | 2023-02-17 | 0
'MC5.1.1.4.1 - Development - RAN Commander feature Extension drop 1 - Q2 2022 feature list'' | 2022-11-28 | 2022-11-28 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2022-11-28 | 2022-11-28 | 0
'MC5.1.1.4.2 - Deployment on Mainz Lab for RAN Commander feature Extension drop 1 - Q2 2022 feature list'' | 2022-11-29 | 2022-12-26 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 35 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2022-11-29 | 2022-12-26 | 0
'MC5.1.1.4.3 - External dependency on QA E2E Testing RAN Commander feature Extension drop 1'' | 2022-12-27 | 2022-12-27 |  |  | 1d | [5 empty] | 36 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2022-12-27 | 2022-12-27 | 0
'MC5.1.1.4.4 - Deployment on Production for RAN Commander feature Extension drop 1 - Q2 2022 feature list'' | 2022-12-28 | 2022-12-28 |  |  | 1d | [5 empty] | 37 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2022-12-28 | 2022-12-28 | 0
'MC5.1.1.4.5 - Development - RAN Commander feature Extension drop 2 - Q4 2022 feature list'' | 2022-12-29 | 2022-12-29 |  |  | 1d | [5 empty] | 38 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2022-12-29 | 2022-12-29 | 0
'MC5.1.1.4.6 - Deployment on Mainz Lab for RAN Commander feature Extension drop 2 - Q4 2022 feature list'' | 2022-12-30 | 2023-01-20 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 39 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2022-12-30 | 2023-01-20 | 0
'MC5.1.1.4.7 - External dependency on QA E2E Testing RAN Commander feature Extension drop 2'' | 2023-01-23 | 2023-01-23 |  |  | 1d | [5 empty] | 40 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2023-01-23 | 2023-01-23 | 0
'MC5.1.1.4.8 - Deployment on Production for RAN Commander feature Extension drop 2 - Q4 2022 feature list'' | 2023-01-24 | 2023-01-24 |  |  | 1d | [5 empty] | 41 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-01-24 | 2023-01-24 | 0
'MC5.1.1.4.9 - Development - RAN Commander feature Extension drop 3 - Q2 2023 feature list'' | 2023-01-25 | 2023-01-25 |  |  | 1d | [5 empty] | 42 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-01-25 | 2023-01-25 | 0
'MC5.1.1.4.10 - Deployment on Mainz Lab for RAN Commander feature Extension drop 3 - Q2 2023 feature list'' | 2023-01-26 | 2023-02-15 | 2022-06-06 | 2022-06-24 | 15d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 43 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2023-01-26 | 2023-02-15 | 0
'MC5.1.1.4.11 - External dependency on QA E2E Testing on RAN Commander feature Extension drop 3' | 2023-02-16 | 2023-02-16 |  |  | 1d | [5 empty] | 44 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-02-16 | 2023-02-16 | 0
'MC5.1.1.4.12 - Deployment on Production for RAN Commander feature Extension drop 3 - Q2 2023 feature list'' | 2023-02-17 | 2023-02-17 |  |  | 1d | [5 empty] | 45 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-02-17 | 2023-02-17 | 0
'MC5.1.1.5 - Financial Manager Readiness'' | 2023-02-20 | 2023-04-25 |  |  | 47d | [5 empty] | 46 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2023-02-20 | 2023-04-25 | 0
'MC5.1.1.5.1 - Development - Financial Manager feature Extension drop 1 - Q2 2022 feature list'' | 2023-02-20 | 2023-02-20 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2023-02-20 | 2023-02-20 | 0
'MC5.1.1.5.2 - Deployment on Mainz Lab for Financial Manager feature Extension drop 1 - Q2 2022 feature list'' | 2023-02-21 | 2023-03-20 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 48 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2023-02-21 | 2023-03-20 | 0
'MC5.1.1.5.3 - External dependency on QA E2E Testing on Financial Manager feature Extension drop 1'' | 2023-03-21 | 2023-03-21 |  |  | 1d | [5 empty] | 49 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2023-03-21 | 2023-03-21 | 0
'MC5.1.1.5.4 - Deployment on Production for Financial Manager feature Extension drop 1 - Q2 2022 feature list'' | 2023-03-22 | 2023-03-22 |  |  | 1d | [5 empty] | 50 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-03-22 | 2023-03-22 | 0
'MC5.1.1.5.5 - Development - Financial Manager feature Extension drop 2 - Q4 2022 feature list'' | 2023-03-23 | 2023-03-23 |  |  | 1d | [5 empty] | 51 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-03-23 | 2023-03-23 | 0
'MC5.1.1.5.6 - Deployment on Mainz Lab for Financial Manager feature Extension drop 2 - Q4 2022 feature list'' | 2023-03-24 | 2023-04-14 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 52 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2023-03-24 | 2023-04-14 | 0
'MC5.1.1.5.7 - External dependency on QA E2E Testing on Financial Manager feature Extension drop 2'' | 2023-04-17 | 2023-04-17 |  |  | 1d | [5 empty] | 53 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-04-17 | 2023-04-17 | 0
'MC5.1.1.5.8 - Deployment on Production for Financial Manager feature Extension drop 2 - Q4 2022 feature list'' | 2023-04-18 | 2023-04-18 |  |  | 1d | [5 empty] | 54 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-04-18 | 2023-04-18 | 0
'MC5.1.1.5.9 - Development - Financial Manager feature Extension drop 3 - Q2 2023 feature list'' | 2023-04-19 | 2023-04-19 |  |  | 1d | [5 empty] | 55 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-04-19 | 2023-04-19 | 0
'MC5.1.1.5.10 - Deployment on Mainz Lab for Financial Manager feature Extension drop 3 - Q2 2023 feature list'' | 2023-04-20 | 2023-04-21 | 2022-06-06 | 2022-06-07 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 56 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2023-04-20 | 2023-04-21 | 0
'MC5.1.1.5.11 - External dependency on QA E2E Testing on Financial Manager feature Extension drop 3'' | 2023-04-24 | 2023-04-24 |  |  | 1d | [5 empty] | 57 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2023-04-24 | 2023-04-24 | 0
'MC5.1.1.5.12 - Deployment on Production for Financial Manager feature Extension drop 3 - Q2 2023 feature list'' | 2023-04-25 | 2023-04-25 |  |  | 1d | [5 empty] | 58 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-04-25 | 2023-04-25 | 0
'MC5.1.1.6 - Procurement Manager Readiness'' | 2023-04-26 | 2023-07-18 |  |  | 60d | [5 empty] | 59 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2023-04-26 | 2023-07-18 | 0
'MC5.1.1.6.1 - Development - Procurement Manager feature Extension drop 1 - Q2 2022 feature list'' | 2023-04-26 | 2023-04-26 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2023-04-26 | 2023-04-26 | 0
'MC5.1.1.6.2 - Deployment on Mainz Lab for Procurement Manager feature Extension drop 1 - Q2 2022 feature list'' | 2023-04-27 | 2023-05-24 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 61 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2023-04-27 | 2023-05-24 | 0
'MC5.1.1.6.3 - External dependency on QA E2E Testing on Procurement Manager feature Extension drop 1'' | 2023-05-25 | 2023-05-25 |  |  | 1d | [5 empty] | 62 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-05-25 | 2023-05-25 | 0
'MC5.1.1.6.4 - Deployment on Production for Procurement Manager feature Extension drop 1 - Q2 2022 feature list'' | 2023-05-26 | 2023-05-26 |  |  | 1d | [5 empty] | 63 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-05-26 | 2023-05-26 | 0
'MC5.1.1.6.5 - Development - Procurement Manager feature Extension drop 2 - Q4 2022 feature list'' | 2023-05-29 | 2023-05-29 |  |  | 1d | [5 empty] | 64 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-05-29 | 2023-05-29 | 0
'MC5.1.1.6.6 - Deployment on Mainz Lab for Procurement Manager feature Extension drop 2 - Q4 2022 feature list'' | 2023-05-30 | 2023-06-20 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 65 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2023-05-30 | 2023-06-20 | 0
'MC5.1.1.6.7 - External dependency on QA E2E Testing Procurement Manager feature Extension drop 2'' | 2023-06-21 | 2023-06-21 |  |  | 1d | [5 empty] | 66 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-06-21 | 2023-06-21 | 0
'MC5.1.1.6.8 - Deployment on Production for Procurement Manager feature Extension drop 2 - Q4 2022 feature list' ' | 2023-06-22 | 2023-06-22 |  |  | 1d | [5 empty] | 67 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-06-22 | 2023-06-22 | 0
'MC5.1.1.6.9 - Development - Procurement Manager feature Extension drop 3 - Q2 2023 feature list'' | 2023-06-23 | 2023-06-23 |  |  | 1d | [5 empty] | 68 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-06-23 | 2023-06-23 | 0
'MC5.1.1.6.10 - Deployment on Mainz Lab for Procurement Manager feature Extension drop 3 - Q2 2023 feature list'' | 2023-06-26 | 2023-07-14 | 2022-06-06 | 2022-06-24 | 15d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 69 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2023-06-26 | 2023-07-14 | 0
'MC5.1.1.6.11 - External dependency on QA E2E Testing on Procurement Manager feature Extension drop 3'' | 2023-07-17 | 2023-07-17 |  |  | 1d | [5 empty] | 70 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-07-17 | 2023-07-17 | 0
'MC5.1.1.6.12 - Deployment on Production for Procurement Manager feature Extension drop 3 - Q2 2023 feature list'' | 2023-07-18 | 2023-07-18 |  |  | 1d | [5 empty] | 71 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-07-18 | 2023-07-18 | 0
'MC5.1.1.7 - RCP Connect Readiness'' | 2023-07-19 | 2023-08-18 |  |  | 23d | [5 empty] | 72 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2023-07-19 | 2023-08-18 | 0
'MC5.1.1.7.1 - Development - RCP Connect feature Extension drop 1 - Q2 2022 feature list'' | 2023-07-19 | 2023-07-19 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2023-07-19 | 2023-07-19 | 0
'MC5.1.1.7.2 - Deployment on Mainz Lab for RCP Connect feature Extension drop 1 - Q2 2022 feature list'' | 2023-07-20 | 2023-08-16 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 74 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2023-07-20 | 2023-08-16 | 0
'MC5.1.1.7.3 - External dependency on QA E2E Testing on RCP Connect feature Extension drop 1'' | 2023-08-17 | 2023-08-17 |  |  | 1d | [5 empty] | 75 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-08-17 | 2023-08-17 | 0
'MC5.1.1.7.4 - Deployment on Production for RCP Connect feature Extension drop 1 - Q2 2022 feature list'' | 2023-08-18 | 2023-08-18 |  |  | 1d | [5 empty] | 76 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-08-18 | 2023-08-18 | 0
'MC5.1.1.8 - Inventory Manager Readiness'' | 2023-08-21 | 2023-10-17 |  |  | 42d | [5 empty] | 77 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2023-08-21 | 2023-10-17 | 0
'MC5.1.1.8.1 - Development - Inventory Manager feature Extension drop 1 - Q2 2022 feature list'' | 2023-08-21 | 2023-08-21 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2023-08-21 | 2023-08-21 | 0
'MC5.1.1.8.2 - Deployment on Mainz Lab for Inventory Manager feature Extension drop 1 - Q2 2022 feature list'' | 2023-08-22 | 2023-09-18 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 79 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2023-08-22 | 2023-09-18 | 0
'MC5.1.1.8.3 - External dependency on QA E2E Testing on Inventory Manager feature Extension drop 1'' | 2023-09-19 | 2023-09-19 |  |  | 1d | [5 empty] | 80 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-09-19 | 2023-09-19 | 0
'MC5.1.1.8.4 - Deployment on Production for Inventory Manager feature Extension drop 1 - Q2 2022 feature list'' | 2023-09-20 | 2023-09-20 |  |  | 1d | [5 empty] | 81 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-09-20 | 2023-09-20 | 0
'MC5.1.1.8.5 - Development - Inventory Manager feature Extension drop 2 - Q4 2022 feature list'' | 2023-09-21 | 2023-09-21 |  |  | 1d | [5 empty] | 82 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-09-21 | 2023-09-21 | 0
'MC5.1.1.8.6 - Deployment on Mainz Lab for Inventory Manager feature Extension drop 2 - Q4 2022 feature list'' | 2023-09-22 | 2023-10-13 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 83 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2023-09-22 | 2023-10-13 | 0
'MC5.1.1.8.7 - External dependency on QA E2E Testing on Inventory Manager feature Extension drop 2'' | 2023-10-16 | 2023-10-16 |  |  | 1d | [5 empty] | 84 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-10-16 | 2023-10-16 | 0
'MC5.1.1.8.8 - Deployment on Production for Inventory Manager feature Extension drop 2 - Q4 2022 feature list '' | 2023-10-17 | 2023-10-17 |  |  | 1d | [5 empty] | 85 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-10-17 | 2023-10-17 | 0
'MC5.1.1.9 - Naming Manager Readiness'' | 2023-10-18 | 2023-11-17 |  |  | 23d | [5 empty] | 86 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2023-10-18 | 2023-11-17 | 0
'MC5.1.1.9.1 - Development - Naming Manager feature Extension drop 1 - Q2 2022 feature list'' | 2023-10-18 | 2023-10-18 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2023-10-18 | 2023-10-18 | 0
'MC5.1.1.9.2 - Deployment on Mainz Lab for Naming Manager feature Extension drop 1 - Q2 2022 feature list'' | 2023-10-19 | 2023-11-15 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 88 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2023-10-19 | 2023-11-15 | 0
'MC5.1.1.9.3 - External dependency on QA E2E Testing Naming Manager feature Extension drop 1'' | 2023-11-16 | 2023-11-16 |  |  | 1d | [5 empty] | 89 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-11-16 | 2023-11-16 | 0
'MC5.1.1.9.4 - Deployment on Production for Naming Manager feature Extension drop 1 - Q2 2022 feature list'' | 2023-11-17 | 2023-11-17 |  |  | 1d | [5 empty] | 90 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-11-17 | 2023-11-17 | 0
'MC5.1.1.10 - Topology Readiness'' | 2023-11-20 | 2024-02-09 |  |  | 60d | [5 empty] | 91 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2023-11-20 | 2024-02-09 | 0
'MC5.1.1.10.1 - Development - Topology initial deployment - Q2 2022 feature list'' | 2023-11-20 | 2023-11-20 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2023-11-20 | 2023-11-20 | 0
'MC5.1.1.10.2 - Deployment on Mainz Lab for Topology initial deployment - Q2 2022 feature list'' | 2023-11-21 | 2023-12-18 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 93 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2023-11-21 | 2023-12-18 | 0
'MC5.1.1.10.3 - External dependency on QA E2E Testing on Topology initial deployment'' | 2023-12-19 | 2023-12-19 |  |  | 1d | [5 empty] | 94 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-12-19 | 2023-12-19 | 0
'MC5.1.1.10.4 - Deployment on Production for Topology initial deployment - Q2 2022 feature list'' | 2023-12-20 | 2023-12-20 |  |  | 1d | [5 empty] | 95 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-12-20 | 2023-12-20 | 0
'MC5.1.1.10.5 - Development - Topology feature Extension drop 1 - Q4 2022 feature list'' | 2023-12-21 | 2023-12-21 |  |  | 1d | [5 empty] | 96 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2023-12-21 | 2023-12-21 | 0
'MC5.1.1.10.6 - Deployment on Mainz Lab for Topology feature Extension drop 1 - Q4 2022 feature list'' | 2023-12-22 | 2024-01-12 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 97 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2023-12-22 | 2024-01-12 | 0
'MC5.1.1.10.7 - External dependency on QA E2E Testing on Topology feature Extension drop 1'' | 2024-01-15 | 2024-01-15 |  |  | 1d | [5 empty] | 98 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-01-15 | 2024-01-15 | 0
'MC5.1.1.10.8 - Deployment on Production for Topology feature Extension drop 1 - Q4 2022 feature list'' | 2024-01-16 | 2024-01-16 |  |  | 1d | [5 empty] | 99 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-01-16 | 2024-01-16 | 0
'MC5.1.1.10.9 - Development - Topology feature Extension drop 2 - Q2 2023 feature list'' | 2024-01-17 | 2024-01-17 |  |  | 1d | [5 empty] | 100 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-01-17 | 2024-01-17 | 0
'MC5.1.1.10.10 - Deployment on Mainz Lab for Topology feature Extension drop 2 - Q2 2023 feature list'' | 2024-01-18 | 2024-02-07 | 2022-06-06 | 2022-06-24 | 15d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 101 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2024-01-18 | 2024-02-07 | 0
'MC5.1.1.10.11 - External dependency on QA E2E Testing on Topology feature Extension drop 2'' | 2024-02-08 | 2024-02-08 |  |  | 1d | [5 empty] | 102 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-02-08 | 2024-02-08 | 0
'MC5.1.1.10.12 - Deployment on Production for Topology feature Extension drop 2 - Q2 2023 feature list'' | 2024-02-09 | 2024-02-09 |  |  | 1d | [5 empty] | 103 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-02-09 | 2024-02-09 | 0
'MC5.1.1.11 - Service Desk Readiness'' | 2024-02-12 | 2024-05-30 |  |  | 79d | [5 empty] | 104 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2024-02-12 | 2024-05-30 | 0
'MC5.1.1.11.1 - Development - Service Desk feature Extension drop 1 - Q2 2022 feature list'' | 2024-02-12 | 2024-02-12 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2024-02-12 | 2024-02-12 | 0
'MC5.1.1.11.2 - Deployment on Mainz Lab for Service Desk feature Extension drop 1 - Q2 2022 feature list'' | 2024-02-13 | 2024-03-11 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 106 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2024-02-13 | 2024-03-11 | 0
'MC5.1.1.11.3 - External dependency on QA E2E Testing on Service Desk feature Extension drop 1'' | 2024-03-12 | 2024-03-12 |  |  | 1d | [5 empty] | 107 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-03-12 | 2024-03-12 | 0
'MC5.1.1.11.4 - Deployment on Production for Service Desk feature Extension drop 1 - Q2 2022 feature list'' | 2024-03-13 | 2024-03-13 |  |  | 1d | [5 empty] | 108 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-03-13 | 2024-03-13 | 0
'MC5.1.1.11.5 - Development - Service Desk feature Extension drop 2 - Q4 2022 feature list'' | 2024-03-14 | 2024-03-14 |  |  | 1d | [5 empty] | 109 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-03-14 | 2024-03-14 | 0
'MC5.1.1.11.6 - Deployment on Mainz Lab for Service Desk feature Extension drop 2 - Q4 2022 feature list'' | 2024-03-15 | 2024-04-05 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 110 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2024-03-15 | 2024-04-05 | 0
'MC5.1.1.11.7 - External dependency on QA E2E Testing on Service Desk feature Extension drop 2'' | 2024-04-08 | 2024-04-08 |  |  | 1d | [5 empty] | 111 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-04-08 | 2024-04-08 | 0
'MC5.1.1.11.8 - Deployment on Production for Service Desk feature Extension drop 2 - Q4 2022 feature list'' | 2024-04-09 | 2024-04-09 |  |  | 1d | [5 empty] | 112 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-04-09 | 2024-04-09 | 0
'MC5.1.1.11.9 - Development - Service Desk feature Extension drop 3 - Q2 2023 feature list'' | 2024-04-10 | 2024-04-10 |  |  | 1d | [5 empty] | 113 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-04-10 | 2024-04-10 | 0
'MC5.1.1.11.10 - Deployment on Mainz Lab for Service Desk feature Extension drop 3 - Q2 2023 feature list'' | 2024-04-11 | 2024-05-01 | 2022-06-06 | 2022-06-24 | 15d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 114 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2024-04-11 | 2024-05-01 | 0
'MC5.1.1.11.11 - External dependency on QA E2E Testing on Service Desk feature Extension drop 3'' | 2024-05-02 | 2024-05-02 |  |  | 1d | [5 empty] | 115 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-05-02 | 2024-05-02 | 0
'MC5.1.1.11.12 - Deployment on Production for Service Desk feature Extension drop 3 - Q2 2023 feature list'' | 2024-05-03 | 2024-05-03 |  |  | 1d | [5 empty] | 116 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-05-03 | 2024-05-03 | 0
'MC5.1.1.11.13 - Development - Service Desk feature Extension drop 4 - Q4 2023 feature list'' | 2024-05-06 | 2024-05-06 |  |  | 1d | [5 empty] | 117 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-05-06 | 2024-05-06 | 0
'MC5.1.1.11.14 - Deployment on Mainz Lab for Service Desk feature Extension drop 4 - Q4 2023 feature list'' | 2024-05-07 | 2024-05-28 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 118 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2024-05-07 | 2024-05-28 | 0
'MC5.1.1.11.15 - External dependency on QA E2E Testing on Service Desk feature Extension drop 4'' | 2024-05-29 | 2024-05-29 |  |  | 1d | [5 empty] | 119 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-05-29 | 2024-05-29 | 0
'MC5.1.1.11.16 - Deployment on Production for Service Desk feature Extension drop 4 - Q4 2023 feature list'' | 2024-05-30 | 2024-05-30 |  |  | 1d | [5 empty] | 120 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-05-30 | 2024-05-30 | 0
'MC5.1.1.12 - Performance Monitor Readiness'' | 2024-05-31 | 2024-08-22 |  |  | 60d | [5 empty] | 121 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2024-05-31 | 2024-08-22 | 0
'MC5.1.1.12.1 - Development - Performance Monitor feature Extension drop 1 - Q2 2022 feature list'' | 2024-05-31 | 2024-05-31 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2024-05-31 | 2024-05-31 | 0
'MC5.1.1.12.2 - Deployment on Mainz Lab for Performance Monitor feature Extension drop 1 - Q2 2022 feature list'' | 2024-06-03 | 2024-06-28 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 123 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2024-06-03 | 2024-06-28 | 0
'MC5.1.1.12.3 - External dependency on QA E2E Testing on Performance Monitor feature Extension drop 1'' | 2024-07-01 | 2024-07-01 |  |  | 1d | [5 empty] | 124 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-07-01 | 2024-07-01 | 0
'MC5.1.1.12.4 - Deployment on Production for Performance Monitor feature Extension drop 1 - Q2 2022 feature list'' | 2024-07-02 | 2024-07-02 |  |  | 1d | [5 empty] | 125 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-07-02 | 2024-07-02 | 0
'MC5.1.1.12.5 - Development - Performance Monitor feature Extension drop 2 - Q4 2022 feature list'' | 2024-07-03 | 2024-07-03 |  |  | 1d | [5 empty] | 126 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-07-03 | 2024-07-03 | 0
'MC5.1.1.12.6 - Deployment on Mainz Lab for Performance Monitor feature Extension drop 2 - Q4 2022 feature list'' | 2024-07-04 | 2024-07-25 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 127 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2024-07-04 | 2024-07-25 | 0
'MC5.1.1.12.7 - External dependency on QA E2E Testing on Performance Monitor feature Extension drop 2'' | 2024-07-26 | 2024-07-26 |  |  | 1d | [5 empty] | 128 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-07-26 | 2024-07-26 | 0
'MC5.1.1.12.8 - Deployment on Production for Performance Monitor feature Extension drop 2 - Q4 2022 feature list'' | 2024-07-29 | 2024-07-29 |  |  | 1d | [5 empty] | 129 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-07-29 | 2024-07-29 | 0
'MC5.1.1.12.9 - Development - Performance Monitor feature Extension drop 3 - Q2 2023 feature list'' | 2024-07-30 | 2024-07-30 |  |  | 1d | [5 empty] | 130 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-07-30 | 2024-07-30 | 0
'MC5.1.1.12.10 - Deployment on Mainz Lab for Performance Monitor feature Extension drop 3 - Q2 2023 feature list'' | 2024-07-31 | 2024-08-20 | 2022-06-06 | 2022-06-24 | 15d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 131 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2024-07-31 | 2024-08-20 | 0
'MC5.1.1.12.11 - External dependency on QA E2E Testing on Performance Monitor feature Extension drop 3'' | 2024-08-21 | 2024-08-21 |  |  | 1d | [5 empty] | 132 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-08-21 | 2024-08-21 | 0
'MC5.1.1.12.12 - Deployment on Production for Performance Monitor feature Extension drop 3 - Q2 2023 feature list'' | 2024-08-22 | 2024-08-22 |  |  | 1d | [5 empty] | 133 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-08-22 | 2024-08-22 | 0
'MC5.1.1.13 - Fault Monitor Readiness'' | 2024-08-23 | 2024-10-29 |  |  | 48d | [5 empty] | 134 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2024-08-23 | 2024-10-29 | 0
'MC5.1.1.13.1 - Development - Fault Monitor feature Extension drop 1 - Q2 2022 feature list'' | 2024-08-23 | 2024-08-23 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2024-08-23 | 2024-08-23 | 0
'MC5.1.1.13.2 - Deployment on Mainz Lab for Fault Monitor feature Extension drop 1 - Q2 2022 feature list'' | 2024-08-26 | 2024-09-20 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 136 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2024-08-26 | 2024-09-20 | 0
'MC5.1.1.13.3 - External dependency on QA E2E Testing on Fault Monitor feature Extension drop 1'' | 2024-09-23 | 2024-09-23 |  |  | 1d | [5 empty] | 137 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-09-23 | 2024-09-23 | 0
'MC5.1.1.13.4 - Deployment on Production for Fault Monitor feature Extension drop 1 - Q2 2022 feature list'' | 2024-09-24 | 2024-09-24 |  |  | 1d | [5 empty] | 138 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-09-24 | 2024-09-24 | 0
'MC5.1.1.13.5 - Development - Fault Monitor feature Extension drop 2 - Q4 2022 feature list'' | 2024-09-25 | 2024-09-25 |  |  | 1d | [5 empty] | 139 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-09-25 | 2024-09-25 | 0
'MC5.1.1.13.6 - Deployment on Mainz Lab for Fault Monitor feature Extension drop 2 - Q4 2022 feature list'' | 2024-09-26 | 2024-10-17 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 140 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2024-09-26 | 2024-10-17 | 0
'MC5.1.1.13.7 - External dependency on QA E2E Testing on Fault Monitor feature Extension drop 2'' | 2024-10-18 | 2024-10-18 |  |  | 1d | [5 empty] | 141 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-10-18 | 2024-10-18 | 0
'MC5.1.1.13.8 - Deployment on Production for Fault Monitor feature Extension drop 2 - Q4 2022 feature list'' | 2024-10-21 | 2024-10-21 |  |  | 1d | [5 empty] | 142 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-10-21 | 2024-10-21 | 0
'MC5.1.1.13.9 - Development - Fault Monitor feature Extension drop 3 - Q2 2023 feature list'' | 2024-10-22 | 2024-10-22 |  |  | 1d | [5 empty] | 143 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-10-22 | 2024-10-22 | 0
'MC5.1.1.13.10 - Deployment on Mainz Lab for Fault Monitor feature Extension drop 3 - Q2 2023 feature list'' | 2024-10-23 | 2024-10-25 | 2023-01-02 | 2023-01-03 | 3d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 144 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2024-10-23 | 2024-10-25 | 0
'MC5.1.1.13.11 - External dependency on QA E2E Testing on Fault Monitor feature Extension drop 3'' | 2024-10-28 | 2024-10-28 |  |  | 1d | [5 empty] | 145 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-10-28 | 2024-10-28 | 0
'MC5.1.1.13.12 - Deployment on Production for Fault Monitor feature Extension drop 3 - Q2 2023 feature list'' | 2024-10-29 | 2024-10-29 |  |  | 1d | [5 empty] | 146 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-10-29 | 2024-10-29 | 0
'MC5.1.1.14 - BI Studio Readiness'' | 2024-10-30 | 2024-12-26 |  |  | 42d | [5 empty] | 147 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2024-10-30 | 2024-12-26 | 0
'MC5.1.1.14.1 - Development - BI Studio feature Extension drop 1 - Q2 2022 feature list'' | 2024-10-30 | 2024-10-30 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2024-10-30 | 2024-10-30 | 0
'MC5.1.1.14.2 - Deployment on Mainz Lab for BI Studio feature Extension drop 1 - Q2 2022 feature list'' | 2024-10-31 | 2024-11-27 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 149 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2024-10-31 | 2024-11-27 | 0
'MC5.1.1.14.3 - External dependency on QA E2E Testing on BI Studio feature Extension drop 1'' | 2024-11-28 | 2024-11-28 |  |  | 1d | [5 empty] | 150 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-11-28 | 2024-11-28 | 0
'MC5.1.1.14.4 - Deployment on Production for BI Studio feature Extension drop 1 - Q2 2022 feature list'' | 2024-11-29 | 2024-11-29 |  |  | 1d | [5 empty] | 151 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-11-29 | 2024-11-29 | 0
'MC5.1.1.14.5 - Development - BI Studio feature Extension drop 2 - Q4 2022 feature list'' | 2024-12-02 | 2024-12-02 |  |  | 1d | [5 empty] | 152 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-12-02 | 2024-12-02 | 0
'MC5.1.1.14.6 - Deployment on Mainz Lab for BI Studio feature Extension drop 2 - Q4 2022 feature list'' | 2024-12-03 | 2024-12-24 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 153 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2024-12-03 | 2024-12-24 | 0
'MC5.1.1.14.7 - External dependency on QA E2E Testing on BI Studio feature Extension drop 2'' | 2024-12-25 | 2024-12-25 |  |  | 1d | [5 empty] | 154 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-12-25 | 2024-12-25 | 0
'MC5.1.1.14.8 - Deployment on Production for BI Studio feature Extension drop 2 - Q4 2022 feature list'' | 2024-12-26 | 2024-12-26 |  |  | 1d | [5 empty] | 155 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2024-12-26 | 2024-12-26 | 0
'MC5.1.1.15 - Automation Studio Readiness'' | 2024-12-27 | 2025-03-21 |  |  | 61d | [5 empty] | 156 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2024-12-27 | 2025-03-21 | 0
'MC5.1.1.15.1 - Development - Automation Studio initial deployment - Q2 2022 feature list'' | 2024-12-27 | 2024-12-27 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2024-12-27 | 2024-12-27 | 0
'MC5.1.1.15.2 - Deployment on Mainz Lab for Automation Studio initial deployment - Q2 2022 feature list'' | 2024-12-30 | 2025-01-24 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 158 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2024-12-30 | 2025-01-24 | 0
'MC5.1.1.15.3 - External dependency on QA E2E Testing on Automation Studio initial deployment'' | 2025-01-27 | 2025-01-27 |  |  | 1d | [5 empty] | 159 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-01-27 | 2025-01-27 | 0
'MC5.1.1.15.4 - Deployment on Production for Automation Studio initial deployment - Q2 2022 feature list'' | 2025-01-28 | 2025-01-28 |  |  | 1d | [5 empty] | 160 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-01-28 | 2025-01-28 | 0
'MC5.1.1.15.5 - Development - Automation Studio feature Extension drop 1 - Q4 2022 feature list'' | 2025-01-29 | 2025-01-29 |  |  | 1d | [5 empty] | 161 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-01-29 | 2025-01-29 | 0
'MC5.1.1.15.6 - Deployment on Mainz Lab for Automation Studio feature Extension drop 1 - Q4 2022 feature list'' | 2025-01-30 | 2025-02-20 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 162 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2025-01-30 | 2025-02-20 | 0
'MC5.1.1.15.7 - External dependency on QA E2E Testing on Automation Studio feature Extension drop 1'' | 2025-02-21 | 2025-02-21 |  |  | 1d | [5 empty] | 163 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-02-21 | 2025-02-21 | 0
'MC5.1.1.15.8 - Deployment on Production for Automation Studio feature Extension drop 1 - Q4 2022 feature list'' | 2025-02-24 | 2025-02-24 |  |  | 1d | [5 empty] | 164 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-02-24 | 2025-02-24 | 0
'MC5.1.1.15.9 - Development - Automation Studio feature Extension drop 2 - Q2 2023 feature list'' | 2025-02-25 | 2025-02-25 |  |  | 1d | [5 empty] | 165 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-02-25 | 2025-02-25 | 0
'MC5.1.1.15.10 - Deployment on Mainz Lab for Automation Studio feature Extension drop 2 - Q2 2023 feature list'' | 2025-02-26 | 2025-03-19 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 166 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2025-02-26 | 2025-03-19 | 0
'MC5.1.1.15.11 - External dependency on QA E2E Testing on Automation Studio feature Extension drop 2'' | 2025-03-20 | 2025-03-20 |  |  | 1d | [5 empty] | 167 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-03-20 | 2025-03-20 | 0
'MC5.1.1.15.12 - Deployment on Production for Automation Studio feature Extension drop 2 - Q2 2023 feature list'' | 2025-03-21 | 2025-03-21 |  |  | 1d | [5 empty] | 168 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-03-21 | 2025-03-21 | 0
'MC5.1.1.16 - Notifications Hub Readiness'' | 2025-03-24 | 2025-05-20 |  |  | 42d | [5 empty] | 169 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2025-03-24 | 2025-05-20 | 0
'MC5.1.1.16.1 - Development - Notifications Hub feature Extension drop 1 - Q2 2022 feature list'' | 2025-03-24 | 2025-03-24 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2025-03-24 | 2025-03-24 | 0
'MC5.1.1.16.2 - Deployment on Mainz Lab for Notifications Hub feature Extension drop 1 - Q2 2022 feature list'' | 2025-03-25 | 2025-04-21 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 171 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2025-03-25 | 2025-04-21 | 0
'MC5.1.1.16.3 - External dependency on QA E2E Testing on Notifications Hub feature Extension drop 1'' | 2025-04-22 | 2025-04-22 |  |  | 1d | [5 empty] | 172 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-04-22 | 2025-04-22 | 0
'MC5.1.1.16.4 - Deployment on Production for Notifications Hub feature Extension drop 1 - Q2 2022 feature list'' | 2025-04-23 | 2025-04-23 |  |  | 1d | [5 empty] | 173 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-04-23 | 2025-04-23 | 0
'MC5.1.1.16.5 - Development Notifications Hub feature Extension drop 2'' | 2025-04-24 | 2025-04-24 |  |  | 1d | [5 empty] | 174 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-04-24 | 2025-04-24 | 0
'MC5.1.1.16.6 - Deployment on Mainz Lab for Notifications Hub feature Extension drop 2'' | 2025-04-25 | 2025-05-16 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 175 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2025-04-25 | 2025-05-16 | 0
'MC5.1.1.16.7 - External dependency on QA E2E Testing on Notifications Hub feature Extension drop 1'' | 2025-05-19 | 2025-05-19 |  |  | 1d | [5 empty] | 176 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-05-19 | 2025-05-19 | 0
'MC5.1.1.16.8 - Deployment on Production for Notifications Hub feature Extension drop 2'' | 2025-05-20 | 2025-05-20 |  |  | 1d | [5 empty] | 177 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-05-20 | 2025-05-20 | 0
'MC5.1.1.17 - Watchtower'' | 2025-05-21 | 2025-09-08 |  |  | 79d | [5 empty] | 178 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2025-05-21 | 2025-09-08 | 0
'MC5.1.1.17.1 - Development - Watchtower feature Extension drop 1 - Q2 2022 feature list'' | 2025-05-21 | 2025-05-21 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2025-05-21 | 2025-05-21 | 0
'MC5.1.1.17.2 - Deployment on Mainz Lab for Watchtower feature Extension drop 1 - Q2 2022 feature list'' | 2025-05-22 | 2025-06-18 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 180 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2025-05-22 | 2025-06-18 | 0
'MC5.1.1.17.3 - External dependency on QA E2E Testing on Watchtower feature Extension drop 1'' | 2025-06-19 | 2025-06-19 |  |  | 1d | [5 empty] | 181 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-06-19 | 2025-06-19 | 0
'MC5.1.1.17.4 - Deployment on Production for Watchtower feature Extension drop 1 - Q2 2022 feature list'' | 2025-06-20 | 2025-06-20 |  |  | 1d | [5 empty] | 182 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-06-20 | 2025-06-20 | 0
'MC5.1.1.17.5 - Development - Watchtower feature Extension drop 2 - Q4 2022 feature list'' | 2025-06-23 | 2025-06-23 |  |  | 1d | [5 empty] | 183 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-06-23 | 2025-06-23 | 0
'MC5.1.1.17.6 - Deployment on Mainz Lab for Watchtower feature Extension drop 2 - Q4 2022 feature list'' | 2025-06-24 | 2025-07-15 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 184 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2025-06-24 | 2025-07-15 | 0
'MC5.1.1.17.7 - External dependency on QA E2E Testing on Watchtower feature Extension drop 2'' | 2025-07-16 | 2025-07-16 |  |  | 1d | [5 empty] | 185 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-07-16 | 2025-07-16 | 0
'MC5.1.1.17.8 - Deployment on Production for Watchtower feature Extension drop 2 - Q4 2022 feature list'' | 2025-07-17 | 2025-07-17 |  |  | 1d | [5 empty] | 186 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-07-17 | 2025-07-17 | 0
'MC5.1.1.17.9 - Development - Watchtower feature Extension drop 1 - Q2 2023 feature list'' | 2025-07-18 | 2025-07-18 |  |  | 1d | [5 empty] | 187 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-07-18 | 2025-07-18 | 0
'MC5.1.1.17.10 - Deployment on Mainz Lab for Watchtower feature Extension drop 1 - Q2 2023 feature list'' | 2025-07-21 | 2025-08-08 | 2022-06-06 | 2022-06-24 | 15d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 188 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2025-07-21 | 2025-08-08 | 0
'MC5.1.1.17.11 - External dependency on QA E2E Testing on Watchtower feature Extension drop 1'' | 2025-08-11 | 2025-08-11 |  |  | 1d | [5 empty] | 189 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-08-11 | 2025-08-11 | 0
'MC5.1.1.17.12 - Deployment on Production for Watchtower feature Extension drop 1 - Q2 2023 feature list'' | 2025-08-12 | 2025-08-12 |  |  | 1d | [5 empty] | 190 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-08-12 | 2025-08-12 | 0
'MC5.1.1.17.13 - Development - Watchtower feature Extension drop 1 - Q4 2023 feature list - Q2 2023'' | 2025-08-13 | 2025-08-13 |  |  | 1d | [5 empty] | 191 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-08-13 | 2025-08-13 | 0
'MC5.1.1.17.14 - Deployment on Mainz Lab for Watchtower feature Extension drop 1 - Q4 2023 feature list'' | 2025-08-14 | 2025-09-04 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 192 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2025-08-14 | 2025-09-04 | 0
'MC5.1.1.17.15 - External dependency on QA E2E Testing on Watchtower feature Extension drop 1 - Q4 2023'' | 2025-09-05 | 2025-09-05 |  |  | 1d | [5 empty] | 193 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-09-05 | 2025-09-05 | 0
'MC5.1.1.17.16 - Deployment on Production for Watchtower feature Extension drop 1 - Q4 2023 feature list'' | 2025-09-08 | 2025-09-08 |  |  | 1d | [5 empty] | 194 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-09-08 | 2025-09-08 | 0
'MC5.1.1.18 - Subscriber Experience Readiness'' | 2025-09-09 | 2025-11-05 |  |  | 42d | [5 empty] | 195 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2025-09-09 | 2025-11-05 | 0
'MC5.1.1.18.1 - Development - Subscriber Experience feature Extension drop 1 - Q1 2022 feature list'' | 2025-09-09 | 2025-09-09 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2025-09-09 | 2025-09-09 | 0
'MC5.1.1.18.2 - Deployment on Mainz Lab for Subscriber Experience feature Extension drop 1 - Q1 2022 feature list'' | 2025-09-10 | 2025-10-07 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 197 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2025-09-10 | 2025-10-07 | 0
'MC5.1.1.18.3 - External dependency on QA E2E Testing on Subscriber Experience feature Extension drop 1'' | 2025-10-08 | 2025-10-08 |  |  | 1d | [5 empty] | 198 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-10-08 | 2025-10-08 | 0
'MC5.1.1.18.4 - Deployment on Production for Subscriber Experience feature Extension drop 1 - Q1 2022 feature list'' | 2025-10-09 | 2025-10-09 |  |  | 1d | [5 empty] | 199 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-10-09 | 2025-10-09 | 0
'MC5.1.1.18.5 - Development - Subscriber Experience feature Extension drop 2 - Q3 2022 feature list'' | 2025-10-10 | 2025-10-10 |  |  | 1d | [5 empty] | 200 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-10-10 | 2025-10-10 | 0
'MC5.1.1.18.6 - Deployment on Mainz Lab for Subscriber Experience feature Extension drop 2 - Q3 2022 feature list'' | 2025-10-13 | 2025-11-03 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 201 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2025-10-13 | 2025-11-03 | 0
'MC5.1.1.18.7 - External dependency on QA E2E Testing on Subscriber Experience feature Extension drop 2'' | 2025-11-04 | 2025-11-04 |  |  | 1d | [5 empty] | 202 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-11-04 | 2025-11-04 | 0
'MC5.1.1.18.8 - Deployment on Production for Subscriber Experience feature Extension drop 2 - Q3 2022 feature list'' | 2025-11-05 | 2025-11-05 |  |  | 1d | [5 empty] | 203 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-11-05 | 2025-11-05 | 0
'MC5.1.1.19 - Knowledge Hub Readiness'' | 2025-11-06 | 2025-12-08 |  |  | 23d | [5 empty] | 204 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2025-11-06 | 2025-12-08 | 0
'MC5.1.1.19.1 - Development - Knowledge Hub feature Extension drop 1 - Q2 2022 feature list'' | 2025-11-06 | 2025-11-06 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2025-11-06 | 2025-11-06 | 0
'MC5.1.1.19.2 - Deployment on Mainz Lab for Knowledge Hub feature Extension drop 1 - Q2 2022 feature list'' | 2025-11-07 | 2025-12-04 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 206 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2025-11-07 | 2025-12-04 | 0
'MC5.1.1.19.3 - External dependency on QA E2E Testing on Knowledge Hub feature Extension drop 1'' | 2025-12-05 | 2025-12-05 |  |  | 1d | [5 empty] | 207 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-12-05 | 2025-12-05 | 0
'MC5.1.1.19.4 - Deployment on Production for Knowledge Hub feature Extension drop 1 - Q2 2022 feature list'' | 2025-12-08 | 2025-12-08 |  |  | 1d | [5 empty] | 208 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2025-12-08 | 2025-12-08 | 0
'MC5.1.1.20 - Service Designer Readiness'' | 2025-12-09 | 2026-02-04 |  |  | 42d | [5 empty] | 209 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2025-12-09 | 2026-02-04 | 0
'MC5.1.1.20.1 - Development - Service Designer feature Extension drop 1 - Q2 2022 feature list'' | 2025-12-09 | 2025-12-09 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2025-12-09 | 2025-12-09 | 0
'MC5.1.1.20.2 - Deployment on Mainz Lab for Service Designer feature Extension drop 1 - Q2 2022 feature list'' | 2025-12-10 | 2026-01-06 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 211 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2025-12-10 | 2026-01-06 | 0
'MC5.1.1.20.3 - External dependency on QA E2E Testing on Service Designer feature Extension drop 1'' | 2026-01-07 | 2026-01-07 |  |  | 1d | [5 empty] | 212 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-01-07 | 2026-01-07 | 0
'MC5.1.1.20.4 - Deployment on Production for Service Designer feature Extension drop 1 - Q2 2022 feature list'' | 2026-01-08 | 2026-01-08 |  |  | 1d | [5 empty] | 213 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-01-08 | 2026-01-08 | 0
'MC5.1.1.20.5 - Development - Service Designer feature Extension drop 2 - Q4 2022 feature list'' | 2026-01-09 | 2026-01-09 |  |  | 1d | [5 empty] | 214 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-01-09 | 2026-01-09 | 0
'MC5.1.1.20.6 - Deployment on Mainz Lab for Service Designer feature Extension drop 2 - Q4 2022 feature list'' | 2026-01-12 | 2026-02-02 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 215 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2026-01-12 | 2026-02-02 | 0
'MC5.1.1.20.7 - External dependency on QA E2E Testing on Service Designer feature Extension drop 2'' | 2026-02-03 | 2026-02-03 |  |  | 1d | [5 empty] | 216 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-02-03 | 2026-02-03 | 0
'MC5.1.1.20.8 - Deployment on Production for Service Designer feature Extension drop 2 - Q4 2022 feature list'' | 2026-02-04 | 2026-02-04 |  |  | 1d | [5 empty] | 217 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-02-04 | 2026-02-04 | 0
'MC5.1.1.21 - Orchestrator Readiness'' | 2026-02-05 | 2026-04-30 |  |  | 61d | [5 empty] | 218 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2026-02-05 | 2026-04-30 | 0
'MC5.1.1.21.1 - Development - Orchestrator feature Extension drop 1 - Q2 2022 feature list'' | 2026-02-05 | 2026-02-05 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2026-02-05 | 2026-02-05 | 0
'MC5.1.1.21.2 - Deployment on Mainz Lab for Orchestrator feature Extension drop 1 - Q2 2022 feature list'' | 2026-02-06 | 2026-03-05 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 220 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2026-02-06 | 2026-03-05 | 0
'MC5.1.1.21.3 - External dependency on QA E2E Testing on Orchestrator feature Extension drop 1'' | 2026-03-06 | 2026-03-06 |  |  | 1d | [5 empty] | 221 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-03-06 | 2026-03-06 | 0
'MC5.1.1.21.4 - Deployment on Production for Orchestrator feature Extension drop 1 - Q2 2022 feature list'' | 2026-03-09 | 2026-03-09 |  |  | 1d | [5 empty] | 222 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-03-09 | 2026-03-09 | 0
'MC5.1.1.21.5 - Development - Orchestrator feature Extension drop 2 - Q4 2022 feature list'' | 2026-03-10 | 2026-03-10 |  |  | 1d | [5 empty] | 223 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-03-10 | 2026-03-10 | 0
'MC5.1.1.21.6 - Deployment on Mainz Lab for Orchestrator feature Extension drop 2 - Q4 2022 feature list'' | 2026-03-11 | 2026-04-01 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 224 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2026-03-11 | 2026-04-01 | 0
'MC5.1.1.21.7 - External dependency on QA E2E Testing on Orchestrator feature Extension drop 2'' | 2026-04-02 | 2026-04-02 |  |  | 1d | [5 empty] | 225 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-04-02 | 2026-04-02 | 0
'MC5.1.1.21.8 - Deployment on Production for Orchestrator feature Extension drop 2 - Q4 2022 feature list'' | 2026-04-03 | 2026-04-03 |  |  | 1d | [5 empty] | 226 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-04-03 | 2026-04-03 | 0
'MC5.1.1.21.9 - Development - Orchestrator feature Extension drop 3 - Q2 2023 feature list'' | 2026-04-06 | 2026-04-06 |  |  | 1d | [5 empty] | 227 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-04-06 | 2026-04-06 | 0
'MC5.1.1.21.10 - Deployment on Mainz Lab for Orchestrator feature Extension drop 3 - Q2 2023 feature list'' | 2026-04-07 | 2026-04-28 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 228 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2026-04-07 | 2026-04-28 | 0
'MC5.1.1.21.11 - External dependency on QA E2E Testing on Orchestrator feature Extension drop 3'' | 2026-04-29 | 2026-04-29 |  |  | 1d | [5 empty] | 229 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-04-29 | 2026-04-29 | 0
'MC5.1.1.21.12 - Deployment on Production for Orchestrator feature Extension drop 3 - Q2 2023 feature list'' | 2026-04-30 | 2026-04-30 |  |  | 1d | [5 empty] | 230 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-04-30 | 2026-04-30 | 0
'MC5.1.1.22 - Harmony Readiness'' | 2026-05-01 | 2026-07-24 |  |  | 61d | [5 empty] | 231 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2026-05-01 | 2026-07-24 | 0
'MC5.1.1.22.1 - Development - Harmony feature Extension drop 1 - Q2 2022 feature list'' | 2026-05-01 | 2026-05-01 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2026-05-01 | 2026-05-01 | 0
'MC5.1.1.22.2 - Deployment on Mainz Lab for Harmony feature Extension drop 3 - Q2 2023 feature list'' | 2026-05-04 | 2026-05-25 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 233 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2026-05-04 | 2026-05-25 | 0
'MC5.1.1.22.3 - External dependency on QA E2E Testing on Harmony feature Extension drop 1'' | 2026-05-26 | 2026-05-26 |  |  | 1d | [5 empty] | 234 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-05-26 | 2026-05-26 | 0
'MC5.1.1.22.4 - Deployment on Production for Harmony feature Extension drop 3 - Q2 2023 feature list'' | 2026-05-27 | 2026-05-27 |  |  | 1d | [5 empty] | 235 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-05-27 | 2026-05-27 | 0
'MC5.1.1.22.5 - Development - Harmony feature Extension drop 1 - Q2 2022 feature list'' | 2026-05-28 | 2026-05-28 |  |  | 1d | [5 empty] | 236 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-05-28 | 2026-05-28 | 0
'MC5.1.1.22.6 - Deployment on Mainz Lab for Harmony feature Extension drop 1 - Q2 2022 feature list'' | 2026-05-29 | 2026-06-25 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 237 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2026-05-29 | 2026-06-25 | 0
'MC5.1.1.22.7 - External dependency on QA E2E Testing on Harmony feature Extension drop 1'' | 2026-06-26 | 2026-06-26 |  |  | 1d | [5 empty] | 238 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-06-26 | 2026-06-26 | 0
'MC5.1.1.22.8 - Deployment on Production for Harmony feature Extension drop 1 - Q2 2022 feature list'' | 2026-06-29 | 2026-06-29 |  |  | 1d | [5 empty] | 239 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-06-29 | 2026-06-29 | 0
'MC5.1.1.22.9 - Development - Harmony feature Extension drop 2 - Q4 2022 feature list'' | 2026-06-30 | 2026-06-30 |  |  | 1d | [5 empty] | 240 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-06-30 | 2026-06-30 | 0
'MC5.1.1.22.10 - Deployment on Mainz Lab for Harmony feature Extension drop 2 - Q4 2022 feature list'' | 2026-07-01 | 2026-07-22 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 241 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2026-07-01 | 2026-07-22 | 0
'MC5.1.1.22.11 - External dependency on QA E2E Testing on Harmony feature Extension drop 2'' | 2026-07-23 | 2026-07-23 |  |  | 1d | [5 empty] | 242 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-07-23 | 2026-07-23 | 0
'MC5.1.1.22.12 - Deployment on Production for Harmony feature Extension drop 2 - Q4 2022 feature list'' | 2026-07-24 | 2026-07-24 |  |  | 1d | [5 empty] | 243 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-07-24 | 2026-07-24 | 0
'MC5.1.1.23 - Cloud Observability Readiness'' | 2026-07-27 | 2026-11-19 |  |  | 84d | [5 empty] | 244 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2026-07-27 | 2026-11-19 | 0
'MC5.1.1.23.1 - Development - Cloud Observability feature Extension drop 1 - Q2 2022 feature list'' | 2026-07-27 | 2026-07-27 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2026-07-27 | 2026-07-27 | 0
'MC5.1.1.23.2 - Deployment on Mainz Lab for Cloud Observability feature Extension drop 1 - Q2 2022 feature list'' | 2026-07-28 | 2026-08-24 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 246 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2026-07-28 | 2026-08-24 | 0
'MC5.1.1.23.2 - External dependency on QA E2E Testing on Cloud Observability feature Extension drop 1'' | 2026-08-25 | 2026-08-25 |  |  | 1d | [5 empty] | 247 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-08-25 | 2026-08-25 | 0
'MC5.1.1.23.3 - Deployment on Production for Cloud Observability feature Extension drop 1 - Q2 2022 feature list'' | 2026-08-26 | 2026-08-26 |  |  | 1d | [5 empty] | 248 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-08-26 | 2026-08-26 | 0
'MC5.1.1.23.4 - Development - Cloud Observability integration extension - Q2 2022 feature list'' | 2026-08-27 | 2026-08-27 |  |  | 1d | [5 empty] | 249 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-08-27 | 2026-08-27 | 0
'MC5.1.1.23.5 - Deployment on Mainz Lab for Cloud Observability integration extension - Q2 2022 feature list'' | 2026-08-28 | 2026-09-24 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 250 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2026-08-28 | 2026-09-24 | 0
'MC5.1.1.23.6 - External dependency on QA E2E Testing on Cloud Observability integration extension - Q2 2022'' | 2026-09-25 | 2026-09-25 |  |  | 1d | [5 empty] | 251 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-09-25 | 2026-09-25 | 0
'MC5.1.1.23.7 - Deployment on Production for Cloud Observability integration extension - Q2 2022 feature list'' | 2026-09-28 | 2026-09-28 |  |  | 1d | [5 empty] | 252 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-09-28 | 2026-09-28 | 0
'Development - Cloud Observability feature Extension drop 2 - Q4 2022 feature list'' | 2026-09-29 | 2026-09-29 |  |  | 1d | [5 empty] | 253 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-09-29 | 2026-09-29 | 0
'MC5.1.1.23.3 - Deployment on Mainz Lab for Cloud Observability feature Extension drop 2 - Q4 2022 feature list'' | 2026-09-30 | 2026-10-21 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 254 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2026-09-30 | 2026-10-21 | 0
'External dependency on QA E2E Testing on Cloud Observability feature Extension drop 2 - Q4 2022'' | 2026-10-22 | 2026-10-22 |  |  | 1d | [5 empty] | 255 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-10-22 | 2026-10-22 | 0
'Deployment on Production for Cloud Observability feature Extension drop 2 - Q4 2022 feature list'' | 2026-10-23 | 2026-10-23 |  |  | 1d | [5 empty] | 256 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-10-23 | 2026-10-23 | 0
'Development - Cloud Observability feature Extension drop 3 - Q2 2023 feature list'' | 2026-10-26 | 2026-10-26 |  |  | 1d | [5 empty] | 257 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-10-26 | 2026-10-26 | 0
'MC5.1.1.23.4 - Deployment on Mainz Lab for Cloud Observability feature Extension drop 3 - Q2 2023 feature list'' | 2026-10-27 | 2026-11-17 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 258 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2026-10-27 | 2026-11-17 | 0
'External dependency on QA E2E Testing on Cloud Observability feature Extension drop 3 - Q2 2023'' | 2026-11-18 | 2026-11-18 |  |  | 1d | [5 empty] | 259 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-11-18 | 2026-11-18 | 0
'Deployment on Production for Cloud Observability feature Extension drop 3 - Q2 2023 feature list'' | 2026-11-19 | 2026-11-19 |  |  | 1d | [5 empty] | 260 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-11-19 | 2026-11-19 | 0
'MC5.1.1.24 - Bare Metal Manager Readiness'' | 2026-11-20 | 2027-02-12 |  |  | 61d | [5 empty] | 261 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2026-11-20 | 2027-02-12 | 0
'Development - Bare Metal Manager feature Extension drop 1 - Q2 2022 feature list'' | 2026-11-20 | 2026-11-20 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2026-11-20 | 2026-11-20 | 0
'MC5.1.1.24.1 - Deployment on Mainz Lab for Bare Metal Manager feature Extension drop 1 - Q2 2022 feature list'' | 2026-11-23 | 2026-12-18 | 2022-06-06 | 2022-07-01 | 20d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 263 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2026-11-23 | 2026-12-18 | 0
'External dependency on QA E2E Testing on Bare Metal Manager feature Extension drop 1'' | 2026-12-21 | 2026-12-21 |  |  | 1d | [5 empty] | 264 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-12-21 | 2026-12-21 | 0
'Deployment on Production for Bare Metal Manager feature Extension drop 1 - Q2 2022 feature list'' | 2026-12-22 | 2026-12-22 |  |  | 1d | [5 empty] | 265 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-12-22 | 2026-12-22 | 0
'Development - Bare Metal Manager feature Extension drop 2 - Q4 2022 feature list'' | 2026-12-23 | 2026-12-23 |  |  | 1d | [5 empty] | 266 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2026-12-23 | 2026-12-23 | 0
'MC5.1.1.24.2 - Deployment on Mainz Lab for Bare Metal Manager feature Extension drop 2 - Q4 2022 feature list'' | 2026-12-24 | 2027-01-14 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 267 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2026-12-24 | 2027-01-14 | 0
'External dependency on QA E2E Testing on Bare Metal Manager feature Extension drop 2'' | 2027-01-15 | 2027-01-15 |  |  | 1d | [5 empty] | 268 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2027-01-15 | 2027-01-15 | 0
'Deployment on Production for Bare Metal Manager feature Extension drop 2 - Q4 2022 feature list'' | 2027-01-18 | 2027-01-18 |  |  | 1d | [5 empty] | 269 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2027-01-18 | 2027-01-18 | 0
'Development - Bare Metal Manager feature Extension drop 3 - Q2 2023 feature list'' | 2027-01-19 | 2027-01-19 |  |  | 1d | [5 empty] | 270 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2027-01-19 | 2027-01-19 | 0
'MC5.1.1.24.3 - Deployment on Mainz Lab for Bare Metal Manager feature Extension drop 3 - Q2 2023 feature list'' | 2027-01-20 | 2027-02-10 | 2022-06-06 | 2022-06-27 | 16d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 271 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | For feature details, refer to Automator & Uplift Product Roadmap | Yes | eMBB | SE&I: OSS & Orchestration | No |  | 2027-01-20 | 2027-02-10 | 0
'External dependency on QA E2E Testing on Bare Metal Manager feature Extension drop 3'' | 2027-02-11 | 2027-02-11 |  |  | 1d | [5 empty] | 272 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2027-02-11 | 2027-02-11 | 0
'Deployment on Production for Bare Metal Manager feature Extension drop 3 - Q2 2023 feature list'' | 2027-02-12 | 2027-02-12 |  |  | 1d | [5 empty] | 273 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2027-02-12 | 2027-02-12 | 0
MC5.1.2 - Supported Use Cases Extension' | 2027-02-15 | 2133-11-23 |  |  | 27856d | [5 empty] | 274 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2027-02-15 | 2133-11-23 | 0
MC5.1.2.1 - Deployment of all Automator & Uplift application features and customizations available ' | 2027-02-15 | 2027-03-08 |  |  | 16d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2027-02-15 | 2027-03-08 | 0
MC5.1.2.1.1 - External dependency on Mainz lab readiness' | 2027-02-15 | 2027-02-15 |  |  | 1d | Rakuten | Rollout | [5 empty] | Consumer | Cluster 4 deployment (from Mainz Lab for Tech Pilot) |  |  | SE&I: OSS & Orchestration |  |  | 2027-02-15 | 2027-02-15 | 0
MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' | 2027-02-16 | 2027-02-16 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 277 | MC5.1.2.1.1 - External dependency on Mainz lab readiness' | Provider | Start date is from the time Lab is ready. End date: 4 weeks after start date is completion date | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-02-16 | 2027-02-16 | 0
MC5.1.2.1.3 - Deployment of RCP supporting applications in Mainz lab' | 2027-02-17 | 2027-02-17 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 278 | MC5.1.2.1.1 - External dependency on Mainz lab readiness' |  | Start date is from the time Lab is ready. End date: 4 weeks after start date is completion date | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-02-17 | 2027-02-17 | 0
MC5.1.2.1.4 - Deployment of RCP Uplift applications in Mainz lab' | 2027-02-18 | 2027-02-18 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 279 | MC5.1.2.1.1 - External dependency on Mainz lab readiness' |  | Start date is from the time Lab is ready. End date: 4 weeks after start date is completion date | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-02-18 | 2027-02-18 | 0
MC5.1.2.1.5 - External dependency on CDC 1 Readiness' | 2027-02-19 | 2027-02-22 | 2022-06-02 | 2022-06-03 | 2d | Rakuten | Rollout |  |  |  | 280 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2027-02-19 | 2027-02-22 | 0
MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production)' | 2027-02-23 | 2027-02-24 | 2022-06-06 | 2022-06-07 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 281 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | Start date is from the time CDC is ready. End date: 4 weeks after start date is completion date | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-02-23 | 2027-02-24 | 0
MC5.1.2.1.7 - Deployment of RCP supporting applications in CDC 1' (production)' | 2027-02-25 | 2027-02-26 | 2022-06-06 | 2022-06-07 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 282 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | Start date is from the time CDC is ready. End date: 4 weeks after start date is completion date | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-02-25 | 2027-02-26 | 0
MC5.1.2.1.8 - Deployment of RCP Uplift applications in CDC 1' (production)' | 2027-03-01 | 2027-03-02 | 2022-06-06 | 2022-06-07 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 283 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness' |  | Start date is from the time CDC is ready. End date: 4 weeks after start date is completion date | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-03-01 | 2027-03-02 | 0
MC5.1.2.1.9 - External dependency on CDC 2 Readiness' | 2027-03-03 | 2027-03-03 |  |  | 1d | Rakuten | Rollout |  |  |  | 284 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2027-03-03 | 2027-03-03 | 0
MC5.1.2.1.10 - Deployment of RCP Automator applications in CDC 2' (production)' | 2027-03-04 | 2027-03-04 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 285 | MC5.1.2.1.9 - External dependency on CDC 2 Readiness' |  | Start date is from the time CDC is ready. End date: 4 weeks after start date is completion date | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-03-04 | 2027-03-04 | 0
MC5.1.2.1.11 - Deployment of RCP supporting applications in CDC 2' (production)' | 2027-03-05 | 2027-03-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 286 | MC5.1.2.1.9 - External dependency on CDC 2 Readiness' |  | Start date is from the time CDC is ready. End date: 4 weeks after start date is completion date | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-03-05 | 2027-03-05 | 0
MC5.1.2.1.12 - Deployment of RCP Uplift applications in CDC 2' (production)' | 2027-03-08 | 2027-03-08 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 287 | MC5.1.2.1.9 - External dependency on CDC 2 Readiness' |  | Start date is from the time CDC is ready. End date: 4 weeks after start date is completion date | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-03-08 | 2027-03-08 | 0
MC5.1.2.2 - RAN surveillance capabilities' | 2027-03-09 | 2030-11-11 |  |  | 960d | [5 empty] | 288 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2027-03-09 | 2030-11-11 | 0
MC5.1.2.2.1 - 5G Surveillance' | 2027-03-09 | 2029-12-13 |  |  | 723d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2027-03-09 | 2029-12-13 | 0
MC5.1.2.2.1.1 - 5G SA - Retrieving integration requirements from vendors for Cloud Observability'' | 2027-03-09 | 2027-05-31 | 2022-01-07 | 2022-03-31 | 60d | Rakuten | SE&I: OSS & Orchestration |  | Not started | [5 empty] | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-03-09 | 2027-05-31 | 0
MC5.1.2.2.1.2 - External dependency on RAN 5G SA node availability in Mainz lab' | 2027-06-01 | 2022-04-01 | 2022-05-31 | 2022-06-01 | 2d | Rakuten | Rollout |  |  |  | 291 | Item belongs to external board, Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.2.1.3 - 5G SA - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2027-03-09 | 2027-03-10 | 2022-06-02 | 2022-06-03 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 292 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab, MC5.1.2.2.1.1 - 5G SA - Retrieving integration requirements from vendors for Cloud Observability', MC5.1.2.2.1.2 - External dependency on RAN 5G SA node availability in Mainz lab' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-03-09 | 2027-03-10 | 0
MC5.1.2.2.1.4 - 5G SA - Retrieving integration requirements from vendors for Inventory Management'' | 2027-03-11 | 2027-06-02 | 2022-01-07 | 2022-03-31 | 60d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 293 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-03-11 | 2027-06-02 | 0
MC5.1.2.2.1.5 - 5G SA - Development (development and development testing) of Inventory Management integration requirements'' | 2027-06-03 | 2027-06-04 | 2022-06-02 | 2022-06-03 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 294 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab, MC5.1.2.2.1.2 - External dependency on RAN 5G SA node availability in Mainz lab, MC5.1.2.2.1.4 - 5G SA - Retrieving integration requirements from vendors for Inventory Management'' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-06-03 | 2027-06-04 | 0
MC5.1.2.2.1.6 - 5G SA - Retrieving integration requirements from vendors for Fault Management'' | 2027-06-07 | 2027-09-22 | 2022-02-01 | 2022-05-19 | 78d | Rakuten | SE&I: OSS & Orchestration |  | In progress |  | 295 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-06-07 | 2027-09-22 | 0
MC5.1.2.2.1.7 - 5G SA - Development (development and development testing) of Fault Management integration requirements'' | 2027-09-23 | 2027-11-04 |  | 2022-06-30 | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 296 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | 'To be deployed in CDC1. Pre-requistie: Completion of integration activities as part of the Mainz Lab Technical Pilot plan'' | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-09-23 | 2027-11-04 | 0
MC5.1.2.2.1.8 - 5G SA - Retrieving integration requirements from vendors for Performance Management'' | 2027-11-05 | 2028-02-22 | 2022-02-01 | 2022-05-19 | 78d | Rakuten | SE&I: OSS & Orchestration |  | In progress |  | 297 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-11-05 | 2028-02-22 | 0
MC5.1.2.2.1.9 - 5G SA - Development (development and development testing) of Performance Management integration requirements'' | 2028-02-23 | 2028-02-24 | 2022-06-06 | 2022-06-07 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 298 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab, MC5.1.2.2.1.2 - External dependency on RAN 5G SA node availability in Mainz lab, MC5.1.2.2.1.3 - 5G SA - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox), MC5.1.2.2.1.5 - 5G SA - Development (development and development testing) of Inventory Management integration requirements', MC5.1.2.2.1.8 - 5G SA - Retrieving integration requirements from vendors for Performance Management'' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2028-02-23 | 2028-02-24 | 0
MC5.1.2.2.1.11 - RAN 5G SA nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2028-02-25 | 2028-02-28 | 2022-07-01 | 2022-07-04 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 299 | MC5.1.2.2.1.1 - 5G SA - Retrieving integration requirements from vendors for Cloud Observability', MC5.1.2.2.1.2 - External dependency on RAN 5G SA node availability in Mainz lab, MC5.1.2.2.1.3 - 5G SA - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox), MC5.1.2.2.1.4 - 5G SA - Retrieving integration requirements from vendors for Inventory Management', MC5.1.2.2.1.5 - 5G SA - Development (development and development testing) of Inventory Management integration requirements', MC5.1.2.2.1.6 - 5G SA - Retrieving integration requirements from vendors for Fault Management', MC5.1.2.2.1.7 - 5G SA - Development (development and development testing) of Fault Management integration requirements', MC5.1.2.2.1.8 - 5G SA - Retrieving integration requirements from vendors for Performance Management', MC5.1.2.2.1.9 - 5G SA - Development (development and development testing) of Performance Management integration requirements', MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' | Provider |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2028-02-25 | 2028-02-28 | 0
MC5.1.2.2.1.12 - External dependency on QA E2E testing' | 2028-02-29 | 2028-02-29 |  |  | 1d | Rakuten | E2E QA |  |  |  | 300 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2028-02-29 | 2028-02-29 | 0
MC5.1.2.2.1.13 - RAN 5G SA nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2028-03-01 | 2028-03-02 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 301 | MC5.1.2.2.1.12 - External dependency on QA E2E testing, MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production)' | Provider | Start date after QA testing completion. End date: 3 Weeks Afte QA testing Completion date | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2028-03-01 | 2028-03-02 | 0
MC5.1.2.2.1.14 - 5G NSA - Retrieving integration requirements from vendors for Cloud Observability'' | 2028-03-03 | 2028-10-03 | 2021-09-01 | 2022-03-31 | 153d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 302 |  |  |  | No | Tech Pilot | SE&I: OSS & Orchestration | No |  | 2028-03-03 | 2028-10-03 | 0
MC5.1.2.2.1.15 - External dependency on RAN 5G NSA node availability in Mainz lab' | 2028-10-04 | 2022-04-01 | 2022-02-16 | 2022-02-17 | 2d | Rakuten | Rollout |  |  |  | 303 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.2.1.16 - 5G NSA - Development (development and development testing) of Cloud Observability integration requirements'' | 2027-03-09 | 2027-03-10 | 2022-04-01 | 2022-04-04 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 304 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab, MC5.1.2.2.1.14 - 5G NSA - Retrieving integration requirements from vendors for Cloud Observability', MC5.1.2.2.1.15 - External dependency on RAN 5G NSA node availability in Mainz lab' |  |  | No | Tech Pilot | SE&I: OSS & Orchestration | No |  | 2027-03-09 | 2027-03-10 | 0
MC5.1.2.2.1.17 - 5G NSA - Retrieving integration requirements from vendors for Inventory Management'' | 2027-03-11 | 2027-10-11 | 2021-09-01 | 2022-03-31 | 153d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 305 |  |  |  | No | Tech Pilot | SE&I: OSS & Orchestration | No |  | 2027-03-11 | 2027-10-11 | 0
MC5.1.2.2.1.18 - 5G NSA - Development (development and development testing) of Inventory Management integration requirements'' | 2027-10-12 | 2027-10-13 | 2022-04-01 | 2022-04-04 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 306 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab, MC5.1.2.2.1.17 - 5G NSA - Retrieving integration requirements from vendors for Inventory Management', MC5.1.2.2.1.15 - External dependency on RAN 5G NSA node availability in Mainz lab' |  |  | No | Tech Pilot | SE&I: OSS & Orchestration | No |  | 2027-10-12 | 2027-10-13 | 0
MC5.1.2.2.1.19 - 5G NSA - Retrieving integration requirements from vendors for Fault Management'' | 2027-10-14 | 2028-07-03 | 2021-09-01 | 2022-05-19 | 188d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 307 |  |  | 'To be deployed in CDC1. Pre-requistie: Completion of integration activities as part of the Mainz Lab Technical Pilot plan'' | No | Tech Pilot | SE&I: OSS & Orchestration | No |  | 2027-10-14 | 2028-07-03 | 0
MC5.1.2.2.1.20 - 5G NSA - Development (development and development testing) of Fault Management integration requirements'' | 2028-07-04 | 2028-08-15 |  | 2022-06-30 | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 308 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  |  | No | Tech Pilot | SE&I: OSS & Orchestration | No |  | 2028-07-04 | 2028-08-15 | 0
MC5.1.2.2.1.21 - 5G NSA - Retrieving integration requirements from vendors for Performance Management'' | 2028-08-16 | 2029-05-04 | 2021-09-01 | 2022-05-19 | 188d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 309 |  |  |  | No | Tech Pilot | SE&I: OSS & Orchestration | No |  | 2028-08-16 | 2029-05-04 | 0
MC5.1.2.2.1.22 - 5G NSA - Development (development and development testing) of Performance Management integration requirements'' | 2029-05-07 | 2029-12-06 | 2021-11-30 | 2022-06-30 | 154d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 310 |  |  |  | No | Tech Pilot | SE&I: OSS & Orchestration | No |  | 2029-05-07 | 2029-12-06 | 0
MC5.1.2.2.1.23 - RAN 5G NSA nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2029-12-07 | 2029-12-10 | 2022-07-01 | 2022-07-04 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 311 | MC5.1.2.2.1.14 - 5G NSA - Retrieving integration requirements from vendors for Cloud Observability', MC5.1.2.2.1.22 - 5G NSA - Development (development and development testing) of Performance Management integration requirements', MC5.1.2.2.1.15 - External dependency on RAN 5G NSA node availability in Mainz lab, MC5.1.2.2.1.16 - 5G NSA - Development (development and development testing) of Cloud Observability integration requirements', MC5.1.2.2.1.17 - 5G NSA - Retrieving integration requirements from vendors for Inventory Management', MC5.1.2.2.1.18 - 5G NSA - Development (development and development testing) of Inventory Management integration requirements', MC5.1.2.2.1.19 - 5G NSA - Retrieving integration requirements from vendors for Fault Management', MC5.1.2.2.1.20 - 5G NSA - Development (development and development testing) of Fault Management integration requirements', MC5.1.2.2.1.21 - 5G NSA - Retrieving integration requirements from vendors for Performance Management'' |  |  | Yes | Tech Pilot | SE&I: OSS & Orchestration | No |  | 2029-12-07 | 2029-12-10 | 0
MC5.1.2.2.1.24 - External dependency on QA E2E testing' | 2029-12-11 | 2029-12-11 |  |  | 1d | Rakuten | E2E QA |  |  |  | 312 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2029-12-11 | 2029-12-11 | 0
MC5.1.2.2.1.25 - RAN 5G NSA nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2029-12-12 | 2029-12-13 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 313 | MC5.1.2.2.1.24 - External dependency on QA E2E testing, MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production)' | Provider | Start date after QA testing completion. End date: 3 Weeks Afte QA testing Completion date | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2029-12-12 | 2029-12-13 | 0
MC5.1.2.2.2 - 4G Surveillance' | 2029-12-14 | 2030-11-11 |  |  | 237d | [5 empty] | 314 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2029-12-14 | 2030-11-11 | 0
MC5.1.2.2.2.1 - External dependencies on RAN 4G EMS availability' | 2029-12-14 | 2029-12-17 | 2022-02-16 | 2022-02-17 | 2d | [7 empty] | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2029-12-14 | 2029-12-17 | 0
MC5.1.2.2.2.2 - 4G monitoring with EMS - Retrieving integration requirements from vendors for Inventory Management'' | 2029-12-18 | 2030-03-18 | 2022-02-18 | 2022-05-19 | 65d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 316 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.2.2.1 - External dependencies on RAN 4G EMS availability' |  |  | No | Tech Pilot | SE&I: OSS & Orchestration | No |  | 2029-12-18 | 2030-03-18 | 0
MC5.1.2.2.2.3 - External dependency on RAN 4G node availability in Mainz lab' | 2030-03-19 | 2030-03-20 | 2022-02-16 | 2022-02-17 | 2d | Rakuten | Rollout |  |  |  | 317 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2030-03-19 | 2030-03-20 | 0
MC5.1.2.2.2.4 - 4G monitoring with EMS - Development (development and development testing) of Inventory Management integration requirements'' | 2030-03-21 | 2030-03-22 | 2022-02-18 | 2022-02-21 | 2d | Rakuten | SE&I: OSS & Orchestration |  | In progress |  | 318 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.2.2.1 - External dependencies on RAN 4G EMS availability, MC5.1.2.2.2.3 - External dependency on RAN 4G node availability in Mainz lab' |  |  | No | Tech Pilot | SE&I: OSS & Orchestration | No |  | 2030-03-21 | 2030-03-22 | 0
MC5.1.2.2.2.5 - 4G monitoring with EMS - Retrieving integration requirements from vendors for Fault Management'' | 2030-03-25 | 2030-06-21 | 2021-09-01 | 2021-11-30 | 65d | Rakuten | SE&I: OSS & Orchestration |  | In progress |  | 319 |  |  |  | No | Tech Pilot | SE&I: OSS & Orchestration | No |  | 2030-03-25 | 2030-06-21 | 0
MC5.1.2.2.2.6 - 4G monitoring with EMS - Development (development and development testing) of Fault Management integration requirements'' | 2030-06-24 | 2030-06-25 | 2022-02-18 | 2022-02-21 | 2d | Rakuten | SE&I: OSS & Orchestration |  | In progress |  | 320 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.2.2.1 - External dependencies on RAN 4G EMS availability, MC5.1.2.2.2.3 - External dependency on RAN 4G node availability in Mainz lab, MC5.1.2.2.2.5 - 4G monitoring with EMS - Retrieving integration requirements from vendors for Fault Management'' |  |  | No | Tech Pilot | SE&I: OSS & Orchestration | No |  | 2030-06-24 | 2030-06-25 | 0
MC5.1.2.2.2.7 - 4G monitoring with EMS - Retrieving integration requirements from vendors for Performance Management'' | 2030-06-26 | 2030-09-24 | 2021-09-01 | 2021-11-30 | 65d | Rakuten | SE&I: OSS & Orchestration |  | In progress |  | 321 |  |  |  | No | Tech Pilot | SE&I: OSS & Orchestration | No |  | 2030-06-26 | 2030-09-24 | 0
MC5.1.2.2.2.8 - 4G monitoring with EMS - Development (development and development testing) of Performance Management integration requirements'' | 2030-09-25 | 2030-11-04 | 2022-02-18 | 2022-03-30 | 29d | Rakuten | SE&I: OSS & Orchestration |  | In progress |  | 322 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.2.2.1 - External dependencies on RAN 4G EMS availability, MC5.1.2.2.2.3 - External dependency on RAN 4G node availability in Mainz lab, MC5.1.2.2.2.7 - 4G monitoring with EMS - Retrieving integration requirements from vendors for Performance Management'' |  |  | No | Tech Pilot | SE&I: OSS & Orchestration | No |  | 2030-09-25 | 2030-11-04 | 0
MC5.1.2.2.2.9 - RAN 4G nodes with EMS surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2030-11-05 | 2030-11-06 | 2022-05-20 | 2022-05-23 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 323 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  |  | Yes | Tech Pilot | SE&I: OSS & Orchestration | No |  | 2030-11-05 | 2030-11-06 | 0
MC5.1.2.2.2.10 - External dependency on QA E2E testing' | 2030-11-07 | 2030-11-07 |  |  | 1d | Rakuten | E2E QA |  |  |  | 324 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2030-11-07 | 2030-11-07 | 0
MC5.1.2.2.2.11 - RAN 4G with EMS nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2030-11-08 | 2030-11-11 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 325 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production), MC5.1.2.2.2.10 - External dependency on QA E2E testing' | Provider | Start date after QA testing completion. End date: 3 Weeks Afte QA testing Completion date | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2030-11-08 | 2030-11-11 | 0
MC5.1.2.3 - Cloud (Bare Metal Server) surveillance' | 2027-02-15 | 2027-11-11 |  |  | 194d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2027-02-15 | 2027-11-11 | 0
MC5.1.2.3.1 - Bare Metal Server - Retrieving integration requirements from vendors for Cloud Observability'' | 2027-02-15 | 2027-05-07 | 2022-01-07 | 2022-03-31 | 60d | Rakuten | SE&I: OSS & Orchestration |  | In progress |  |  |  | Consumer |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-02-15 | 2027-05-07 | 0
MC5.1.2.3.2 - External dependency on Bare Metal servers availability in Mainz lab' | 2027-05-10 | 2022-03-31 | 2022-05-24 | 2022-05-25 | 2d | Rakuten | Rollout |  |  |  | 328 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.3.3 - Bare Metal Server - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2027-02-15 | 2027-02-16 | 2022-05-26 | 2022-05-27 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 329 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.3.1 - Bare Metal Server - Retrieving integration requirements from vendors for Cloud Observability', MC5.1.2.3.2 - External dependency on Bare Metal servers availability in Mainz lab' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-02-15 | 2027-02-16 | 0
MC5.1.2.3.4 - Bare Metal Server - Retrieving integration requirements from vendors for Inventory Management'' | 2027-02-17 | 2027-05-11 | 2022-01-07 | 2022-03-31 | 60d | Rakuten | SE&I: OSS & Orchestration |  | In progress |  | 330 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-02-17 | 2027-05-11 | 0
MC5.1.2.3.5 - Bare Metal Server - Development (development and development testing) of Inventory Management integration requirements'' | 2027-05-12 | 2027-08-10 | 2022-05-30 | 2022-08-26 | 65d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 331 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.3.3 - Bare Metal Server - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox), MC5.1.2.3.2 - External dependency on Bare Metal servers availability in Mainz lab' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-05-12 | 2027-08-10 | 0
MC5.1.2.3.6 - Bare Metal Server - Retrieving integration requirements from vendors for Fault Management'' | 2027-08-11 | 2027-11-02 | 2022-01-07 | 2022-03-31 | 60d | Rakuten | SE&I: OSS & Orchestration |  | In progress |  | 332 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-08-11 | 2027-11-02 | 0
MC5.1.2.3.7 - Bare Metal Server - Development (development and development testing) of Fault Management integration requirements'' | 2027-11-03 | 2027-11-04 | 2022-08-29 | 2022-08-30 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 333 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.3.2 - External dependency on Bare Metal servers availability in Mainz lab, MC5.1.2.3.3 - Bare Metal Server - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox), MC5.1.2.3.5 - Bare Metal Server - Development (development and development testing) of Inventory Management integration requirements', MC5.1.2.3.6 - Bare Metal Server - Retrieving integration requirements from vendors for Fault Management'' |  | 'To be deployed in CDC1. Pre-requistie: Completion of integration activities as part of the Mainz Lab Technical Pilot plan'' | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-11-03 | 2027-11-04 | 0
MC5.1.2.3.8 - surveillance integration for Fault and Performance management systems for all Baremetal nodes in Mainz Lab''' | 2027-11-05 | 2027-11-08 | 2022-08-31 | 2022-09-01 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 334 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab, MC5.1.2.3.1 - Bare Metal Server - Retrieving integration requirements from vendors for Cloud Observability', MC5.1.2.3.2 - External dependency on Bare Metal servers availability in Mainz lab, MC5.1.2.3.3 - Bare Metal Server - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox), MC5.1.2.3.4 - Bare Metal Server - Retrieving integration requirements from vendors for Inventory Management', MC5.1.2.3.5 - Bare Metal Server - Development (development and development testing) of Inventory Management integration requirements', MC5.1.2.3.6 - Bare Metal Server - Retrieving integration requirements from vendors for Fault Management', MC5.1.2.3.7 - Bare Metal Server - Development (development and development testing) of Fault Management integration requirements'' |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2027-11-05 | 2027-11-08 | 0
MC5.1.2.3.9 - External dependency on QA E2E testing' | 2027-11-09 | 2027-11-09 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 335 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2027-11-09 | 2027-11-09 | 0
MC5.1.2.3.10 - surveillance Deployment for Fault and Performance management systems for all Baremetal nodes in production'' | 2027-11-10 | 2027-11-11 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 336 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production)' |  | Start date after QA testing completion. End date: 3 Weeks Afte QA testing Completion date | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2027-11-10 | 2027-11-11 | 0
MC5.1.2.4 - Transport surveillance' | 2027-02-15 | 2034-01-31 |  |  | 1817d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2027-02-15 | 2034-01-31 | 0
MC5.1.2.4.1 - Dasan STU - Retrieving integration requirements from vendors for Cloud Observability'' | 2027-02-15 | 2027-05-17 | 2021-11-01 | 2022-01-31 | 66d | Rakuten | SE&I: OSS & Orchestration |  | In progress | [5 empty] | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-02-15 | 2027-05-17 | 0
MC5.1.2.4.2 - External dependency on DASAN STU Nodes availability in Mainz lab' | 2027-05-18 | 2027-05-18 |  |  | 1d | Rakuten | Rollout |  |  |  | 339 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2027-05-18 | 2027-05-18 | 0
MC5.1.2.4.3 - Dasan STU - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2027-05-19 | 2027-06-30 | 2022-02-01 | 2022-03-15 | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 340 | MC5.1.2.4.1 - Dasan STU - Retrieving integration requirements from vendors for Cloud Observability', MC5.1.2.4.2 - External dependency on DASAN STU Nodes availability in Mainz lab, MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-05-19 | 2027-06-30 | 0
MC5.1.2.4.4 - Dasan STU - Retrieving integration requirements from vendors for Inventory Management'' | 2027-07-01 | 2027-09-30 | 2021-11-01 | 2022-01-31 | 66d | Rakuten | SE&I: OSS & Orchestration |  | In progress |  | 341 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-07-01 | 2027-09-30 | 0
MC5.1.2.4.5 - Dasan STU - Development (development and development testing) of Inventory Management integration requirements'' | 2027-10-01 | 2027-11-12 | 2022-02-01 | 2022-03-15 | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 342 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-10-01 | 2027-11-12 | 0
MC5.1.2.4.6 - Dasan STU - Retrieving integration requirements from vendors for Fault Management'' | 2027-11-15 | 2028-03-28 | 2021-11-01 | 2022-03-15 | 97d | Rakuten | SE&I: OSS & Orchestration |  | In progress |  | 343 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-11-15 | 2028-03-28 | 0
MC5.1.2.4.7 - Dasan STU - Development (development and development testing) of Fault Management integration requirements'' | 2028-03-29 | 2028-05-12 | 2022-03-16 | 2022-04-30 | 33d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 344 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2028-03-29 | 2028-05-12 | 0
MC5.1.2.4.8 - Dasan STU - Retrieving integration requirements from vendors for Performance Management'' | 2028-05-15 | 2028-09-26 | 2021-11-01 | 2022-03-15 | 97d | Rakuten | SE&I: OSS & Orchestration |  | In progress |  | 345 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2028-05-15 | 2028-09-26 | 0
MC5.1.2.4.9 - Dasan STU - Development (development and development testing) of Performance Management integration requirements'' | 2028-09-27 | 2028-11-10 | 2022-03-16 | 2022-04-30 | 33d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 346 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2028-09-27 | 2028-11-10 | 0
MC5.1.2.4.10 - Dasan STU nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2028-11-13 | 2028-12-12 | 2022-05-01 | 2022-05-31 | 22d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 347 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2028-11-13 | 2028-12-12 | 0
MC5.1.2.4.11 - External dependency on QA E2E testing' | 2028-12-13 | 2028-12-13 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 348 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2028-12-13 | 2028-12-13 | 0
MC5.1.2.4.12 - Dasan STU nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2028-12-14 | 2028-12-14 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 349 |  |  | Start date after QA testing completion. End date: 3 Weeks Afte QA testing Completion date | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2028-12-14 | 2028-12-14 | 0
MC5.1.2.4.13 - Cisco TOR SW - Retrieving integration requirements from vendors for Cloud Observability'' | 2028-12-15 | 2029-03-14 | 2022-02-01 | 2022-04-30 | 64d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 350 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2028-12-15 | 2029-03-14 | 0
MC5.1.2.4.14 - External dependency on Cisco TOR SW Nodes availability in Mainz lab' | 2029-03-15 | 2029-03-15 |  |  | 1d | Rakuten | Rollout |  |  |  | 351 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2029-03-15 | 2029-03-15 | 0
MC5.1.2.4.15 - Cisco TOR SW - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2029-03-16 | 2029-04-16 | 2022-05-01 | 2022-05-31 | 22d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 352 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2029-03-16 | 2029-04-16 | 0
MC5.1.2.4.16 - Cisco TOR SW - Retrieving integration requirements from vendors for Inventory Management'' | 2029-04-17 | 2029-07-27 | 2022-02-01 | 2022-05-15 | 74d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 353 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2029-04-17 | 2029-07-27 | 0
MC5.1.2.4.17 - Cisco TOR SW - Development (development and development testing) of Inventory Management integration requirements'' | 2029-07-30 | 2029-08-28 | 2022-05-01 | 2022-05-31 | 22d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 354 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2029-07-30 | 2029-08-28 | 0
MC5.1.2.4.18 - Cisco TOR SW - Retrieving integration requirements from vendors for Fault Management'' | 2029-08-29 | 2029-12-26 | 2022-02-01 | 2022-05-31 | 86d | Rakuten | SE&I: OSS & Orchestration |  | In progress |  | 355 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2029-08-29 | 2029-12-26 | 0
MC5.1.2.4.19 - Cisco TOR SW - Development (development and development testing) of Fault Management integration requirements'' | 2029-12-27 | 2030-02-11 | 2022-06-01 | 2022-07-15 | 33d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 356 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2029-12-27 | 2030-02-11 | 0
MC5.1.2.4.20 - Cisco TOR SW - Retrieving integration requirements from vendors for Performance Management'' | 2030-02-12 | 2030-06-11 | 2022-02-01 | 2022-05-31 | 86d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 357 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2030-02-12 | 2030-06-11 | 0
MC5.1.2.4.21 - Cisco TOR SW - Development (development and development testing) of Performance Management integration requirements'' | 2030-06-12 | 2030-07-26 | 2022-06-01 | 2022-07-15 | 33d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 358 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2030-06-12 | 2030-07-26 | 0
MC5.1.2.4.22 - Cisco TOR SW nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2030-07-29 | 2030-08-27 | 2022-07-16 | 2022-08-16 | 22d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 359 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2030-07-29 | 2030-08-27 | 0
MC5.1.2.4.23 - External dependency on QA E2E testing' | 2030-08-28 | 2030-08-28 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 360 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2030-08-28 | 2030-08-28 | 0
MC5.1.2.4.24 - Cisco TOR SW nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2030-08-29 | 2030-08-30 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 361 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production), MC5.1.2.4.23 - External dependency on QA E2E testing' |  | Start date after QA testing completion. End date: 3 Weeks Afte QA testing Completion date | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2030-08-29 | 2030-08-30 | 0
MC5.1.2.4.25 - Cisco OOB Routers/Switches - Retrieving integration requirements from vendors for Cloud Observability'' | 2030-09-02 | 2030-11-28 | 2022-02-01 | 2022-04-30 | 64d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 362 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2030-09-02 | 2030-11-28 | 0
MC5.1.2.4.26 - External dependency on Cisco OOB Routers/Switches Nodes availability in Mainz lab' | 2030-11-29 | 2030-11-29 |  |  | 1d | Rakuten | Rollout |  |  |  | 363 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2030-11-29 | 2030-11-29 | 0
MC5.1.2.4.27 - Cisco OOB Routers/Switches - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2030-12-02 | 2030-12-31 | 2022-05-02 | 2022-05-31 | 22d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 364 | MC5.1.2.4.25 - Cisco OOB Routers/Switches - Retrieving integration requirements from vendors for Cloud Observability', MC5.1.2.4.26 - External dependency on Cisco OOB Routers/Switches Nodes availability in Mainz lab, MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2030-12-02 | 2030-12-31 | 0
MC5.1.2.4.28 - Cisco OOB Routers/Switches - Retrieving integration requirements from vendors for Inventory Management'' | 2031-01-01 | 2031-04-14 | 2022-02-01 | 2022-05-15 | 74d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 365 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2031-01-01 | 2031-04-14 | 0
MC5.1.2.4.29 - Cisco OOB Routers/Switches - Development (development and development testing) of Inventory Management integration requirements'' | 2031-04-15 | 2031-05-14 | 2022-06-01 | 2022-06-30 | 22d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 366 | MC5.1.2.4.26 - External dependency on Cisco OOB Routers/Switches Nodes availability in Mainz lab, MC5.1.2.4.27 - Cisco OOB Routers/Switches - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox), MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2031-04-15 | 2031-05-14 | 0
MC5.1.2.4.30 - Cisco OOB Routers/Switches - Retrieving integration requirements from vendors for Fault Management'' | 2031-05-15 | 2031-09-11 | 2022-02-01 | 2022-05-31 | 86d | Rakuten | SE&I: OSS & Orchestration |  | In progress |  | 367 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2031-05-15 | 2031-09-11 | 0
MC5.1.2.4.31 - Cisco OOB Routers/Switches - Development (development and development testing) of Fault Management integration requirements'' | 2031-09-12 | 2031-10-28 | 2022-06-01 | 2022-07-15 | 33d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 368 | MC5.1.2.4.26 - External dependency on Cisco OOB Routers/Switches Nodes availability in Mainz lab, MC5.1.2.4.30 - Cisco OOB Routers/Switches - Retrieving integration requirements from vendors for Fault Management', MC5.1.2.4.3 - Dasan STU - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox), MC5.1.2.4.5 - Dasan STU - Development (development and development testing) of Inventory Management integration requirements', MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2031-09-12 | 2031-10-28 | 0
MC5.1.2.4.32 - Cisco OOB Routers/Switches - Retrieving integration requirements from vendors for Performance Management'' | 2031-10-29 | 2032-02-25 | 2022-02-01 | 2022-05-31 | 86d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 369 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2031-10-29 | 2032-02-25 | 0
MC5.1.2.4.33 - Cisco OOB Routers/Switches - Development (development and development testing) of Performance Management integration requirements'' | 2032-02-26 | 2032-04-12 | 2022-08-01 | 2022-09-14 | 33d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 370 | MC5.1.2.4.26 - External dependency on Cisco OOB Routers/Switches Nodes availability in Mainz lab, MC5.1.2.4.43 - Cisco Leaf SW - Development (development and development testing) of Fault Management integration requirements', MC5.1.2.4.31 - Cisco OOB Routers/Switches - Development (development and development testing) of Fault Management integration requirements', MC5.1.2.4.29 - Cisco OOB Routers/Switches - Development (development and development testing) of Inventory Management integration requirements', MC5.1.2.1.1 - External dependency on Mainz lab readiness' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2032-02-26 | 2032-04-12 | 0
MC5.1.2.4.34 - Cisco OOB Routers/Switches nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2032-04-13 | 2032-05-12 | 2022-09-15 | 2022-10-14 | 22d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 371 | MC5.1.2.4.25 - Cisco OOB Routers/Switches - Retrieving integration requirements from vendors for Cloud Observability', MC5.1.2.4.26 - External dependency on Cisco OOB Routers/Switches Nodes availability in Mainz lab, MC5.1.2.4.27 - Cisco OOB Routers/Switches - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox), MC5.1.2.4.28 - Cisco OOB Routers/Switches - Retrieving integration requirements from vendors for Inventory Management', MC5.1.2.4.29 - Cisco OOB Routers/Switches - Development (development and development testing) of Inventory Management integration requirements', MC5.1.2.4.30 - Cisco OOB Routers/Switches - Retrieving integration requirements from vendors for Fault Management', MC5.1.2.4.31 - Cisco OOB Routers/Switches - Development (development and development testing) of Fault Management integration requirements', MC5.1.2.4.32 - Cisco OOB Routers/Switches - Retrieving integration requirements from vendors for Performance Management', MC5.1.2.4.33 - Cisco OOB Routers/Switches - Development (development and development testing) of Performance Management integration requirements', MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2032-04-13 | 2032-05-12 | 0
MC5.1.2.4.35 - External dependency on QA E2E testing' | 2032-05-13 | 2032-05-13 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 372 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2032-05-13 | 2032-05-13 | 0
MC5.1.2.4.36 - Cisco OOB Routers/Switches nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2032-05-14 | 2032-05-17 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 373 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production), MC5.1.2.4.35 - External dependency on QA E2E testing' |  | Start date after QA testing completion. End date: 3 Weeks Afte QA testing Completion date | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2032-05-14 | 2032-05-17 | 0
MC5.1.2.4.37 - Cisco Leaf SW - Retrieving integration requirements from vendors for Cloud Observability'' | 2032-05-18 | 2032-08-13 | 2022-02-01 | 2022-04-30 | 64d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 374 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2032-05-18 | 2032-08-13 | 0
MC5.1.2.4.38 - External dependency on Cisco Leaf SW Nodes availability in Mainz lab' | 2032-08-16 | 2032-08-16 |  |  | 1d | Rakuten | Rollout |  |  |  | 375 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2032-08-16 | 2032-08-16 | 0
MC5.1.2.4.39 - Cisco Leaf SW - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2032-08-17 | 2032-09-15 | 2022-05-02 | 2022-05-31 | 22d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 376 | MC5.1.2.4.37 - Cisco Leaf SW - Retrieving integration requirements from vendors for Cloud Observability', MC5.1.2.4.38 - External dependency on Cisco Leaf SW Nodes availability in Mainz lab, MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2032-08-17 | 2032-09-15 | 0
MC5.1.2.4.40 - Cisco Leaf SW - Retrieving integration requirements from vendors for Inventory Management'' | 2032-09-16 | 2032-12-28 | 2022-02-01 | 2022-05-15 | 74d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 377 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2032-09-16 | 2032-12-28 | 0
MC5.1.2.4.41 - Cisco Leaf SW - Development (development and development testing) of Inventory Management integration requirements'' | 2032-12-29 | 2033-01-27 | 2022-05-16 | 2022-06-14 | 22d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 378 | MC5.1.2.4.38 - External dependency on Cisco Leaf SW Nodes availability in Mainz lab, MC5.1.2.4.40 - Cisco Leaf SW - Retrieving integration requirements from vendors for Inventory Management', MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2032-12-29 | 2033-01-27 | 0
MC5.1.2.4.42 - Cisco Leaf SW - Retrieving integration requirements from vendors for Fault Management'' | 2033-01-28 | 2033-05-27 | 2022-02-01 | 2022-05-31 | 86d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 379 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2033-01-28 | 2033-05-27 | 0
MC5.1.2.4.43 - Cisco Leaf SW - Development (development and development testing) of Fault Management integration requirements'' | 2033-05-30 | 2033-07-13 | 2022-06-15 | 2022-07-29 | 33d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 380 | MC5.1.2.4.38 - External dependency on Cisco Leaf SW Nodes availability in Mainz lab, MC5.1.2.4.42 - Cisco Leaf SW - Retrieving integration requirements from vendors for Fault Management', MC5.1.2.4.41 - Cisco Leaf SW - Development (development and development testing) of Inventory Management integration requirements', MC5.1.2.4.39 - Cisco Leaf SW - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox), MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2033-05-30 | 2033-07-13 | 0
MC5.1.2.4.44 - Cisco Leaf SW - Retrieving integration requirements from vendors for Performance Management'' | 2033-07-14 | 2033-11-10 | 2022-02-01 | 2022-05-31 | 86d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 381 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2033-07-14 | 2033-11-10 | 0
MC5.1.2.4.45 - Cisco Leaf SW - Development (development and development testing) of Performance Management integration requirements'' | 2033-11-11 | 2033-12-27 | 2022-08-01 | 2022-09-14 | 33d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 382 | MC5.1.2.4.38 - External dependency on Cisco Leaf SW Nodes availability in Mainz lab, MC5.1.2.4.44 - Cisco Leaf SW - Retrieving integration requirements from vendors for Performance Management', MC5.1.2.4.41 - Cisco Leaf SW - Development (development and development testing) of Inventory Management integration requirements', MC5.1.2.4.43 - Cisco Leaf SW - Development (development and development testing) of Fault Management integration requirements', MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2033-11-11 | 2033-12-27 | 0
MC5.1.2.4.46 - Cisco Leaf SW nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2033-12-28 | 2034-01-26 | 2022-09-15 | 2022-10-14 | 22d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 383 | MC5.1.2.4.37 - Cisco Leaf SW - Retrieving integration requirements from vendors for Cloud Observability', MC5.1.2.4.38 - External dependency on Cisco Leaf SW Nodes availability in Mainz lab, MC5.1.2.4.39 - Cisco Leaf SW - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox), MC5.1.2.4.40 - Cisco Leaf SW - Retrieving integration requirements from vendors for Inventory Management', MC5.1.2.4.41 - Cisco Leaf SW - Development (development and development testing) of Inventory Management integration requirements', MC5.1.2.4.42 - Cisco Leaf SW - Retrieving integration requirements from vendors for Fault Management', MC5.1.2.4.43 - Cisco Leaf SW - Development (development and development testing) of Fault Management integration requirements', MC5.1.2.4.44 - Cisco Leaf SW - Retrieving integration requirements from vendors for Performance Management', MC5.1.2.4.45 - Cisco Leaf SW - Development (development and development testing) of Performance Management integration requirements', MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2033-12-28 | 2034-01-26 | 0
MC5.1.2.4.47 - External dependency on QA E2E testing' | 2034-01-27 | 2034-01-27 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 384 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2034-01-27 | 2034-01-27 | 0
MC5.1.2.4.48 - Cisco Leaf SW nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2034-01-30 | 2034-01-31 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 385 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production), MC5.1.2.4.47 - External dependency on QA E2E testing' |  | Start date after QA testing completion. End date: 3 Weeks Afte QA testing Completion date | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2034-01-30 | 2034-01-31 | 0
MC5.1.2.5 - Security surveillance' | 2027-02-15 | 2066-10-15 |  |  | 10350d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2027-02-15 | 2066-10-15 | 0
MC5.1.2.5.1 - IAM Nodes' | 2027-02-15 | 2036-02-22 |  |  | 2355d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2027-02-15 | 2036-02-22 | 0
MC5.1.2.5.1.1 - RedHat IPA - Retrieving integration requirements from vendors for Cloud Observability'' | 2027-02-15 | 2027-05-12 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  |  |  |  | Integration Priority 1 | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-02-15 | 2027-05-12 | 0
MC5.1.2.5.1.2 - External dependency on Nodes availability in Mainz lab' | 2027-05-13 | 2027-05-13 |  |  | 1d | Rakuten | Rollout |  |  |  | 389 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2027-05-13 | 2027-05-13 | 0
MC5.1.2.5.1.3 - RedHat IPA - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2027-05-14 | 2027-06-25 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 390 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 1 | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-05-14 | 2027-06-25 | 0
MC5.1.2.5.1.4 - RedHat IPA - Retrieving integration requirements from vendors for Inventory Management'' | 2027-06-28 | 2027-09-22 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 391 |  |  | Integration Priority 1 | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-06-28 | 2027-09-22 | 0
MC5.1.2.5.1.5 - RedHat IPA - Development (development and development testing) of Inventory Management integration requirements'' | 2027-09-23 | 2027-11-04 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 392 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 1 | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-09-23 | 2027-11-04 | 0
MC5.1.2.5.1.6 - RedHat IPA - Retrieving integration requirements from vendors for Fault Management'' | 2027-11-05 | 2028-03-15 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 393 |  |  | Integration Priority 1 | No | FWA | SE&I: OSS & Orchestration | No |  | 2027-11-05 | 2028-03-15 | 0
MC5.1.2.5.1.7 - RedHat IPA - Development (development and development testing) of Fault Management integration requirements'' | 2028-03-16 | 2028-05-02 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 394 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 1 | No | FWA | SE&I: OSS & Orchestration | No |  | 2028-03-16 | 2028-05-02 | 0
MC5.1.2.5.1.8 - RedHat IPA - Retrieving integration requirements from vendors for Performance Management'' | 2028-05-03 | 2028-09-11 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 395 |  |  | Integration Priority 1 | No | FWA | SE&I: OSS & Orchestration | No |  | 2028-05-03 | 2028-09-11 | 0
MC5.1.2.5.1.9 - RedHat IPA - Development (development and development testing) of Performance Management integration requirements'' | 2028-09-12 | 2028-10-27 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 396 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 1 | No | FWA | SE&I: OSS & Orchestration | No |  | 2028-09-12 | 2028-10-27 | 0
MC5.1.2.5.1.10 - RedHat IPA nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2028-10-30 | 2028-11-29 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 397 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 1 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2028-10-30 | 2028-11-29 | 0
MC5.1.2.5.1.11 - External dependency on QA E2E testing' | 2028-11-30 | 2028-11-30 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 398 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2028-11-30 | 2028-11-30 | 0
MC5.1.2.5.1.12 - RedHat IPA nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2028-12-01 | 2028-12-04 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 399 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production)' |  | Integration Priority 1 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2028-12-01 | 2028-12-04 | 0
MC5.1.2.5.1.13 - Cisco ISE - Retrieving integration requirements from vendors for Cloud Observability'' | 2028-12-05 | 2029-03-01 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 400 |  |  | Integration Priority 2 | No | FWA | SE&I: OSS & Orchestration | No |  | 2028-12-05 | 2029-03-01 | 0
MC5.1.2.5.1.14 - External dependency on Nodes availability in Mainz lab' | 2029-03-02 | 2029-03-02 | 2022-10-01 | 2022-10-02 | 1d | Rakuten | Rollout |  |  |  | 401 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2029-03-02 | 2029-03-02 | 0
MC5.1.2.5.1.15 - Cisco ISE - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2029-03-05 | 2029-04-16 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 402 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 2 | No | FWA | SE&I: OSS & Orchestration | No |  | 2029-03-05 | 2029-04-16 | 0
MC5.1.2.5.1.16 - Cisco ISE - Retrieving integration requirements from vendors for Inventory Management'' | 2029-04-17 | 2029-07-12 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 403 |  |  | Integration Priority 2 | No | FWA | SE&I: OSS & Orchestration | No |  | 2029-04-17 | 2029-07-12 | 0
MC5.1.2.5.1.17 - Cisco ISE - Development (development and development testing) of Inventory Management integration requirements'' | 2029-07-13 | 2029-08-24 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 404 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 2 | No | FWA | SE&I: OSS & Orchestration | No |  | 2029-07-13 | 2029-08-24 | 0
MC5.1.2.5.1.18 - Cisco ISE - Retrieving integration requirements from vendors for Fault Management'' | 2029-08-27 | 2030-01-03 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 405 |  |  | Integration Priority 2 | No | FWA | SE&I: OSS & Orchestration | No |  | 2029-08-27 | 2030-01-03 | 0
MC5.1.2.5.1.19 - Cisco ISE - Development (development and development testing) of Fault Management integration requirements'' | 2030-01-04 | 2030-02-20 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 406 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 2 | No | FWA | SE&I: OSS & Orchestration | No |  | 2030-01-04 | 2030-02-20 | 0
MC5.1.2.5.1.20 - Cisco ISE - Retrieving integration requirements from vendors for Performance Management'' | 2030-02-21 | 2030-07-02 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 407 |  |  | Integration Priority 2 | No | FWA | SE&I: OSS & Orchestration | No |  | 2030-02-21 | 2030-07-02 | 0
MC5.1.2.5.1.21 - Cisco ISE - Development (development and development testing) of Performance Management integration requirements'' | 2030-07-03 | 2030-08-19 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 408 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 2 | No | FWA | SE&I: OSS & Orchestration | No |  | 2030-07-03 | 2030-08-19 | 0
MC5.1.2.5.1.22 - Cisco ISE nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2030-08-20 | 2030-09-19 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 409 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 2 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2030-08-20 | 2030-09-19 | 0
MC5.1.2.5.1.23 - External dependency on QA E2E testing' | 2030-09-20 | 2030-09-20 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 410 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2030-09-20 | 2030-09-20 | 0
MC5.1.2.5.1.24 - Cisco ISE nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2030-09-23 | 2030-09-24 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 411 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production)' |  | Integration Priority 2 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2030-09-23 | 2030-09-24 | 0
MC5.1.2.5.1.25 - Microsoft AD - Retrieving integration requirements from vendors for Cloud Observability'' | 2030-09-25 | 2030-12-20 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 412 |  |  | Integration Priority 3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2030-09-25 | 2030-12-20 | 0
MC5.1.2.5.1.26 - External dependency on Nodes availability in Mainz lab' | 2030-12-23 | 2030-12-23 | 2022-10-01 | 2022-10-02 | 1d | Rakuten | Rollout |  |  |  | 413 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2030-12-23 | 2030-12-23 | 0
MC5.1.2.5.1.27 - Microsoft AD - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2030-12-24 | 2031-02-04 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 414 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2030-12-24 | 2031-02-04 | 0
MC5.1.2.5.1.28 - Microsoft AD - Retrieving integration requirements from vendors for Inventory Management'' | 2031-02-05 | 2031-05-02 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 415 |  |  | Integration Priority 3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2031-02-05 | 2031-05-02 | 0
MC5.1.2.5.1.29 - Microsoft AD - Development (development and development testing) of Inventory Management integration requirements'' | 2031-05-05 | 2031-06-16 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 416 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2031-05-05 | 2031-06-16 | 0
MC5.1.2.5.1.30 - Microsoft AD - Retrieving integration requirements from vendors for Fault Management'' | 2031-06-17 | 2031-10-24 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 417 |  |  | Integration Priority 3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2031-06-17 | 2031-10-24 | 0
MC5.1.2.5.1.31 - Microsoft AD - Development (development and development testing) of Fault Management integration requirements'' | 2031-10-27 | 2031-12-11 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 418 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2031-10-27 | 2031-12-11 | 0
MC5.1.2.5.1.32 - Microsoft AD - Retrieving integration requirements from vendors for Performance Management'' | 2031-12-12 | 2032-04-21 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 419 |  |  | Integration Priority 3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2031-12-12 | 2032-04-21 | 0
MC5.1.2.5.1.33 - Microsoft AD - Development (development and development testing) of Performance Management integration requirements'' | 2032-04-22 | 2032-06-08 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 420 |  |  | Integration Priority 3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2032-04-22 | 2032-06-08 | 0
MC5.1.2.5.1.34 - Microsoft AD nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2032-06-09 | 2032-07-09 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 421 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 3 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2032-06-09 | 2032-07-09 | 0
MC5.1.2.5.1.35 - External dependency on QA E2E testing' | 2032-07-12 | 2032-07-12 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 422 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2032-07-12 | 2032-07-12 | 0
MC5.1.2.5.1.36 - Microsoft AD nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2032-07-13 | 2032-07-14 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 423 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production)' |  | Integration Priority 3 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2032-07-13 | 2032-07-14 | 0
MC5.1.2.5.1.37 - Cisco ASAV - Retrieving integration requirements from vendors for Cloud Observability'' | 2032-07-15 | 2032-10-11 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 424 |  |  | Integration Priority 4 | No | FWA | SE&I: OSS & Orchestration | No |  | 2032-07-15 | 2032-10-11 | 0
MC5.1.2.5.1.38 - External dependency on Cisco ASAV Nodes availability in Mainz lab' | 2032-10-12 | 2032-10-12 |  |  | 1d | Rakuten | Rollout |  |  |  | 425 |  | Consumer | Integration Priority 4 |  | FWA | SE&I: OSS & Orchestration |  |  | 2032-10-12 | 2032-10-12 | 0
MC5.1.2.5.1.39 - Cisco ASAV - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2032-10-13 | 2032-11-24 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 426 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 4 | No | FWA | SE&I: OSS & Orchestration | No |  | 2032-10-13 | 2032-11-24 | 0
MC5.1.2.5.1.40 - Cisco ASAV - Retrieving integration requirements from vendors for Inventory Management'' | 2032-11-25 | 2033-02-21 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 427 |  |  | Integration Priority 4 | No | FWA | SE&I: OSS & Orchestration | No |  | 2032-11-25 | 2033-02-21 | 0
MC5.1.2.5.1.41 - Cisco ASAV - Development (development and development testing) of Inventory Management integration requirements'' | 2033-02-22 | 2033-04-05 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 428 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 4 | No | FWA | SE&I: OSS & Orchestration | No |  | 2033-02-22 | 2033-04-05 | 0
MC5.1.2.5.1.42 - Cisco ASAV - Retrieving integration requirements from vendors for Fault Management'' | 2033-04-06 | 2033-08-15 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 429 |  |  | Integration Priority 4 | No | FWA | SE&I: OSS & Orchestration | No |  | 2033-04-06 | 2033-08-15 | 0
MC5.1.2.5.1.43 - Cisco ASAV - Development (development and development testing) of Fault Management integration requirements'' | 2033-08-16 | 2033-09-30 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 430 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 4 | No | FWA | SE&I: OSS & Orchestration | No |  | 2033-08-16 | 2033-09-30 | 0
MC5.1.2.5.1.44 - Cisco ASAV - Retrieving integration requirements from vendors for Performance Management'' | 2033-10-03 | 2034-02-09 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 431 |  |  | Integration Priority 4 | No | FWA | SE&I: OSS & Orchestration | No |  | 2033-10-03 | 2034-02-09 | 0
MC5.1.2.5.1.45 - Cisco ASAV - Development (development and development testing) of Performance Management integration requirements'' | 2034-02-10 | 2034-03-29 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 432 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 4 | No | FWA | SE&I: OSS & Orchestration | No |  | 2034-02-10 | 2034-03-29 | 0
MC5.1.2.5.1.46 - Cisco ASAV nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2034-03-30 | 2034-05-01 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 433 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 4 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2034-03-30 | 2034-05-01 | 0
MC5.1.2.5.1.47 - External dependency on QA E2E testing' | 2034-05-02 | 2034-05-02 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 434 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2034-05-02 | 2034-05-02 | 0
MC5.1.2.5.1.48 - Cisco ASAV nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2034-05-03 | 2034-05-04 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 435 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production)' |  | Integration Priority 4 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2034-05-03 | 2034-05-04 | 0
MC5.1.2.5.1.49 - KeyClock - Retrieving integration requirements from vendors for Cloud Observability'' | 2034-05-05 | 2034-08-01 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 436 |  |  | Integration Priority 14 | No | FWA | SE&I: OSS & Orchestration | No |  | 2034-05-05 | 2034-08-01 | 0
MC5.1.2.5.1.50 - External dependency on KeyClock Nodes availability in Mainz lab' | 2034-08-02 | 2034-08-02 |  |  | 1d | Rakuten | Rollout |  |  |  | 437 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2034-08-02 | 2034-08-02 | 0
MC5.1.2.5.1.51 - KeyClock - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2034-08-03 | 2034-09-14 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 438 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 14 | No | FWA | SE&I: OSS & Orchestration | No |  | 2034-08-03 | 2034-09-14 | 0
MC5.1.2.5.1.52 - KeyClock - Retrieving integration requirements from vendors for Inventory Management'' | 2034-09-15 | 2034-12-12 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 439 |  |  | Integration Priority 14 | No | FWA | SE&I: OSS & Orchestration | No |  | 2034-09-15 | 2034-12-12 | 0
MC5.1.2.5.1.53 - KeyClock - Development (development and development testing) of Inventory Management integration requirements'' | 2034-12-13 | 2035-01-24 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 440 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 14 | No | FWA | SE&I: OSS & Orchestration | No |  | 2034-12-13 | 2035-01-24 | 0
MC5.1.2.5.1.54 - KeyClock - Retrieving integration requirements from vendors for Fault Management'' | 2035-01-25 | 2035-06-05 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 441 |  |  | Integration Priority 14 | No | FWA | SE&I: OSS & Orchestration | No |  | 2035-01-25 | 2035-06-05 | 0
MC5.1.2.5.1.55 - KeyClock - Development (development and development testing) of Fault Management integration requirements'' | 2035-06-06 | 2035-07-23 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 442 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 14 | No | FWA | SE&I: OSS & Orchestration | No |  | 2035-06-06 | 2035-07-23 | 0
MC5.1.2.5.1.56 - KeyClock - Retrieving integration requirements from vendors for Performance Management'' | 2035-07-24 | 2035-11-30 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 443 |  |  | Integration Priority 14 | No | FWA | SE&I: OSS & Orchestration | No |  | 2035-07-24 | 2035-11-30 | 0
MC5.1.2.5.1.57 - KeyClock - Development (development and development testing) of Performance Management integration requirements'' | 2035-12-03 | 2036-01-17 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 444 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 14 | No | FWA | SE&I: OSS & Orchestration | No |  | 2035-12-03 | 2036-01-17 | 0
MC5.1.2.5.1.58 - KeyClock nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2036-01-18 | 2036-02-19 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 445 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 14 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2036-01-18 | 2036-02-19 | 0
MC5.1.2.5.1.59 - External dependency on QA E2E testing' | 2036-02-20 | 2036-02-20 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 446 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2036-02-20 | 2036-02-20 | 0
MC5.1.2.5.1.60 - KeyClock nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2036-02-21 | 2036-02-22 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 447 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production)' |  | Integration Priority 14 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2036-02-21 | 2036-02-22 | 0
MC5.1.2.5.2 - Platform Security Nodes' | 2036-02-25 | 2052-05-17 |  |  | 4235d | [5 empty] | 448 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2036-02-25 | 2052-05-17 | 0
MC5.1.2.5.2.1 - Linux SFTP Server - Retrieving integration requirements from vendors for Cloud Observability'' | 2036-02-25 | 2036-05-21 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  |  |  |  | Integration Priority 5 | No | FWA | SE&I: OSS & Orchestration | No |  | 2036-02-25 | 2036-05-21 | 0
MC5.1.2.5.2.2 - External dependency on Linux SFTP Server Nodes availability in Mainz lab' | 2036-05-22 | 2036-05-22 | 2022-10-01 | 2022-10-02 | 1d | Rakuten | Rollout |  |  |  | 450 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2036-05-22 | 2036-05-22 | 0
MC5.1.2.5.2.3 - Linux SFTP Server - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2036-05-23 | 2036-07-04 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 451 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 5 | No | FWA | SE&I: OSS & Orchestration | No |  | 2036-05-23 | 2036-07-04 | 0
MC5.1.2.5.2.4 - Linux SFTP Server - Retrieving integration requirements from vendors for Inventory Management'' | 2036-07-07 | 2036-10-01 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 452 |  |  | Integration Priority 5 | No | FWA | SE&I: OSS & Orchestration | No |  | 2036-07-07 | 2036-10-01 | 0
MC5.1.2.5.2.5 - Linux SFTP Server - Development (development and development testing) of Inventory Management integration requirements'' | 2036-10-02 | 2036-11-13 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 453 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 5 | No | FWA | SE&I: OSS & Orchestration | No |  | 2036-10-02 | 2036-11-13 | 0
MC5.1.2.5.2.6 - Linux SFTP Server - Retrieving integration requirements from vendors for Fault Management'' | 2036-11-14 | 2037-03-25 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 454 |  |  | Integration Priority 5 | No | FWA | SE&I: OSS & Orchestration | No |  | 2036-11-14 | 2037-03-25 | 0
MC5.1.2.5.2.7 - Linux SFTP Server - Development (development and development testing) of Fault Management integration requirements'' | 2037-03-26 | 2037-05-12 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 455 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 5 | No | FWA | SE&I: OSS & Orchestration | No |  | 2037-03-26 | 2037-05-12 | 0
MC5.1.2.5.2.8 - Linux SFTP Server - Retrieving integration requirements from vendors for Performance Management'' | 2037-05-13 | 2037-09-21 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 456 |  |  | Integration Priority 5 | No | FWA | SE&I: OSS & Orchestration | No |  | 2037-05-13 | 2037-09-21 | 0
MC5.1.2.5.2.9 - Linux SFTP Server - Development (development and development testing) of Performance Management integration requirements'' | 2037-09-22 | 2037-11-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 457 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 5 | No | FWA | SE&I: OSS & Orchestration | No |  | 2037-09-22 | 2037-11-06 | 0
MC5.1.2.5.2.10 - Linux SFTP Server nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2037-11-09 | 2037-12-09 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 458 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 5 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2037-11-09 | 2037-12-09 | 0
MC5.1.2.5.2.11 - External dependency on QA E2E testing' | 2037-12-10 | 2037-12-10 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 459 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2037-12-10 | 2037-12-10 | 0
MC5.1.2.5.2.12 - Linux SFTP Server nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2037-12-11 | 2037-12-14 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 460 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production)' |  | Integration Priority 5 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2037-12-11 | 2037-12-14 | 0
MC5.1.2.5.2.13 - Linux Microsemi TP 5000 - Retrieving integration requirements from vendors for Cloud Observability'' | 2037-12-15 | 2038-03-11 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 461 |  |  | Integration Priority 6 | No | FWA | SE&I: OSS & Orchestration | No |  | 2037-12-15 | 2038-03-11 | 0
MC5.1.2.5.2.14 - External dependency on Nodes availability in Mainz lab' | 2038-03-12 | 2038-03-12 | 2022-10-01 | 2022-10-02 | 1d | Rakuten | Rollout |  |  |  | 462 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2038-03-12 | 2038-03-12 | 0
MC5.1.2.5.2.15 - Linux Microsemi TP 5000 - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2038-03-15 | 2038-04-26 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 463 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 6 | No | FWA | SE&I: OSS & Orchestration | No |  | 2038-03-15 | 2038-04-26 | 0
MC5.1.2.5.2.16 - Linux Microsemi TP 5000 - Retrieving integration requirements from vendors for Inventory Management'' | 2038-04-27 | 2038-07-22 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 464 |  |  | Integration Priority 6 | No | FWA | SE&I: OSS & Orchestration | No |  | 2038-04-27 | 2038-07-22 | 0
MC5.1.2.5.2.17 - Linux Microsemi TP 5000 - Development (development and development testing) of Inventory Management integration requirements'' | 2038-07-23 | 2038-09-03 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 465 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 6 | No | FWA | SE&I: OSS & Orchestration | No |  | 2038-07-23 | 2038-09-03 | 0
MC5.1.2.5.2.18 - Linux Microsemi TP 5000 - Retrieving integration requirements from vendors for Fault Management'' | 2038-09-06 | 2039-01-13 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 466 |  |  | Integration Priority 6 | No | FWA | SE&I: OSS & Orchestration | No |  | 2038-09-06 | 2039-01-13 | 0
MC5.1.2.5.2.19 - Linux Microsemi TP 5000 - Development (development and development testing) of Fault Management integration requirements'' | 2039-01-14 | 2039-03-02 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 467 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 6 | No | FWA | SE&I: OSS & Orchestration | No |  | 2039-01-14 | 2039-03-02 | 0
MC5.1.2.5.2.20 - Linux Microsemi TP 5000 - Retrieving integration requirements from vendors for Performance Management'' | 2039-03-03 | 2039-07-12 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 468 |  |  | Integration Priority 6 | No | FWA | SE&I: OSS & Orchestration | No |  | 2039-03-03 | 2039-07-12 | 0
MC5.1.2.5.2.21 - Linux Microsemi TP 5000 - Development (development and development testing) of Performance Management integration requirements'' | 2039-07-13 | 2039-08-29 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 469 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 6 | No | FWA | SE&I: OSS & Orchestration | No |  | 2039-07-13 | 2039-08-29 | 0
MC5.1.2.5.2.22 - Linux Microsemi TP 5000 nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2039-08-30 | 2039-09-29 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 470 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 6 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2039-08-30 | 2039-09-29 | 0
MC5.1.2.5.2.23 - External dependency on QA E2E testing' | 2039-09-30 | 2039-09-30 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 471 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2039-09-30 | 2039-09-30 | 0
MC5.1.2.5.2.24 - Linux Microsemi TP 5000 nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2039-10-03 | 2039-10-04 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 472 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production)' |  | Integration Priority 6 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2039-10-03 | 2039-10-04 | 0
MC5.1.2.5.2.25 - F5 Load balancer - Retrieving integration requirements from vendors for Cloud Observability'' | 2039-10-05 | 2039-12-30 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 473 |  |  | Integration Priority 7 | No | FWA | SE&I: OSS & Orchestration | No |  | 2039-10-05 | 2039-12-30 | 0
MC5.1.2.5.2.26 - External dependency on Nodes availability in Mainz lab' | 2040-01-02 | 2040-01-02 | 2022-10-01 | 2022-10-02 | 1d | Rakuten | Rollout |  |  |  | 474 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2040-01-02 | 2040-01-02 | 0
MC5.1.2.5.2.27 - F5 Load balancer - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2040-01-03 | 2040-02-14 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 475 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 7 | No | FWA | SE&I: OSS & Orchestration | No |  | 2040-01-03 | 2040-02-14 | 0
MC5.1.2.5.2.28 - F5 Load balancer - Retrieving integration requirements from vendors for Inventory Management'' | 2040-02-15 | 2040-05-11 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 476 |  |  | Integration Priority 7 | No | FWA | SE&I: OSS & Orchestration | No |  | 2040-02-15 | 2040-05-11 | 0
MC5.1.2.5.2.29 - F5 Load balancer - Development (development and development testing) of Inventory Management integration requirements'' | 2040-05-14 | 2040-06-25 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 477 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 7 | No | FWA | SE&I: OSS & Orchestration | No |  | 2040-05-14 | 2040-06-25 | 0
MC5.1.2.5.2.30 - F5 Load balancer - Retrieving integration requirements from vendors for Fault Management'' | 2040-06-26 | 2040-11-02 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 478 |  |  | Integration Priority 7 | No | FWA | SE&I: OSS & Orchestration | No |  | 2040-06-26 | 2040-11-02 | 0
MC5.1.2.5.2.31 - F5 Load balancer - Development (development and development testing) of Fault Management integration requirements'' | 2040-11-05 | 2040-12-20 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 479 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 7 | No | FWA | SE&I: OSS & Orchestration | No |  | 2040-11-05 | 2040-12-20 | 0
MC5.1.2.5.2.32 - F5 Load balancer - Retrieving integration requirements from vendors for Performance Management'' | 2040-12-21 | 2041-05-01 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 480 |  |  | Integration Priority 7 | No | FWA | SE&I: OSS & Orchestration | No |  | 2040-12-21 | 2041-05-01 | 0
MC5.1.2.5.2.33 - F5 Load balancer - Development (development and development testing) of Performance Management integration requirements'' | 2041-05-02 | 2041-06-18 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 481 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 7 | No | FWA | SE&I: OSS & Orchestration | No |  | 2041-05-02 | 2041-06-18 | 0
MC5.1.2.5.2.34 - F5 Load balancer nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2041-06-19 | 2041-07-19 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 482 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 7 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2041-06-19 | 2041-07-19 | 0
MC5.1.2.5.2.35 - External dependency on QA E2E testing' | 2041-07-22 | 2041-07-22 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 483 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2041-07-22 | 2041-07-22 | 0
MC5.1.2.5.2.36 - F5 Load balancer nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2041-07-23 | 2041-07-24 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 484 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production)' |  | Integration Priority 7 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2041-07-23 | 2041-07-24 | 0
MC5.1.2.5.2.37 - F5 DHCP+EMS - Retrieving integration requirements from vendors for Cloud Observability'' | 2041-07-25 | 2041-10-21 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 485 |  |  | Integration Priority 9 | No | FWA | SE&I: OSS & Orchestration | No |  | 2041-07-25 | 2041-10-21 | 0
MC5.1.2.5.2.38 - External dependency on Nodes availability in Mainz lab' | 2041-10-22 | 2041-10-22 |  |  | 1d | Rakuten | Rollout |  |  |  | 486 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2041-10-22 | 2041-10-22 | 0
MC5.1.2.5.2.39 - F5 DHCP+EMS - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2041-10-23 | 2041-12-04 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 487 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 9 | No | FWA | SE&I: OSS & Orchestration | No |  | 2041-10-23 | 2041-12-04 | 0
MC5.1.2.5.2.40 - F5 DHCP+EMS - Retrieving integration requirements from vendors for Inventory Management'' | 2041-12-05 | 2042-03-03 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 488 |  |  | Integration Priority 9 | No | FWA | SE&I: OSS & Orchestration | No |  | 2041-12-05 | 2042-03-03 | 0
MC5.1.2.5.2.41 - F5 DHCP+EMS - Development (development and development testing) of Inventory Management integration requirements'' | 2042-03-04 | 2042-04-15 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 489 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 9 | No | FWA | SE&I: OSS & Orchestration | No |  | 2042-03-04 | 2042-04-15 | 0
MC5.1.2.5.2.42 - F5 DHCP+EMS - Retrieving integration requirements from vendors for Fault Management'' | 2042-04-16 | 2042-08-25 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 490 |  |  | Integration Priority 9 | No | FWA | SE&I: OSS & Orchestration | No |  | 2042-04-16 | 2042-08-25 | 0
MC5.1.2.5.2.43 - F5 DHCP+EMS - Development (development and development testing) of Fault Management integration requirements'' | 2042-08-26 | 2042-10-10 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 491 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 9 | No | FWA | SE&I: OSS & Orchestration | No |  | 2042-08-26 | 2042-10-10 | 0
MC5.1.2.5.2.44 - F5 DHCP+EMS - Retrieving integration requirements from vendors for Performance Management'' | 2042-10-13 | 2043-02-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 492 |  |  | Integration Priority 9 | No | FWA | SE&I: OSS & Orchestration | No |  | 2042-10-13 | 2043-02-19 | 0
MC5.1.2.5.2.45 - F5 DHCP+EMS - Development (development and development testing) of Performance Management integration requirements'' | 2043-02-20 | 2043-04-08 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 493 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 9 | No | FWA | SE&I: OSS & Orchestration | No |  | 2043-02-20 | 2043-04-08 | 0
MC5.1.2.5.2.46 - F5 DHCP+EMS nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2043-04-09 | 2043-05-11 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 494 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 9 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2043-04-09 | 2043-05-11 | 0
MC5.1.2.5.2.47 - External dependency on QA E2E testing' | 2043-05-12 | 2043-05-12 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 495 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2043-05-12 | 2043-05-12 | 0
MC5.1.2.5.2.48 - F5 DHCP+EMS nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2043-05-13 | 2043-05-14 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 496 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production)' |  | Integration Priority 9 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2043-05-13 | 2043-05-14 | 0
MC5.1.2.5.2.49 - Mavenir SecGw - Retrieving integration requirements from vendors for Cloud Observability'' | 2043-05-15 | 2043-08-11 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 497 |  |  | Integration Priority 13 | No | FWA | SE&I: OSS & Orchestration | No |  | 2043-05-15 | 2043-08-11 | 0
MC5.1.2.5.2.50 - External dependency on Nodes availability in Mainz lab' | 2043-08-12 | 2043-08-12 |  |  | 1d | Rakuten | Rollout |  |  |  | 498 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2043-08-12 | 2043-08-12 | 0
MC5.1.2.5.2.51 - Mavenir SecGw - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2043-08-13 | 2043-09-24 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 499 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 13 | No | FWA | SE&I: OSS & Orchestration | No |  | 2043-08-13 | 2043-09-24 | 0
MC5.1.2.5.2.52 - Mavenir SecGw - Retrieving integration requirements from vendors for Inventory Management'' | 2043-09-25 | 2043-12-22 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 500 |  |  | Integration Priority 13 | No | FWA | SE&I: OSS & Orchestration | No |  | 2043-09-25 | 2043-12-22 | 0
MC5.1.2.5.2.53 - Mavenir SecGw - Development (development and development testing) of Inventory Management integration requirements'' | 2043-12-23 | 2044-02-03 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 501 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 13 | No | FWA | SE&I: OSS & Orchestration | No |  | 2043-12-23 | 2044-02-03 | 0
MC5.1.2.5.2.54 - Mavenir SecGw - Retrieving integration requirements from vendors for Fault Management'' | 2044-02-04 | 2044-06-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 502 |  |  | Integration Priority 13 | No | FWA | SE&I: OSS & Orchestration | No |  | 2044-02-04 | 2044-06-14 | 0
MC5.1.2.5.2.55 - Mavenir SecGw - Development (development and development testing) of Fault Management integration requirements'' | 2044-06-15 | 2044-08-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 503 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 13 | No | FWA | SE&I: OSS & Orchestration | No |  | 2044-06-15 | 2044-08-01 | 0
MC5.1.2.5.2.56 - Mavenir SecGw - Retrieving integration requirements from vendors for Performance Management'' | 2044-08-02 | 2044-12-09 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 504 |  |  | Integration Priority 13 | No | FWA | SE&I: OSS & Orchestration | No |  | 2044-08-02 | 2044-12-09 | 0
MC5.1.2.5.2.57 - Mavenir SecGw - Development (development and development testing) of Performance Management integration requirements'' | 2044-12-12 | 2045-01-26 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 505 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 13 | No | FWA | SE&I: OSS & Orchestration | No |  | 2044-12-12 | 2045-01-26 | 0
MC5.1.2.5.2.58 - Mavenir SecGw nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2045-01-27 | 2045-02-28 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 506 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 13 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2045-01-27 | 2045-02-28 | 0
MC5.1.2.5.2.59 - External dependency on QA E2E testing' | 2045-03-01 | 2045-03-01 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 507 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2045-03-01 | 2045-03-01 | 0
MC5.1.2.5.2.60 - Mavenir SecGw nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2045-03-02 | 2045-03-03 | 2022-06-08 | 2022-06-09 | 2d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 508 | MC5.1.2.1.5 - External dependency on CDC 1 Readiness, MC5.1.2.1.6 - Deployment of RCP Automator applications in CDC 1' (production)' |  | Integration Priority 13 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2045-03-02 | 2045-03-03 | 0
MC5.1.2.5.2.61 - F5 DNS+GSLB - Retrieving integration requirements from vendors for Cloud Observability'' | 2045-03-06 | 2045-05-31 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 509 |  |  | Integration Priority 17 | No | FWA | SE&I: OSS & Orchestration | No |  | 2045-03-06 | 2045-05-31 | 0
MC5.1.2.5.2.62 - External dependency on Nodes availability in Mainz lab' | 2045-06-01 | 2045-06-01 |  |  | 1d | Rakuten | Rollout |  |  |  | 510 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2045-06-01 | 2045-06-01 | 0
MC5.1.2.5.2.63 - F5 DNS+GSLB - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2045-06-02 | 2045-07-14 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 511 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 17 | No | FWA | SE&I: OSS & Orchestration | No |  | 2045-06-02 | 2045-07-14 | 0
MC5.1.2.5.2.64 - F5 DNS+GSLB - Retrieving integration requirements from vendors for Inventory Management'' | 2045-07-17 | 2045-10-11 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 512 |  |  | Integration Priority 17 | No | FWA | SE&I: OSS & Orchestration | No |  | 2045-07-17 | 2045-10-11 | 0
MC5.1.2.5.2.65 - F5 DNS+GSLB - Development (development and development testing) of Inventory Management integration requirements'' | 2045-10-12 | 2045-11-23 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 513 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 17 | No | FWA | SE&I: OSS & Orchestration | No |  | 2045-10-12 | 2045-11-23 | 0
MC5.1.2.5.2.66 - F5 DNS+GSLB - Retrieving integration requirements from vendors for Fault Management'' | 2045-11-24 | 2046-04-04 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 514 |  |  | Integration Priority 17 | No | FWA | SE&I: OSS & Orchestration | No |  | 2045-11-24 | 2046-04-04 | 0
MC5.1.2.5.2.67 - F5 DNS+GSLB - Development (development and development testing) of Fault Management integration requirements'' | 2046-04-05 | 2046-05-22 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 515 | MC5.1.2.1.1 - External dependency on Mainz lab readiness, MC5.1.2.1.2 - Deployment of RCP Automator applications in Mainz lab' |  | Integration Priority 17 | No | FWA | SE&I: OSS & Orchestration | No |  | 2046-04-05 | 2046-05-22 | 0
MC5.1.2.5.2.68 - F5 DNS+GSLB - Retrieving integration requirements from vendors for Performance Management'' | 2046-05-23 | 2046-10-01 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 516 |  |  | Integration Priority 17 | No | FWA | SE&I: OSS & Orchestration | No |  | 2046-05-23 | 2046-10-01 | 0
MC5.1.2.5.2.69 - F5 DNS+GSLB - Development (development and development testing) of Performance Management integration requirements'' | 2046-10-02 | 2046-11-16 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 517 |  |  | Integration Priority 17 | No | FWA | SE&I: OSS & Orchestration | No |  | 2046-10-02 | 2046-11-16 | 0
MC5.1.2.5.2.70 - F5 DNS+GSLB nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2046-11-19 | 2046-12-19 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 518 |  |  | Integration Priority 17 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2046-11-19 | 2046-12-19 | 0
MC5.1.2.5.2.71 - External dependency on QA E2E testing' | 2046-12-20 | 2046-12-20 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 519 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2046-12-20 | 2046-12-20 | 0
MC5.1.2.5.2.72 - F5 DNS+GSLB nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2046-12-21 | 2046-12-21 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 520 |  |  | Integration Priority 17 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2046-12-21 | 2046-12-21 | 0
MC5.1.2.5.2.73 - Ookla Speedtest - Retrieving integration requirements from vendors for Cloud Observability'' | 2046-12-24 | 2047-03-20 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 521 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2046-12-24 | 2047-03-20 | 0
MC5.1.2.5.2.74 - External dependency on Nodes availability in Mainz lab' | 2047-03-21 | 2047-03-21 |  |  | 1d | Rakuten | Rollout |  |  |  | 522 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2047-03-21 | 2047-03-21 | 0
MC5.1.2.5.2.75 - Ookla Speedtest - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2047-03-22 | 2047-05-03 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 523 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2047-03-22 | 2047-05-03 | 0
MC5.1.2.5.2.76 - Ookla Speedtest - Retrieving integration requirements from vendors for Inventory Management'' | 2047-05-06 | 2047-07-31 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 524 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2047-05-06 | 2047-07-31 | 0
MC5.1.2.5.2.77 - Ookla Speedtest - Development (development and development testing) of Inventory Management integration requirements'' | 2047-08-01 | 2047-09-12 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 525 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2047-08-01 | 2047-09-12 | 0
MC5.1.2.5.2.78 - Ookla Speedtest - Retrieving integration requirements from vendors for Fault Management'' | 2047-09-13 | 2048-01-22 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 526 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2047-09-13 | 2048-01-22 | 0
MC5.1.2.5.2.79 - Ookla Speedtest - Development (development and development testing) of Fault Management integration requirements'' | 2048-01-23 | 2048-03-10 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 527 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2048-01-23 | 2048-03-10 | 0
MC5.1.2.5.2.80 - Ookla Speedtest - Retrieving integration requirements from vendors for Performance Management'' | 2048-03-11 | 2048-07-20 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 528 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2048-03-11 | 2048-07-20 | 0
MC5.1.2.5.2.81 - Ookla Speedtest - Development (development and development testing) of Performance Management integration requirements'' | 2048-07-21 | 2048-09-04 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 529 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2048-07-21 | 2048-09-04 | 0
MC5.1.2.5.2.82 - Ookla Speedtest nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2048-09-07 | 2048-10-07 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 530 |  |  | Integration Priority | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2048-09-07 | 2048-10-07 | 0
MC5.1.2.5.2.83 - External dependency on QA E2E testing' | 2048-10-08 | 2048-10-08 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 531 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2048-10-08 | 2048-10-08 | 0
MC5.1.2.5.2.84 - Ookla Speedtest nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2048-10-09 | 2048-10-09 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 532 |  |  | Integration Priority | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2048-10-09 | 2048-10-09 | 0
MC5.1.2.5.2.85 - Redhat Repo Server - Retrieving integration requirements from vendors for Cloud Observability'' | 2048-10-12 | 2049-01-06 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 533 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2048-10-12 | 2049-01-06 | 0
MC5.1.2.5.2.86 - External dependency on Nodes availability in Mainz lab' | 2049-01-07 | 2049-01-07 |  |  | 1d | Rakuten | Rollout |  |  |  | 534 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2049-01-07 | 2049-01-07 | 0
MC5.1.2.5.2.87 - Redhat Repo Server - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2049-01-08 | 2049-02-19 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 535 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2049-01-08 | 2049-02-19 | 0
MC5.1.2.5.2.88 - Redhat Repo Server - Retrieving integration requirements from vendors for Inventory Management'' | 2049-02-22 | 2049-05-19 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 536 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2049-02-22 | 2049-05-19 | 0
MC5.1.2.5.2.89 - Redhat Repo Server - Development (development and development testing) of Inventory Management integration requirements'' | 2049-05-20 | 2049-07-01 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 537 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2049-05-20 | 2049-07-01 | 0
MC5.1.2.5.2.90 - Redhat Repo Server - Retrieving integration requirements from vendors for Fault Management'' | 2049-07-02 | 2049-11-10 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 538 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2049-07-02 | 2049-11-10 | 0
MC5.1.2.5.2.91 - Redhat Repo Server - Development (development and development testing) of Fault Management integration requirements'' | 2049-11-11 | 2049-12-28 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 539 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2049-11-11 | 2049-12-28 | 0
MC5.1.2.5.2.92 - Redhat Repo Server - Retrieving integration requirements from vendors for Performance Management'' | 2049-12-29 | 2050-05-09 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 540 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2049-12-29 | 2050-05-09 | 0
MC5.1.2.5.2.93 - Redhat Repo Server - Development (development and development testing) of Performance Management integration requirements'' | 2050-05-10 | 2050-06-24 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 541 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2050-05-10 | 2050-06-24 | 0
MC5.1.2.5.2.94 - Redhat Repo Server nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2050-06-27 | 2050-07-27 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 542 |  |  | Integration Priority | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2050-06-27 | 2050-07-27 | 0
MC5.1.2.5.2.95 - External dependency on QA E2E testing' | 2050-07-28 | 2050-07-28 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 543 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2050-07-28 | 2050-07-28 | 0
MC5.1.2.5.2.96 - Redhat Repo Server nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2050-07-29 | 2050-07-29 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 544 |  |  | Integration Priority | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2050-07-29 | 2050-07-29 | 0
MC5.1.2.5.2.97 - Linux postfix - Retrieving integration requirements from vendors for Cloud Observability'' | 2050-08-01 | 2050-10-26 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 545 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2050-08-01 | 2050-10-26 | 0
MC5.1.2.5.2.98 - External dependency on Nodes availability in Mainz lab' | 2050-10-27 | 2050-10-27 |  |  | 1d | Rakuten | Rollout |  |  |  | 546 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2050-10-27 | 2050-10-27 | 0
MC5.1.2.5.2.99 - Linux postfix - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2050-10-28 | 2050-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 547 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2050-10-28 | 2050-12-09 | 0
MC5.1.2.5.2.100 - Linux postfix - Retrieving integration requirements from vendors for Inventory Management'' | 2050-12-12 | 2051-03-08 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 548 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2050-12-12 | 2051-03-08 | 0
MC5.1.2.5.2.101 - Linux postfix - Development (development and development testing) of Inventory Management integration requirements'' | 2051-03-09 | 2051-04-20 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 549 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2051-03-09 | 2051-04-20 | 0
MC5.1.2.5.2.102 - Linux postfix - Retrieving integration requirements from vendors for Fault Management'' | 2051-04-21 | 2051-08-30 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 550 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2051-04-21 | 2051-08-30 | 0
MC5.1.2.5.2.103 - Linux postfix - Development (development and development testing) of Fault Management integration requirements'' | 2051-08-31 | 2051-10-17 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 551 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2051-08-31 | 2051-10-17 | 0
MC5.1.2.5.2.104 - Linux postfix - Retrieving integration requirements from vendors for Performance Management'' | 2051-10-18 | 2052-02-26 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 552 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2051-10-18 | 2052-02-26 | 0
MC5.1.2.5.2.105 - Linux postfix - Development (development and development testing) of Performance Management integration requirements'' | 2052-02-27 | 2052-04-12 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 553 |  |  | Integration Priority | No | FWA | SE&I: OSS & Orchestration | No |  | 2052-02-27 | 2052-04-12 | 0
MC5.1.2.5.2.106 - Linux postfix nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2052-04-15 | 2052-05-15 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 554 |  |  | Integration Priority | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2052-04-15 | 2052-05-15 | 0
MC5.1.2.5.2.107 - External dependency on QA E2E testing' | 2052-05-16 | 2052-05-16 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 555 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2052-05-16 | 2052-05-16 | 0
MC5.1.2.5.2.108 - Linux postfix nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2052-05-17 | 2052-05-17 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 556 |  |  | Integration Priority | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2052-05-17 | 2052-05-17 | 0
MC5.1.2.5.3 - Crypto Nodes' | 2052-05-20 | 2059-08-01 |  |  | 1880d | [5 empty] | 557 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2052-05-20 | 2059-08-01 | 0
MC5.1.2.5.3.1 - Utimaco HSM - Retrieving integration requirements from vendors for Cloud Observability'' | 2052-05-20 | 2052-08-14 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  |  |  |  | Integration Priority 8 | No | FWA | SE&I: OSS & Orchestration | No |  | 2052-05-20 | 2052-08-14 | 0
MC5.1.2.5.3.2 - External dependency on Nodes availability in Mainz lab' | 2052-08-15 | 2052-08-15 |  |  | 1d | Rakuten | Rollout |  |  |  | 559 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2052-08-15 | 2052-08-15 | 0
MC5.1.2.5.3.3 - Utimaco HSM - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2052-08-16 | 2052-09-27 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 560 |  |  | Integration Priority 8 | No | FWA | SE&I: OSS & Orchestration | No |  | 2052-08-16 | 2052-09-27 | 0
MC5.1.2.5.3.4 - Utimaco HSM - Retrieving integration requirements from vendors for Inventory Management'' | 2052-09-30 | 2052-12-25 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 561 |  |  | Integration Priority 8 | No | FWA | SE&I: OSS & Orchestration | No |  | 2052-09-30 | 2052-12-25 | 0
MC5.1.2.5.3.5 - Utimaco HSM - Development (development and development testing) of Inventory Management integration requirements'' | 2052-12-26 | 2053-02-06 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 562 |  |  | Integration Priority 8 | No | FWA | SE&I: OSS & Orchestration | No |  | 2052-12-26 | 2053-02-06 | 0
MC5.1.2.5.3.6 - Utimaco HSM - Retrieving integration requirements from vendors for Fault Management'' | 2053-02-07 | 2053-06-18 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 563 |  |  | Integration Priority 8 | No | FWA | SE&I: OSS & Orchestration | No |  | 2053-02-07 | 2053-06-18 | 0
MC5.1.2.5.3.7 - Utimaco HSM - Development (development and development testing) of Fault Management integration requirements'' | 2053-06-19 | 2053-08-05 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 564 |  |  | Integration Priority 8 | No | FWA | SE&I: OSS & Orchestration | No |  | 2053-06-19 | 2053-08-05 | 0
MC5.1.2.5.3.8 - Utimaco HSM - Retrieving integration requirements from vendors for Performance Management'' | 2053-08-06 | 2053-12-15 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 565 |  |  | Integration Priority 8 | No | FWA | SE&I: OSS & Orchestration | No |  | 2053-08-06 | 2053-12-15 | 0
MC5.1.2.5.3.9 - Utimaco HSM - Development (development and development testing) of Performance Management integration requirements'' | 2053-12-16 | 2054-01-30 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 566 |  |  | Integration Priority 8 | No | FWA | SE&I: OSS & Orchestration | No |  | 2053-12-16 | 2054-01-30 | 0
MC5.1.2.5.3.10 - Utimaco HSM nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2054-02-02 | 2054-03-04 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 567 |  |  | Integration Priority 8 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2054-02-02 | 2054-03-04 | 0
MC5.1.2.5.3.11 - External dependency on QA E2E testing' | 2054-03-05 | 2054-03-05 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 568 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2054-03-05 | 2054-03-05 | 0
MC5.1.2.5.3.12 - Utimaco HSM nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2054-03-06 | 2054-03-06 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 569 |  |  | Integration Priority 8 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2054-03-06 | 2054-03-06 | 0
MC5.1.2.5.3.13 - Prime Key EJBCA - Retrieving integration requirements from vendors for Cloud Observability'' | 2054-03-09 | 2054-06-03 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 570 |  |  | Integration Priority 12 | No | FWA | SE&I: OSS & Orchestration | No |  | 2054-03-09 | 2054-06-03 | 0
MC5.1.2.5.3.14 - External dependency on Nodes availability in Mainz lab' | 2054-06-04 | 2054-06-04 |  |  | 1d | Rakuten | Rollout |  |  |  | 571 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2054-06-04 | 2054-06-04 | 0
MC5.1.2.5.3.15 - Prime Key EJBCA - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2054-06-05 | 2054-07-17 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 572 |  |  | Integration Priority 12 | No | FWA | SE&I: OSS & Orchestration | No |  | 2054-06-05 | 2054-07-17 | 0
MC5.1.2.5.3.16 - Prime Key EJBCA - Retrieving integration requirements from vendors for Inventory Management'' | 2054-07-20 | 2054-10-14 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 573 |  |  | Integration Priority 12 | No | FWA | SE&I: OSS & Orchestration | No |  | 2054-07-20 | 2054-10-14 | 0
MC5.1.2.5.3.17 - Prime Key EJBCA - Development (development and development testing) of Inventory Management integration requirements'' | 2054-10-15 | 2054-11-26 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 574 |  |  | Integration Priority 12 | No | FWA | SE&I: OSS & Orchestration | No |  | 2054-10-15 | 2054-11-26 | 0
MC5.1.2.5.3.18 - Prime Key EJBCA - Retrieving integration requirements from vendors for Fault Management'' | 2054-11-27 | 2055-04-07 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 575 |  |  | Integration Priority 12 | No | FWA | SE&I: OSS & Orchestration | No |  | 2054-11-27 | 2055-04-07 | 0
MC5.1.2.5.3.19 - Prime Key EJBCA - Development (development and development testing) of Fault Management integration requirements'' | 2055-04-08 | 2055-05-25 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 576 |  |  | Integration Priority 12 | No | FWA | SE&I: OSS & Orchestration | No |  | 2055-04-08 | 2055-05-25 | 0
MC5.1.2.5.3.20 - Prime Key EJBCA - Retrieving integration requirements from vendors for Performance Management'' | 2055-05-26 | 2055-10-04 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 577 |  |  | Integration Priority 12 | No | FWA | SE&I: OSS & Orchestration | No |  | 2055-05-26 | 2055-10-04 | 0
MC5.1.2.5.3.21 - Prime Key EJBCA - Development (development and development testing) of Performance Management integration requirements'' | 2055-10-05 | 2055-11-19 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 578 |  |  | Integration Priority 12 | No | FWA | SE&I: OSS & Orchestration | No |  | 2055-10-05 | 2055-11-19 | 0
MC5.1.2.5.3.22 - Prime Key EJBCA nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2055-11-22 | 2055-12-22 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 579 |  |  | Integration Priority 12 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2055-11-22 | 2055-12-22 | 0
MC5.1.2.5.3.23 - External dependency on QA E2E testing' | 2055-12-23 | 2055-12-23 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 580 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2055-12-23 | 2055-12-23 | 0
MC5.1.2.5.3.24 - Prime Key EJBCA nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2055-12-24 | 2055-12-24 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 581 |  |  | Integration Priority 12 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2055-12-24 | 2055-12-24 | 0
MC5.1.2.5.3.25 - Keyfactor - Retrieving integration requirements from vendors for Cloud Observability'' | 2055-12-27 | 2056-03-22 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 582 |  |  | Integration Priority 15 | No | FWA | SE&I: OSS & Orchestration | No |  | 2055-12-27 | 2056-03-22 | 0
MC5.1.2.5.3.26 - External dependency on Nodes availability in Mainz lab' | 2056-03-23 | 2056-03-23 |  |  | 1d | Rakuten | Rollout |  |  |  | 583 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2056-03-23 | 2056-03-23 | 0
MC5.1.2.5.3.27 - Keyfactor - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2056-03-24 | 2056-05-05 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 584 |  |  | Integration Priority 15 | No | FWA | SE&I: OSS & Orchestration | No |  | 2056-03-24 | 2056-05-05 | 0
MC5.1.2.5.3.28 - Keyfactor - Retrieving integration requirements from vendors for Inventory Management'' | 2056-05-08 | 2056-08-02 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 585 |  |  | Integration Priority 15 | No | FWA | SE&I: OSS & Orchestration | No |  | 2056-05-08 | 2056-08-02 | 0
MC5.1.2.5.3.29 - Keyfactor - Development (development and development testing) of Inventory Management integration requirements'' | 2056-08-03 | 2056-09-14 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 586 |  |  | Integration Priority 15 | No | FWA | SE&I: OSS & Orchestration | No |  | 2056-08-03 | 2056-09-14 | 0
MC5.1.2.5.3.30 - Keyfactor - Retrieving integration requirements from vendors for Fault Management'' | 2056-09-15 | 2057-01-24 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 587 |  |  | Integration Priority 15 | No | FWA | SE&I: OSS & Orchestration | No |  | 2056-09-15 | 2057-01-24 | 0
MC5.1.2.5.3.31 - Keyfactor - Development (development and development testing) of Fault Management integration requirements'' | 2057-01-25 | 2057-03-13 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 588 |  |  | Integration Priority 15 | No | FWA | SE&I: OSS & Orchestration | No |  | 2057-01-25 | 2057-03-13 | 0
MC5.1.2.5.3.32 - Keyfactor - Retrieving integration requirements from vendors for Performance Management'' | 2057-03-14 | 2057-07-23 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 589 |  |  | Integration Priority 15 | No | FWA | SE&I: OSS & Orchestration | No |  | 2057-03-14 | 2057-07-23 | 0
MC5.1.2.5.3.33 - Keyfactor - Development (development and development testing) of Performance Management integration requirements'' | 2057-07-24 | 2057-09-07 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 590 |  |  | Integration Priority 15 | No | FWA | SE&I: OSS & Orchestration | No |  | 2057-07-24 | 2057-09-07 | 0
MC5.1.2.5.3.34 - Keyfactor nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2057-09-10 | 2057-10-10 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 591 |  |  | Integration Priority 15 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2057-09-10 | 2057-10-10 | 0
MC5.1.2.5.3.35 - External dependency on QA E2E testing' | 2057-10-11 | 2057-10-11 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 592 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2057-10-11 | 2057-10-11 | 0
MC5.1.2.5.3.36 - Keyfactor nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2057-10-12 | 2057-10-12 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 593 |  |  | Integration Priority 15 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2057-10-12 | 2057-10-12 | 0
MC5.1.2.5.3.37 - Harchicorp Vault - Retrieving integration requirements from vendors for Cloud Observability'' | 2057-10-15 | 2058-01-09 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 594 |  |  | Integration Priority 18 | No | FWA | SE&I: OSS & Orchestration | No |  | 2057-10-15 | 2058-01-09 | 0
MC5.1.2.5.3.38 - External dependency on Nodes availability in Mainz lab' | 2058-01-10 | 2058-01-10 |  |  | 1d | Rakuten | Rollout |  |  |  | 595 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2058-01-10 | 2058-01-10 | 0
MC5.1.2.5.3.39 - Harchicorp Vault - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2058-01-11 | 2058-02-22 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 596 |  |  | Integration Priority 18 | No | FWA | SE&I: OSS & Orchestration | No |  | 2058-01-11 | 2058-02-22 | 0
MC5.1.2.5.3.40 - Harchicorp Vault - Retrieving integration requirements from vendors for Inventory Management'' | 2058-02-25 | 2058-05-22 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 597 |  |  | Integration Priority 18 | No | FWA | SE&I: OSS & Orchestration | No |  | 2058-02-25 | 2058-05-22 | 0
MC5.1.2.5.3.41 - Harchicorp Vault - Development (development and development testing) of Inventory Management integration requirements'' | 2058-05-23 | 2058-07-04 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 598 |  |  | Integration Priority 18 | No | FWA | SE&I: OSS & Orchestration | No |  | 2058-05-23 | 2058-07-04 | 0
MC5.1.2.5.3.42 - Harchicorp Vault - Retrieving integration requirements from vendors for Fault Management'' | 2058-07-05 | 2058-11-13 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 599 |  |  | Integration Priority 18 | No | FWA | SE&I: OSS & Orchestration | No |  | 2058-07-05 | 2058-11-13 | 0
MC5.1.2.5.3.43 - Harchicorp Vault - Development (development and development testing) of Fault Management integration requirements'' | 2058-11-14 | 2058-12-31 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 600 |  |  | Integration Priority 18 | No | FWA | SE&I: OSS & Orchestration | No |  | 2058-11-14 | 2058-12-31 | 0
MC5.1.2.5.3.44 - Harchicorp Vault - Retrieving integration requirements from vendors for Performance Management'' | 2059-01-01 | 2059-05-12 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 601 |  |  | Integration Priority 18 | No | FWA | SE&I: OSS & Orchestration | No |  | 2059-01-01 | 2059-05-12 | 0
MC5.1.2.5.3.45 - Harchicorp Vault - Development (development and development testing) of Performance Management integration requirements'' | 2059-05-13 | 2059-06-27 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 602 |  |  | Integration Priority 18 | No | FWA | SE&I: OSS & Orchestration | No |  | 2059-05-13 | 2059-06-27 | 0
MC5.1.2.5.3.46 - Harchicorp Vault nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2059-06-30 | 2059-07-30 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 603 |  |  | Integration Priority 18 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2059-06-30 | 2059-07-30 | 0
MC5.1.2.5.3.47 - External dependency on QA E2E testing' | 2059-07-31 | 2059-07-31 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 604 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2059-07-31 | 2059-07-31 | 0
MC5.1.2.5.3.48 - Harchicorp Vault nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2059-08-01 | 2059-08-01 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 605 |  |  | Integration Priority 18 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2059-08-01 | 2059-08-01 | 0
MC5.1.2.5.4 - Perimeter Security' | 2059-08-04 | 2066-10-15 |  |  | 1880d | [5 empty] | 606 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2059-08-04 | 2066-10-15 | 0
MC5.1.2.5.4.1 - F5 FW - Retrieving integration requirements from vendors for Cloud Observability'' | 2059-08-04 | 2059-10-29 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  |  |  |  | Integration Priority 10 | No | FWA | SE&I: OSS & Orchestration | No |  | 2059-08-04 | 2059-10-29 | 0
MC5.1.2.5.4.2 - External dependency on Nodes availability in Mainz lab' | 2059-10-30 | 2059-10-30 |  |  | 1d | Rakuten | Rollout |  |  |  | 608 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2059-10-30 | 2059-10-30 | 0
MC5.1.2.5.4.3 - F5 FW - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2059-10-31 | 2059-12-12 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 609 |  |  | Integration Priority 10 | No | FWA | SE&I: OSS & Orchestration | No |  | 2059-10-31 | 2059-12-12 | 0
MC5.1.2.5.4.4 - F5 FW - Retrieving integration requirements from vendors for Inventory Management'' | 2059-12-15 | 2060-03-10 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 610 |  |  | Integration Priority 10 | No | FWA | SE&I: OSS & Orchestration | No |  | 2059-12-15 | 2060-03-10 | 0
MC5.1.2.5.4.5 - F5 FW - Development (development and development testing) of Inventory Management integration requirements'' | 2060-03-11 | 2060-04-22 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 611 |  |  | Integration Priority 10 | No | FWA | SE&I: OSS & Orchestration | No |  | 2060-03-11 | 2060-04-22 | 0
MC5.1.2.5.4.6 - F5 FW - Retrieving integration requirements from vendors for Fault Management'' | 2060-04-23 | 2060-09-01 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 612 |  |  | Integration Priority 10 | No | FWA | SE&I: OSS & Orchestration | No |  | 2060-04-23 | 2060-09-01 | 0
MC5.1.2.5.4.7 - F5 FW - Development (development and development testing) of Fault Management integration requirements'' | 2060-09-02 | 2060-10-19 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 613 |  |  | Integration Priority 10 | No | FWA | SE&I: OSS & Orchestration | No |  | 2060-09-02 | 2060-10-19 | 0
MC5.1.2.5.4.8 - F5 FW - Retrieving integration requirements from vendors for Performance Management'' | 2060-10-20 | 2061-02-28 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 614 |  |  | Integration Priority 10 | No | FWA | SE&I: OSS & Orchestration | No |  | 2060-10-20 | 2061-02-28 | 0
MC5.1.2.5.4.9 - F5 FW - Development (development and development testing) of Performance Management integration requirements'' | 2061-03-01 | 2061-04-15 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 615 |  |  | Integration Priority 10 | No | FWA | SE&I: OSS & Orchestration | No |  | 2061-03-01 | 2061-04-15 | 0
MC5.1.2.5.4.10 - F5 FW nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2061-04-18 | 2061-05-18 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 616 |  |  | Integration Priority 10 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2061-04-18 | 2061-05-18 | 0
MC5.1.2.5.4.11 - External dependency on QA E2E testing' | 2061-05-19 | 2061-05-19 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 617 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2061-05-19 | 2061-05-19 | 0
MC5.1.2.5.4.12 - F5 FW nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2061-05-20 | 2061-05-20 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 618 |  |  | Integration Priority 10 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2061-05-20 | 2061-05-20 | 0
MC5.1.2.5.4.13 - F5 WAF - Retrieving integration requirements from vendors for Cloud Observability'' | 2061-05-23 | 2061-08-17 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 619 |  |  | Integration Priority 11 | No | FWA | SE&I: OSS & Orchestration | No |  | 2061-05-23 | 2061-08-17 | 0
MC5.1.2.5.4.14 - External dependency on Nodes availability in Mainz lab' | 2061-08-18 | 2061-08-18 |  |  | 1d | Rakuten | Rollout |  |  |  | 620 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2061-08-18 | 2061-08-18 | 0
MC5.1.2.5.4.15 - F5 WAF - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2061-08-19 | 2061-09-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 621 |  |  | Integration Priority 11 | No | FWA | SE&I: OSS & Orchestration | No |  | 2061-08-19 | 2061-09-30 | 0
MC5.1.2.5.4.16 - F5 WAF - Retrieving integration requirements from vendors for Inventory Management'' | 2061-10-03 | 2061-12-28 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 622 |  |  | Integration Priority 11 | No | FWA | SE&I: OSS & Orchestration | No |  | 2061-10-03 | 2061-12-28 | 0
MC5.1.2.5.4.17 - F5 WAF - Development (development and development testing) of Inventory Management integration requirements'' | 2061-12-29 | 2062-02-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 623 |  |  | Integration Priority 11 | No | FWA | SE&I: OSS & Orchestration | No |  | 2061-12-29 | 2062-02-09 | 0
MC5.1.2.5.4.18 - F5 WAF - Retrieving integration requirements from vendors for Fault Management'' | 2062-02-10 | 2062-06-21 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 624 |  |  | Integration Priority 11 | No | FWA | SE&I: OSS & Orchestration | No |  | 2062-02-10 | 2062-06-21 | 0
MC5.1.2.5.4.19 - F5 WAF - Development (development and development testing) of Fault Management integration requirements'' | 2062-06-22 | 2062-08-08 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 625 |  |  | Integration Priority 11 | No | FWA | SE&I: OSS & Orchestration | No |  | 2062-06-22 | 2062-08-08 | 0
MC5.1.2.5.4.20 - F5 WAF - Retrieving integration requirements from vendors for Performance Management'' | 2062-08-09 | 2062-12-18 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 626 |  |  | Integration Priority 11 | No | FWA | SE&I: OSS & Orchestration | No |  | 2062-08-09 | 2062-12-18 | 0
MC5.1.2.5.4.21 - F5 WAF - Development (development and development testing) of Performance Management integration requirements'' | 2062-12-19 | 2063-02-02 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 627 |  |  | Integration Priority 11 | No | FWA | SE&I: OSS & Orchestration | No |  | 2062-12-19 | 2063-02-02 | 0
MC5.1.2.5.4.22 - F5 WAF nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2063-02-05 | 2063-03-07 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 628 |  |  | Integration Priority 11 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2063-02-05 | 2063-03-07 | 0
MC5.1.2.5.4.23 - External dependency on QA E2E testing' | 2063-03-08 | 2063-03-08 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 629 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2063-03-08 | 2063-03-08 | 0
MC5.1.2.5.4.24 - F5 WAF nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2063-03-09 | 2063-03-09 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 630 |  |  | Integration Priority 11 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2063-03-09 | 2063-03-09 | 0
MC5.1.2.5.4.25 - F5 Web Proxy - Retrieving integration requirements from vendors for Cloud Observability'' | 2063-03-12 | 2063-06-06 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 631 |  |  | Integration Priority 16 | No | FWA | SE&I: OSS & Orchestration | No |  | 2063-03-12 | 2063-06-06 | 0
MC5.1.2.5.4.26 - External dependency on Nodes availability in Mainz lab' | 2063-06-07 | 2063-06-07 |  |  | 1d | Rakuten | Rollout |  |  |  | 632 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2063-06-07 | 2063-06-07 | 0
MC5.1.2.5.4.27 - F5 Web Proxy - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2063-06-08 | 2063-07-20 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 633 |  |  | Integration Priority 16 | No | FWA | SE&I: OSS & Orchestration | No |  | 2063-06-08 | 2063-07-20 | 0
MC5.1.2.5.4.28 - F5 Web Proxy - Retrieving integration requirements from vendors for Inventory Management'' | 2063-07-23 | 2063-10-17 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 634 |  |  | Integration Priority 16 | No | FWA | SE&I: OSS & Orchestration | No |  | 2063-07-23 | 2063-10-17 | 0
MC5.1.2.5.4.29 - F5 Web Proxy - Development (development and development testing) of Inventory Management integration requirements'' | 2063-10-18 | 2063-11-29 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 635 |  |  | Integration Priority 16 | No | FWA | SE&I: OSS & Orchestration | No |  | 2063-10-18 | 2063-11-29 | 0
MC5.1.2.5.4.30 - F5 Web Proxy - Retrieving integration requirements from vendors for Fault Management'' | 2063-11-30 | 2064-04-09 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 636 |  |  | Integration Priority 16 | No | FWA | SE&I: OSS & Orchestration | No |  | 2063-11-30 | 2064-04-09 | 0
MC5.1.2.5.4.31 - F5 Web Proxy - Development (development and development testing) of Fault Management integration requirements'' | 2064-04-10 | 2064-05-27 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 637 |  |  | Integration Priority 16 | No | FWA | SE&I: OSS & Orchestration | No |  | 2064-04-10 | 2064-05-27 | 0
MC5.1.2.5.4.32 - F5 Web Proxy - Retrieving integration requirements from vendors for Performance Management'' | 2064-05-28 | 2064-10-06 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 638 |  |  | Integration Priority 16 | No | FWA | SE&I: OSS & Orchestration | No |  | 2064-05-28 | 2064-10-06 | 0
MC5.1.2.5.4.33 - F5 Web Proxy - Development (development and development testing) of Performance Management integration requirements'' | 2064-10-07 | 2064-11-21 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 639 |  |  | Integration Priority 16 | No | FWA | SE&I: OSS & Orchestration | No |  | 2064-10-07 | 2064-11-21 | 0
MC5.1.2.5.4.34 - F5 Web Proxy nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2064-11-24 | 2064-12-24 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 640 |  |  | Integration Priority 16 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2064-11-24 | 2064-12-24 | 0
MC5.1.2.5.4.35 - External dependency on QA E2E testing' | 2064-12-25 | 2064-12-25 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 641 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2064-12-25 | 2064-12-25 | 0
MC5.1.2.5.4.36 - F5 Web Proxy nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2064-12-26 | 2064-12-26 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 642 |  |  | Integration Priority 16 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2064-12-26 | 2064-12-26 | 0
MC5.1.2.5.4.37 - F5 Big IQ - Retrieving integration requirements from vendors for Cloud Observability'' | 2064-12-29 | 2065-03-25 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 643 |  |  | Integration Priority 19 | No | FWA | SE&I: OSS & Orchestration | No |  | 2064-12-29 | 2065-03-25 | 0
MC5.1.2.5.4.38 - External dependency on Nodes availability in Mainz lab' | 2065-03-26 | 2065-03-26 |  |  | 1d | Rakuten | Rollout |  |  |  | 644 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2065-03-26 | 2065-03-26 | 0
MC5.1.2.5.4.39 - F5 Big IQ - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2065-03-27 | 2065-05-08 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 645 |  |  | Integration Priority 19 | No | FWA | SE&I: OSS & Orchestration | No |  | 2065-03-27 | 2065-05-08 | 0
MC5.1.2.5.4.40 - F5 Big IQ - Retrieving integration requirements from vendors for Inventory Management'' | 2065-05-11 | 2065-08-05 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 646 |  |  | Integration Priority 19 | No | FWA | SE&I: OSS & Orchestration | No |  | 2065-05-11 | 2065-08-05 | 0
MC5.1.2.5.4.41 - F5 Big IQ - Development (development and development testing) of Inventory Management integration requirements'' | 2065-08-06 | 2065-09-17 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 647 |  |  | Integration Priority 19 | No | FWA | SE&I: OSS & Orchestration | No |  | 2065-08-06 | 2065-09-17 | 0
MC5.1.2.5.4.42 - F5 Big IQ - Retrieving integration requirements from vendors for Fault Management'' | 2065-09-18 | 2066-01-27 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 648 |  |  | Integration Priority 19 | No | FWA | SE&I: OSS & Orchestration | No |  | 2065-09-18 | 2066-01-27 | 0
MC5.1.2.5.4.43 - F5 Big IQ - Development (development and development testing) of Fault Management integration requirements'' | 2066-01-28 | 2066-03-16 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 649 |  |  | Integration Priority 19 | No | FWA | SE&I: OSS & Orchestration | No |  | 2066-01-28 | 2066-03-16 | 0
MC5.1.2.5.4.44 - F5 Big IQ - Retrieving integration requirements from vendors for Performance Management'' | 2066-03-17 | 2066-07-26 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 650 |  |  | Integration Priority 19 | No | FWA | SE&I: OSS & Orchestration | No |  | 2066-03-17 | 2066-07-26 | 0
MC5.1.2.5.4.45 - F5 Big IQ - Development (development and development testing) of Performance Management integration requirements'' | 2066-07-27 | 2066-09-10 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 651 |  |  | Integration Priority 19 | No | FWA | SE&I: OSS & Orchestration | No |  | 2066-07-27 | 2066-09-10 | 0
MC5.1.2.5.4.46 - F5 Big IQ nodes surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2066-09-13 | 2066-10-13 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 652 |  |  | Integration Priority 19 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2066-09-13 | 2066-10-13 | 0
MC5.1.2.5.4.47 - External dependency on QA E2E testing' | 2066-10-14 | 2066-10-14 | 2022-03-05 | 2022-03-06 | 1d | Rakuten | E2E QA |  |  |  | 653 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2066-10-14 | 2066-10-14 | 0
MC5.1.2.5.4.48 - F5 Big IQ nodes surveillancee Deployment for Fault and Performance management systems in production'' | 2066-10-15 | 2066-10-15 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 654 |  |  | Integration Priority 19 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2066-10-15 | 2066-10-15 | 0
MC5.1.2.6 - Core surveillance' | 2066-10-18 | 2074-10-24 |  |  | 2093d | [5 empty] | 655 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2066-10-18 | 2074-10-24 | 0
MC5.1.2.6.1 - Management Nodes Surveillance' | 2066-10-18 | 2068-08-02 |  |  | 469d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2066-10-18 | 2068-08-02 | 0
MC5.1.2.6.1.1 - mCMS - Retrieving integration requirements from vendors for Cloud Observability'' | 2066-10-18 | 2067-01-12 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  |  |  |  | Integration Priority 1 | No | FWA | SE&I: OSS & Orchestration | No |  | 2066-10-18 | 2067-01-12 | 0
MC5.1.2.6.1.2 - External dependency on mCMS availability in Mainz lab' | 2067-01-13 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 658 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.1.3 - mCMS - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2066-10-18 | 2066-11-29 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 659 |  |  | Integration Priority 1 | No | FWA | SE&I: OSS & Orchestration | No |  | 2066-10-18 | 2066-11-29 | 0
MC5.1.2.6.1.4 - mCMS - Retrieving integration requirements from vendors for Inventory Management'' | 2066-11-30 | 2067-02-24 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 660 |  |  | Integration Priority 1 | No | FWA | SE&I: OSS & Orchestration | No |  | 2066-11-30 | 2067-02-24 | 0
MC5.1.2.6.1.5 - mCMS - Development (development and development testing) of Inventory Management integration requirements'' | 2067-02-25 | 2067-04-08 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 661 |  |  | Integration Priority 1 | No | FWA | SE&I: OSS & Orchestration | No |  | 2067-02-25 | 2067-04-08 | 0
MC5.1.2.6.1.6 - mCMS - Retrieving integration requirements from vendors for Fault Management'' | 2067-04-11 | 2067-08-18 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 662 |  |  | Integration Priority 1 | No | FWA | SE&I: OSS & Orchestration | No |  | 2067-04-11 | 2067-08-18 | 0
MC5.1.2.6.1.7 - mCMS - Development (development and development testing) of Fault Management integration requirements'' | 2067-08-19 | 2067-10-05 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 663 |  |  | Integration Priority 1 | No | FWA | SE&I: OSS & Orchestration | No |  | 2067-08-19 | 2067-10-05 | 0
MC5.1.2.6.1.8 - mCMS - Retrieving integration requirements from vendors for Performance Management'' | 2067-10-06 | 2068-02-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 664 |  |  | Integration Priority 1 | No | FWA | SE&I: OSS & Orchestration | No |  | 2067-10-06 | 2068-02-14 | 0
MC5.1.2.6.1.9 - mCMS - Development (development and development testing) of Performance Management integration requirements'' | 2068-02-15 | 2068-04-02 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 665 |  |  | Integration Priority 1 | No | FWA | SE&I: OSS & Orchestration | No |  | 2068-02-15 | 2068-04-02 | 0
MC5.1.2.6.1.10 - mCMS - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2068-04-03 | 2068-05-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 666 |  |  | Integration Priority 1 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2068-04-03 | 2068-05-03 | 0
MC5.1.2.6.1.11 - External dependency on QA E2E testing' | 2068-05-04 | 2068-05-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 667 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2068-05-04 | 2068-05-04 | 0
MC5.1.2.6.1.12 - mCMS - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2068-05-07 | 2068-05-07 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 668 |  |  | Integration Priority 1 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2068-05-07 | 2068-05-07 | 0
MC5.1.2.6.1.13 - MTCIL - Retrieving integration requirements from vendors for Cloud Observability'' | 2068-05-08 | 2068-08-02 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 669 |  |  | Integration Priority 2 | No | FWA | SE&I: OSS & Orchestration | No |  | 2068-05-08 | 2068-08-02 | 0
MC5.1.2.6.1.14 - External dependency on Nodes availability in Mainz lab' | 2068-08-03 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 670 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.1.15 - MTCIL - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2066-10-18 | 2066-11-29 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 671 |  |  | Integration Priority 2 | No | FWA | SE&I: OSS & Orchestration | No |  | 2066-10-18 | 2066-11-29 | 0
MC5.1.2.6.1.16 - MTCIL - Retrieving integration requirements from vendors for Inventory Management'' | 2066-11-30 | 2067-02-24 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 672 |  |  | Integration Priority 2 | No | FWA | SE&I: OSS & Orchestration | No |  | 2066-11-30 | 2067-02-24 | 0
MC5.1.2.6.1.17 - MTCIL - Development (development and development testing) of Inventory Management integration requirements'' | 2067-02-25 | 2067-04-08 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 673 |  |  | Integration Priority 2 | No | FWA | SE&I: OSS & Orchestration | No |  | 2067-02-25 | 2067-04-08 | 0
MC5.1.2.6.1.18 - MTCIL - Retrieving integration requirements from vendors for Fault Management'' | 2067-04-11 | 2067-08-18 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 674 |  |  | Integration Priority 2 | No | FWA | SE&I: OSS & Orchestration | No |  | 2067-04-11 | 2067-08-18 | 0
MC5.1.2.6.1.19 - MTCIL - Development (development and development testing) of Fault Management integration requirements'' | 2067-08-19 | 2067-10-05 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 675 |  |  | Integration Priority 2 | No | FWA | SE&I: OSS & Orchestration | No |  | 2067-08-19 | 2067-10-05 | 0
MC5.1.2.6.1.20 - MTCIL - Retrieving integration requirements from vendors for Performance Management'' | 2067-10-06 | 2068-02-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 676 |  |  | Integration Priority 2 | No | FWA | SE&I: OSS & Orchestration | No |  | 2067-10-06 | 2068-02-14 | 0
MC5.1.2.6.1.21 - MTCIL - Development (development and development testing) of Performance Management integration requirements'' | 2068-02-15 | 2068-04-02 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 677 |  |  | Integration Priority 2 | No | FWA | SE&I: OSS & Orchestration | No |  | 2068-02-15 | 2068-04-02 | 0
MC5.1.2.6.1.22 - MTCIL - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2068-04-03 | 2068-05-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 678 |  |  | Integration Priority 2 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2068-04-03 | 2068-05-03 | 0
MC5.1.2.6.1.23 - External dependency on QA E2E testing' | 2068-05-04 | 2068-05-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 679 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2068-05-04 | 2068-05-04 | 0
MC5.1.2.6.1.24 - MTCIL - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2068-05-07 | 2068-05-07 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 680 |  |  | Integration Priority 2 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2068-05-07 | 2068-05-07 | 0
MC5.1.2.6.1.25 - Analytics - Retrieving integration requirements from vendors for Cloud Observability'' | 2068-05-08 | 2068-08-02 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 681 |  |  | Integration Priority 18 | No | FWA | SE&I: OSS & Orchestration | No |  | 2068-05-08 | 2068-08-02 | 0
MC5.1.2.6.1.26 - External dependency on Nodes availability in Mainz lab' | 2068-08-03 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 682 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration
MC5.1.2.6.1.27 - Analytics - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2066-10-18 | 2066-11-29 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 683 |  |  | Integration Priority 18 | No | FWA | SE&I: OSS & Orchestration | No |  | 2066-10-18 | 2066-11-29 | 0
MC5.1.2.6.1.28 - Analytics - Retrieving integration requirements from vendors for Inventory Management'' | 2066-11-30 | 2067-02-24 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 684 |  |  | Integration Priority 18 | No | FWA | SE&I: OSS & Orchestration | No |  | 2066-11-30 | 2067-02-24 | 0
MC5.1.2.6.1.29 - Analytics - Development (development and development testing) of Inventory Management integration requirements'' | 2067-02-25 | 2067-04-08 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 685 |  |  | Integration Priority 18 | No | FWA | SE&I: OSS & Orchestration | No |  | 2067-02-25 | 2067-04-08 | 0
MC5.1.2.6.1.30 - Analytics - Retrieving integration requirements from vendors for Fault Management'' | 2067-04-11 | 2067-08-18 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 686 |  |  | Integration Priority 18 | No | FWA | SE&I: OSS & Orchestration | No |  | 2067-04-11 | 2067-08-18 | 0
MC5.1.2.6.1.31 - Analytics - Development (development and development testing) of Fault Management integration requirements'' | 2067-08-19 | 2067-10-05 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 687 |  |  | Integration Priority 18 | No | FWA | SE&I: OSS & Orchestration | No |  | 2067-08-19 | 2067-10-05 | 0
MC5.1.2.6.1.32 - Analytics - Retrieving integration requirements from vendors for Performance Management'' | 2067-10-06 | 2068-02-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 688 |  |  | Integration Priority 18 | No | FWA | SE&I: OSS & Orchestration | No |  | 2067-10-06 | 2068-02-14 | 0
MC5.1.2.6.1.33 - Analytics - Development (development and development testing) of Performance Management integration requirements'' | 2068-02-15 | 2068-04-02 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 689 |  |  | Integration Priority 18 | No | FWA | SE&I: OSS & Orchestration | No |  | 2068-02-15 | 2068-04-02 | 0
MC5.1.2.6.1.34 - Analytics - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2068-04-03 | 2068-05-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 690 |  |  | Integration Priority 18 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2068-04-03 | 2068-05-03 | 0
MC5.1.2.6.1.35 - External dependency on QA E2E testing' | 2068-05-04 | 2068-05-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 691 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2068-05-04 | 2068-05-04 | 0
MC5.1.2.6.1.36 - Analytics - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2068-05-07 | 2068-05-07 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 692 |  |  | Integration Priority 18 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2068-05-07 | 2068-05-07 | 0
MC5.1.2.6.2 - CAT-D Nodes Surveillance' | 2068-05-08 | 2069-11-26 |  |  | 406d | [5 empty] | 693 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2068-05-08 | 2069-11-26 | 0
MC5.1.2.6.2.1 - CRDL/CRDL admin - Retrieving integration requirements from vendors for Cloud Observability'' | 2068-05-08 | 2068-08-02 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  |  |  |  | Integration Priority 3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2068-05-08 | 2068-08-02 | 0
MC5.1.2.6.2.2 - External dependency on Nodes availability in Mainz lab' | 2068-08-03 | 2022-01-31 | 2022-04-19 | 2022-04-20 | 2d | Rakuten | Rollout |  |  |  | 695 |  | Consumer |  |  | FWA | SE&I: OSS & Orchestration
MC5.1.2.6.2.3 - CRDL/CRDL admin - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2068-05-08 | 2068-06-19 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 696 |  |  | Integration Priority 3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2068-05-08 | 2068-06-19 | 0
MC5.1.2.6.2.4 - CRDL/CRDL admin - Retrieving integration requirements from vendors for Inventory Management'' | 2068-06-20 | 2068-09-14 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 697 |  |  | Integration Priority 3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2068-06-20 | 2068-09-14 | 0
MC5.1.2.6.2.5 - CRDL/CRDL admin - Development (development and development testing) of Inventory Management integration requirements'' | 2068-09-17 | 2068-10-29 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 698 |  |  | Integration Priority 3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2068-09-17 | 2068-10-29 | 0
MC5.1.2.6.2.6 - CRDL/CRDL admin - Retrieving integration requirements from vendors for Fault Management'' | 2068-10-30 | 2069-03-08 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 699 |  |  | Integration Priority 3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2068-10-30 | 2069-03-08 | 0
MC5.1.2.6.2.7 - CRDL/CRDL admin - Development (development and development testing) of Fault Management integration requirements'' | 2069-03-11 | 2069-04-25 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 700 |  |  | Integration Priority 3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2069-03-11 | 2069-04-25 | 0
MC5.1.2.6.2.8 - CRDL/CRDL admin - Retrieving integration requirements from vendors for Performance Management'' | 2069-04-26 | 2069-09-04 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 701 |  |  | Integration Priority 3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2069-04-26 | 2069-09-04 | 0
MC5.1.2.6.2.9 - CRDL/CRDL admin - Development (development and development testing) of Performance Management integration requirements'' | 2069-09-05 | 2069-10-22 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 702 |  |  | Integration Priority 3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2069-09-05 | 2069-10-22 | 0
MC5.1.2.6.2.10 - CRDL/CRDL admin - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2069-10-23 | 2069-11-22 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 703 |  |  | Integration Priority 3 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2069-10-23 | 2069-11-22 | 0
MC5.1.2.6.2.11 - External dependency on QA E2E testing' | 2069-11-25 | 2069-11-25 |  |  | 1d | Rakuten | E2E QA |  |  |  | 704 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2069-11-25 | 2069-11-25 | 0
MC5.1.2.6.2.12 - CRDL/CRDL admin - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2069-11-26 | 2069-11-26 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 705 |  |  | Integration Priority 3 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2069-11-26 | 2069-11-26 | 0
MC5.1.2.6.3 - VM Based Applications Surveillance' | 2069-11-27 | 2071-06-17 |  |  | 406d | [5 empty] | 706 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2069-11-27 | 2071-06-17 | 0
MC5.1.2.6.3.1 - Gi DNS / DHCP (secure 64) - Retrieving integration requirements from vendors for Cloud Observability'' | 2069-11-27 | 2070-02-21 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  |  |  |  | Integration Priority 4 | No | FWA | SE&I: OSS & Orchestration | No |  | 2069-11-27 | 2070-02-21 | 0
MC5.1.2.6.3.2 - External dependency on Nodes availability in Mainz lab' | 2070-02-24 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 708 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.3.3 - Gi DNS / DHCP (secure 64) - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2069-11-27 | 2070-01-08 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 709 |  |  | Integration Priority 4 | No | FWA | SE&I: OSS & Orchestration | No |  | 2069-11-27 | 2070-01-08 | 0
MC5.1.2.6.3.4 - Gi DNS / DHCP (secure 64) - Retrieving integration requirements from vendors for Inventory Management'' | 2070-01-09 | 2070-04-07 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 710 |  |  | Integration Priority 4 | No | FWA | SE&I: OSS & Orchestration | No |  | 2070-01-09 | 2070-04-07 | 0
MC5.1.2.6.3.5 - Gi DNS / DHCP (secure 64) - Development (development and development testing) of Inventory Management integration requirements'' | 2070-04-08 | 2070-05-20 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 711 |  |  | Integration Priority 4 | No | FWA | SE&I: OSS & Orchestration | No |  | 2070-04-08 | 2070-05-20 | 0
MC5.1.2.6.3.6 - Gi DNS / DHCP (secure 64) - Retrieving integration requirements from vendors for Fault Management'' | 2070-05-21 | 2070-09-29 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 712 |  |  | Integration Priority 4 | No | FWA | SE&I: OSS & Orchestration | No |  | 2070-05-21 | 2070-09-29 | 0
MC5.1.2.6.3.7 - Gi DNS / DHCP (secure 64) - Development (development and development testing) of Fault Management integration requirements'' | 2070-09-30 | 2070-11-14 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 713 |  |  | Integration Priority 4 | No | FWA | SE&I: OSS & Orchestration | No |  | 2070-09-30 | 2070-11-14 | 0
MC5.1.2.6.3.8 - Gi DNS / DHCP (secure 64) - Retrieving integration requirements from vendors for Performance Management'' | 2070-11-17 | 2071-03-26 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 714 |  |  | Integration Priority 4 | No | FWA | SE&I: OSS & Orchestration | No |  | 2070-11-17 | 2071-03-26 | 0
MC5.1.2.6.3.9 - Gi DNS / DHCP (secure 64) - Development (development and development testing) of Performance Management integration requirements'' | 2071-03-27 | 2071-05-13 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 715 |  |  | Integration Priority 4 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-03-27 | 2071-05-13 | 0
MC5.1.2.6.3.10 - Gi DNS / DHCP (secure 64) - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2071-05-14 | 2071-06-15 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 716 |  |  | Integration Priority 4 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2071-05-14 | 2071-06-15 | 0
MC5.1.2.6.3.11 - External dependency on QA E2E testing' | 2071-06-16 | 2071-06-16 |  |  | 1d | Rakuten | E2E QA |  |  |  | 717 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2071-06-16 | 2071-06-16 | 0
MC5.1.2.6.3.12 - Gi DNS / DHCP (secure 64) - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2071-06-17 | 2071-06-17 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 718 |  |  | Integration Priority 4 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-17 | 2071-06-17 | 0
MC5.1.2.6.4 - CAT-C Nodes Surveillance' | 2071-06-18 | 2073-04-04 |  |  | 469d | [5 empty] | 719 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2071-06-18 | 2073-04-04 | 0
MC5.1.2.6.4.1 - AMF - Retrieving integration requirements from vendors for Cloud Observability'' | 2071-06-18 | 2071-09-14 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  |  |  |  | Integration Priority 5 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-09-14 | 0
MC5.1.2.6.4.2 - External dependency on Nodes availability in Mainz lab' | 2071-09-15 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 721 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.3 - AMF - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 722 |  |  | Integration Priority 5 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.4 - AMF - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 723 |  |  | Integration Priority 5 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.5 - AMF - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 724 |  |  | Integration Priority 5 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.6 - AMF - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 725 |  |  | Integration Priority 5 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.7 - AMF - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 726 |  |  | Integration Priority 5 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.8 - AMF - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 727 |  |  | Integration Priority 5 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.9 - AMF - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 728 |  |  | Integration Priority 5 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.10 - AMF - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 729 |  |  | Integration Priority 5 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.11 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 730 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.12 - AMF - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 731 |  |  | Integration Priority 5 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.13 - NSSF - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 732 |  |  | Integration Priority 6 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.14 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 733 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration
MC5.1.2.6.4.15 - NSSF - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 734 |  |  | Integration Priority 6 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.16 - NSSF - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 735 |  |  | Integration Priority 6 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.17 - NSSF - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 736 |  |  | Integration Priority 6 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.18 - NSSF - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 737 |  |  | Integration Priority 6 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.19 - NSSF - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 738 |  |  | Integration Priority 6 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.20 - NSSF - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 739 |  |  | Integration Priority 6 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.21 - NSSF - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 740 |  |  | Integration Priority 6 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.22 - NSSF - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 741 |  |  | Integration Priority 6 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.23 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 742 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.24 - NSSF - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 743 |  |  | Integration Priority 6 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.25 - NRF - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 744 |  |  | Integration Priority 7 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.26 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 745 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.27 - NRF - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 746 |  |  | Integration Priority 7 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.28 - NRF - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 747 |  |  | Integration Priority 7 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.29 - NRF - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 748 |  |  | Integration Priority 7 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.30 - NRF - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 749 |  |  | Integration Priority 7 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.31 - NRF - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 750 |  |  | Integration Priority 7 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.32 - NRF - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 751 |  |  | Integration Priority 7 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.33 - NRF - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 752 |  |  | Integration Priority 7 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.34 - NRF - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 753 |  |  | Integration Priority 7 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.35 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 754 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.36 - NRF - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 755 |  |  | Integration Priority 7 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.37 - SMF+SAEGW-C - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 756 |  |  | Integration Priority 8 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.38 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 757 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.39 - SMF+SAEGW-C - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 758 |  |  | Integration Priority 8 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.40 - SMF+SAEGW-C - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 759 |  |  | Integration Priority 8 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.41 - SMF+SAEGW-C - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 760 |  |  | Integration Priority 8 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.42 - SMF+SAEGW-C - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 761 |  |  | Integration Priority 8 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.43 - SMF+SAEGW-C - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 762 |  |  | Integration Priority 8 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.44 - SMF+SAEGW-C - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 763 |  |  | Integration Priority 8 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.45 - SMF+SAEGW-C - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 764 |  |  | Integration Priority 8 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.46 - SMF+SAEGW-C - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 765 |  |  | Integration Priority 8 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.47 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 766 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.48 - SMF+SAEGW-C - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 767 |  |  | Integration Priority 8 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.49 - UPF+SAEGW-U - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 768 |  |  | Integration Priority 9 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.50 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 769 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration
MC5.1.2.6.4.51 - UPF+SAEGW-U - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 770 |  |  | Integration Priority 9 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.52 - UPF+SAEGW-U - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 771 |  |  | Integration Priority 9 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.53 - UPF+SAEGW-U - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 772 |  |  | Integration Priority 9 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.54 - UPF+SAEGW-U - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 773 |  |  | Integration Priority 9 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.55 - UPF+SAEGW-U - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 774 |  |  | Integration Priority 9 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.56 - UPF+SAEGW-U - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 775 |  |  | Integration Priority 9 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.57 - UPF+SAEGW-U - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 776 |  |  | Integration Priority 9 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.58 - UPF+SAEGW-U - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 777 |  |  | Integration Priority 9 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.59 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 778 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.60 - UPF+SAEGW-U - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 779 |  |  | Integration Priority 9 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.61 - UDSF - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 780 |  |  | Integration Priority 10 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.62 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 781 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.63 - UDSF - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 782 |  |  | Integration Priority 10 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.64 - UDSF - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 783 |  |  | Integration Priority 10 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.65 - UDSF - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 784 |  |  | Integration Priority 10 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.66 - UDSF - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 785 |  |  | Integration Priority 10 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.67 - UDSF - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 786 |  |  | Integration Priority 10 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.68 - UDSF - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 787 |  |  | Integration Priority 10 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.69 - UDSF - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 788 |  |  | Integration Priority 10 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.70 - UDSF - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 789 |  |  | Integration Priority 10 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.71 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 790 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.72 - UDSF - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 791 |  |  | Integration Priority 10 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.73 - AUSF - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 792 |  |  | Integration Priority 11 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.74 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 793 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.75 - AUSF - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 794 |  |  | Integration Priority 11 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.76 - AUSF - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 795 |  |  | Integration Priority 11 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.77 - AUSF - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 796 |  |  | Integration Priority 11 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.78 - AUSF - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 797 |  |  | Integration Priority 11 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.79 - AUSF - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 798 |  |  | Integration Priority 11 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.80 - AUSF - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 799 |  |  | Integration Priority 11 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.81 - AUSF - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 800 |  |  | Integration Priority 11 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.82 - AUSF - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 801 |  |  | Integration Priority 11 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.83 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 802 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.84 - AUSF - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 803 |  |  | Integration Priority 11 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.85 - UDM - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 804 |  |  | Integration Priority 12 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.86 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 805 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.87 - UDM - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 806 |  |  | Integration Priority 12 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.88 - UDM - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 807 |  |  | Integration Priority 12 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.89 - UDM - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 808 |  |  | Integration Priority 12 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.90 - UDM - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 809 |  |  | Integration Priority 12 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.91 - UDM - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 810 |  |  | Integration Priority 12 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.92 - UDM - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 811 |  |  | Integration Priority 12 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.93 - UDM - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 812 |  |  | Integration Priority 12 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.94 - UDM - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 813 |  |  | Integration Priority 12 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.95 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 814 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.96 - UDM - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 815 |  |  | Integration Priority 12 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.97 - UDR - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 816 |  |  | Integration Priority 13 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.98 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 817 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration
MC5.1.2.6.4.99 - UDR - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 818 |  |  | Integration Priority 13 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.100 - UDR - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 819 |  |  | Integration Priority 13 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.101 - UDR - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 820 |  |  | Integration Priority 13 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.102 - UDR - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 821 |  |  | Integration Priority 13 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.103 - UDR - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 822 |  |  | Integration Priority 13 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.104 - UDR - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 823 |  |  | Integration Priority 13 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.105 - UDR - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 824 |  |  | Integration Priority 13 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.106 - UDR - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 825 |  |  | Integration Priority 13 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.107 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 826 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.108 - UDR - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 827 |  |  | Integration Priority 13 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.109 - PCF - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 828 |  |  | Integration Priority 14 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.110 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 829 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.111 - PCF - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 830 |  |  | Integration Priority 14 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.112 - PCF - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 831 |  |  | Integration Priority 14 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.113 - PCF - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 832 |  |  | Integration Priority 14 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.114 - PCF - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 833 |  |  | Integration Priority 14 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.115 - PCF - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 834 |  |  | Integration Priority 14 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.116 - PCF - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 835 |  |  | Integration Priority 14 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.117 - PCF - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 836 |  |  | Integration Priority 14 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.118 - PCF - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 837 |  |  | Integration Priority 14 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.119 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 838 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.120 - PCF - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 839 |  |  | Integration Priority 14 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.121 - ME (CGNAT+Firewall) - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 840 |  |  | Integration Priority 16 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.122 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 841 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration
MC5.1.2.6.4.123 - ME (CGNAT+Firewall) - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 842 |  |  | Integration Priority 16 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.124 - ME (CGNAT+Firewall) - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 843 |  |  | Integration Priority 16 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.125 - ME (CGNAT+Firewall) - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 844 |  |  | Integration Priority 16 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.126 - ME (CGNAT+Firewall) - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 845 |  |  | Integration Priority 16 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.127 - ME (CGNAT+Firewall) - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 846 |  |  | Integration Priority 16 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.128 - ME (CGNAT+Firewall) - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 847 |  |  | Integration Priority 16 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.129 - ME (CGNAT+Firewall) - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 848 |  |  | Integration Priority 16 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.130 - ME (CGNAT+Firewall) - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 849 |  |  | Integration Priority 16 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.131 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 850 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.132 - ME (CGNAT+Firewall) - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 851 |  |  | Integration Priority 16 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.133 - NEF - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 852 |  |  | Integration Priority 19 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.134 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 853 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.135 - NEF - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 854 |  |  | Integration Priority 19 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.136 - NEF - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 855 |  |  | Integration Priority 19 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.137 - NEF - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 856 |  |  | Integration Priority 19 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.138 - NEF - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 857 |  |  | Integration Priority 19 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.139 - NEF - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 858 |  |  | Integration Priority 19 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.140 - NEF - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 859 |  |  | Integration Priority 19 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.141 - NEF - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 860 |  |  | Integration Priority 19 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.142 - NEF - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 861 |  |  | Integration Priority 19 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.143 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 862 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.144 - NEF - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 863 |  |  | Integration Priority 19 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.145 - SecGW - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 864 |  |  | Integration Priority 20 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.146 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 865 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.147 - SecGW - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 866 |  |  | Integration Priority 20 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.148 - SecGW - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 867 |  |  | Integration Priority 20 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.149 - SecGW - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 868 |  |  | Integration Priority 20 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.150 - SecGW - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 869 |  |  | Integration Priority 20 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.151 - SecGW - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 870 |  |  | Integration Priority 20 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.152 - SecGW - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 871 |  |  | Integration Priority 20 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.153 - SecGW - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 872 |  |  | Integration Priority 20 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.154 - SecGW - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 873 |  |  | Integration Priority 20 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.155 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 874 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.156 - SecGW - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 875 |  |  | Integration Priority 20 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.157 - BSF - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 876 |  |  | Integration Priority 21 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.158 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 877 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.159 - BSF - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 878 |  |  | Integration Priority 21 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.160 - BSF - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 879 |  |  | Integration Priority 21 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.161 - BSF - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 880 |  |  | Integration Priority 21 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.162 - BSF - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 881 |  |  | Integration Priority 21 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.163 - BSF - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 882 |  |  | Integration Priority 21 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.164 - BSF - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 883 |  |  | Integration Priority 21 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.165 - BSF - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 884 |  |  | Integration Priority 21 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.166 - BSF - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 885 |  |  | Integration Priority 21 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.167 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 886 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.168 - BSF - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 887 |  |  | Integration Priority 21 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.169 - SCP - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 888 |  |  | Integration Priority 22 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.170 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-04-15 | 2022-04-18 | 2d | Rakuten | Rollout |  |  |  | 889 |  | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.171 - SCP - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 890 |  |  | Integration Priority 22 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.172 - SCP - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 891 |  |  | Integration Priority 22 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.173 - SCP - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 892 |  |  | Integration Priority 22 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.174 - SCP - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 893 |  |  | Integration Priority 22 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.175 - SCP - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 894 |  |  | Integration Priority 22 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.176 - SCP - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 895 |  |  | Integration Priority 22 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.177 - SCP - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 896 |  |  | Integration Priority 22 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.178 - SCP - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 897 |  |  | Integration Priority 22 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.179 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 898 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.180 - SCP - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 899 |  |  | Integration Priority 22 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.181 - SEPP - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 900 |  |  | Integration Priority 23 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.182 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-04-19 | 2022-04-20 | 2d | Rakuten | Rollout |  |  |  | 901 |  | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.183 - SEPP - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 902 |  |  | Integration Priority 23 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.184 - SEPP - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 903 |  |  | Integration Priority 23 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.185 - SEPP - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 904 |  |  | Integration Priority 23 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.186 - SEPP - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 905 |  |  | Integration Priority 23 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.187 - SEPP - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 906 |  |  | Integration Priority 23 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.188 - SEPP - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 907 |  |  | Integration Priority 23 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.189 - SEPP - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 908 |  |  | Integration Priority 23 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.190 - SEPP - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 909 |  |  | Integration Priority 23 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.191 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 910 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.192 - SEPP - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 911 |  |  | Integration Priority 23 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.193 - SCE-AS - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 912 |  |  | Integration Priority 24 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.194 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-04-15 | 2022-04-18 | 2d | Rakuten | Rollout |  |  |  | 913 |  | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.195 - SCE-AS - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 914 |  |  | Integration Priority 24 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.196 - SCE-AS - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 915 |  |  | Integration Priority 24 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.197 - SCE-AS - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 916 |  |  | Integration Priority 24 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.198 - SCE-AS - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 917 |  |  | Integration Priority 24 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.199 - SCE-AS - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 918 |  |  | Integration Priority 24 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.200 - SCE-AS - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 919 |  |  | Integration Priority 24 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.201 - SCE-AS - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 920 |  |  | Integration Priority 24 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.202 - SCE-AS - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 921 |  |  | Integration Priority 24 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.203 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 922 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.204 - SCE-AS - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 923 |  |  | Integration Priority 24 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.205 - CCS - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 924 |  |  | Integration Priority 25 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.206 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 925 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.207 - CCS - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 926 |  |  | Integration Priority 25 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.208 - CCS - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 927 |  |  | Integration Priority 25 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.209 - CCS - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 928 |  |  | Integration Priority 25 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.210 - CCS - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 929 |  |  | Integration Priority 25 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.211 - CCS - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 930 |  |  | Integration Priority 25 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.212 - CCS - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 931 |  |  | Integration Priority 25 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.213 - CCS - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 932 |  |  | Integration Priority 25 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.214 - CCS - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 933 |  |  | Integration Priority 25 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.215 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 934 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.216 - CCS - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 935 |  |  | Integration Priority 25 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.217 - Mediation GW - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 936 |  |  | Integration Priority 26 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.218 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 937 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.219 - Mediation GW - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 938 |  |  | Integration Priority 26 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.220 - Mediation GW - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 939 |  |  | Integration Priority 26 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.221 - Mediation GW - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 940 |  |  | Integration Priority 26 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.222 - Mediation GW - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 941 |  |  | Integration Priority 26 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.223 - Mediation GW - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 942 |  |  | Integration Priority 26 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.224 - Mediation GW - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 943 |  |  | Integration Priority 26 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.225 - Mediation GW - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 944 |  |  | Integration Priority 26 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.226 - Mediation GW - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 945 |  |  | Integration Priority 26 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.227 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 946 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.228 - Mediation GW - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 947 |  |  | Integration Priority 26 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.229 - Provisioning Gateway - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 948 |  |  | Integration Priority 27 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.230 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 949 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.231 - Provisioning Gateway - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 950 |  |  | Integration Priority 27 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.232 - Provisioning Gateway - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 951 |  |  | Integration Priority 27 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.233 - Provisioning Gateway - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 952 |  |  | Integration Priority 27 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.234 - Provisioning Gateway - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 953 |  |  | Integration Priority 27 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.235 - Provisioning Gateway - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 954 |  |  | Integration Priority 27 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.236 - Provisioning Gateway - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 955 |  |  | Integration Priority 27 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.237 - Provisioning Gateway - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 956 |  |  | Integration Priority 27 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.238 - Provisioning Gateway - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 957 |  |  | Integration Priority 27 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.239 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 958 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.240 - Provisioning Gateway - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 959 |  |  | Integration Priority 27 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.241 - DSC - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 960 |  |  | Integration Priority 28 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.242 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 961 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.243 - DSC - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 962 |  |  | Integration Priority 28 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.244 - DSC - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 963 |  |  | Integration Priority 28 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.245 - DSC - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 964 |  |  | Integration Priority 28 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.246 - DSC - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 965 |  |  | Integration Priority 28 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.247 - DSC - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 966 |  |  | Integration Priority 28 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.248 - DSC - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 967 |  |  | Integration Priority 28 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.249 - DSC - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 968 |  |  | Integration Priority 28 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.250 - DSC - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 969 |  |  | Integration Priority 28 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.251 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 970 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.252 - DSC - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 971 |  |  | Integration Priority 28 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.253 - NWDAF - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 972 |  |  | Integration Priority 30 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.254 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-04-15 | 2022-04-18 | 2d | Rakuten | Rollout |  |  |  | 973 |  | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.255 - NWDAF - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 974 |  |  | Integration Priority 30 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.256 - NWDAF - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 975 |  |  | Integration Priority 30 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.257 - NWDAF - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 976 |  |  | Integration Priority 30 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.258 - NWDAF - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 977 |  |  | Integration Priority 30 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.259 - NWDAF - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 978 |  |  | Integration Priority 30 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.260 - NWDAF - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 979 |  |  | Integration Priority 30 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.261 - NWDAF - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 980 |  |  | Integration Priority 30 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.262 - NWDAF - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 981 |  |  | Integration Priority 30 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.263 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 982 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.264 - NWDAF - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 983 |  |  | Integration Priority 30 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.4.265 - DEP - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 984 |  |  | Integration Priority 31 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.4.266 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 985 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.4.267 - DEP - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2071-06-18 | 2071-07-30 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 986 |  |  | Integration Priority 31 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-06-18 | 2071-07-30 | 0
MC5.1.2.6.4.268 - DEP - Retrieving integration requirements from vendors for Inventory Management'' | 2071-07-31 | 2071-10-27 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 987 |  |  | Integration Priority 31 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-07-31 | 2071-10-27 | 0
MC5.1.2.6.4.269 - DEP - Development (development and development testing) of Inventory Management integration requirements'' | 2071-10-28 | 2071-12-09 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 988 |  |  | Integration Priority 31 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-10-28 | 2071-12-09 | 0
MC5.1.2.6.4.270 - DEP - Retrieving integration requirements from vendors for Fault Management'' | 2071-12-10 | 2072-04-19 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 989 |  |  | Integration Priority 31 | No | FWA | SE&I: OSS & Orchestration | No |  | 2071-12-10 | 2072-04-19 | 0
MC5.1.2.6.4.271 - DEP - Development (development and development testing) of Fault Management integration requirements'' | 2072-04-20 | 2072-06-06 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 990 |  |  | Integration Priority 31 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-04-20 | 2072-06-06 | 0
MC5.1.2.6.4.272 - DEP - Retrieving integration requirements from vendors for Performance Management'' | 2072-06-07 | 2072-10-14 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 991 |  |  | Integration Priority 31 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-06-07 | 2072-10-14 | 0
MC5.1.2.6.4.273 - DEP - Development (development and development testing) of Performance Management integration requirements'' | 2072-10-17 | 2072-12-01 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 992 |  |  | Integration Priority 31 | No | FWA | SE&I: OSS & Orchestration | No |  | 2072-10-17 | 2072-12-01 | 0
MC5.1.2.6.4.274 - DEP - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2072-12-02 | 2073-01-03 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 993 |  |  | Integration Priority 31 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2072-12-02 | 2073-01-03 | 0
MC5.1.2.6.4.275 - External dependency on QA E2E testing' | 2073-01-04 | 2073-01-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 994 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2073-01-04 | 2073-01-04 | 0
MC5.1.2.6.4.276 - DEP - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2073-01-05 | 2073-01-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 995 |  |  | Integration Priority 31 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-05 | 2073-01-05 | 0
MC5.1.2.6.5 - CAT-A Nodes Surveillance' | 2073-01-06 | 2074-10-24 |  |  | 469d | [5 empty] | 996 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2073-01-06 | 2074-10-24 | 0
MC5.1.2.6.5.1 - MME - Retrieving integration requirements from vendors for Cloud Observability'' | 2073-01-06 | 2073-04-04 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  |  |  |  | Integration Priority 15 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-04-04 | 0
MC5.1.2.6.5.2 - External dependency on Nodes availability in Mainz lab' | 2073-04-05 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 998 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.5.3 - MME - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2073-01-06 | 2073-02-17 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 999 |  |  | Integration Priority 15 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-02-17 | 0
MC5.1.2.6.5.4 - MME - Retrieving integration requirements from vendors for Inventory Management'' | 2073-02-20 | 2073-05-17 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1000 |  |  | Integration Priority 15 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-02-20 | 2073-05-17 | 0
MC5.1.2.6.5.5 - MME - Development (development and development testing) of Inventory Management integration requirements'' | 2073-05-18 | 2073-06-29 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1001 |  |  | Integration Priority 15 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-05-18 | 2073-06-29 | 0
MC5.1.2.6.5.6 - MME - Retrieving integration requirements from vendors for Fault Management'' | 2073-06-30 | 2073-11-08 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 1002 |  |  | Integration Priority 15 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-06-30 | 2073-11-08 | 0
MC5.1.2.6.5.7 - MME - Development (development and development testing) of Fault Management integration requirements'' | 2073-11-09 | 2073-12-26 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1003 |  |  | Integration Priority 15 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-11-09 | 2073-12-26 | 0
MC5.1.2.6.5.8 - MME - Retrieving integration requirements from vendors for Performance Management'' | 2073-12-27 | 2074-05-07 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 1004 |  |  | Integration Priority 15 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-12-27 | 2074-05-07 | 0
MC5.1.2.6.5.9 - MME - Development (development and development testing) of Performance Management integration requirements'' | 2074-05-08 | 2074-06-22 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1005 |  |  | Integration Priority 15 | No | FWA | SE&I: OSS & Orchestration | No |  | 2074-05-08 | 2074-06-22 | 0
MC5.1.2.6.5.10 - MME - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2074-06-25 | 2074-07-25 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1006 |  |  | Integration Priority 15 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2074-06-25 | 2074-07-25 | 0
MC5.1.2.6.5.11 - External dependency on QA E2E testing' | 2074-07-26 | 2074-07-26 |  |  | 1d | Rakuten | E2E QA |  |  |  | 1007 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2074-07-26 | 2074-07-26 | 0
MC5.1.2.6.5.12 - MME - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2074-07-27 | 2074-07-27 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1008 |  |  | Integration Priority 15 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2074-07-27 | 2074-07-27 | 0
MC5.1.2.6.5.13 - HSS - Retrieving integration requirements from vendors for Cloud Observability'' | 2074-07-30 | 2074-10-24 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1009 |  |  | Integration Priority 17 | No | FWA | SE&I: OSS & Orchestration | No |  | 2074-07-30 | 2074-10-24 | 0
MC5.1.2.6.5.14 - External dependency on Nodes availability in Mainz lab' | 2074-10-25 | 2022-01-31 | 2022-01-25 | 2022-01-26 | 2d | Rakuten | Rollout |  |  |  | 1010 | Item belongs to external board | Consumer |  |  |  | SE&I: OSS & Orchestration
MC5.1.2.6.5.15 - HSS - Development (development and development testing) of Cloud Observability integration requirements' (Sandbox)' | 2073-01-06 | 2073-02-17 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1011 |  |  | Integration Priority 17 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-01-06 | 2073-02-17 | 0
MC5.1.2.6.5.16 - HSS - Retrieving integration requirements from vendors for Inventory Management'' | 2073-02-20 | 2073-05-17 |  |  | 63d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 1012 |  |  | Integration Priority 17 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-02-20 | 2073-05-17 | 0
MC5.1.2.6.5.17 - HSS - Development (development and development testing) of Inventory Management integration requirements'' | 2073-05-18 | 2073-06-29 |  |  | 31d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1013 |  |  | Integration Priority 17 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-05-18 | 2073-06-29 | 0
MC5.1.2.6.5.18 - HSS - Retrieving integration requirements from vendors for Fault Management'' | 2073-06-30 | 2073-11-08 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | Completed |  | 1014 |  |  | Integration Priority 17 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-06-30 | 2073-11-08 | 0
MC5.1.2.6.5.19 - HSS - Development (development and development testing) of Fault Management integration requirements'' | 2073-11-09 | 2073-12-26 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1015 |  |  | Integration Priority 17 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-11-09 | 2073-12-26 | 0
MC5.1.2.6.5.20 - HSS - Retrieving integration requirements from vendors for Performance Management'' | 2073-12-27 | 2074-05-07 |  |  | 94d | Rakuten | SE&I: OSS & Orchestration |  | In Progress |  | 1016 |  |  | Integration Priority 17 | No | FWA | SE&I: OSS & Orchestration | No |  | 2073-12-27 | 2074-05-07 | 0
MC5.1.2.6.5.21 - HSS - Development (development and development testing) of Performance Management integration requirements'' | 2074-05-08 | 2074-06-22 |  |  | 34d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1017 |  |  | Integration Priority 17 | No | FWA | SE&I: OSS & Orchestration | No |  | 2074-05-08 | 2074-06-22 | 0
MC5.1.2.6.5.22 - HSS - Surveillance integration for Fault and Performance management systems in Mainz Lab''' | 2074-06-25 | 2074-07-25 |  |  | 23d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1018 |  |  | Integration Priority 17 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2074-06-25 | 2074-07-25 | 0
MC5.1.2.6.5.23 - External dependency on QA E2E testing' | 2074-07-26 | 2074-07-26 |  |  | 1d | Rakuten | E2E QA |  |  |  | 1019 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2074-07-26 | 2074-07-26 | 0
MC5.1.2.6.5.24 - HSS - Surveillancee Deployment for Fault and Performance management systems in Production'' | 2074-07-27 | 2074-07-27 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1020 |  |  | Integration Priority 17 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2074-07-27 | 2074-07-27 | 0
MC5.1.2.7 - RAN automation' | 2074-07-30 | 2086-07-29 |  |  | 3131d | [5 empty] | 1021 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2074-07-30 | 2086-07-29 | 0
MC5.1.2.7.1 - Use Case 1: 5G RAN automation' | 2074-07-30 | 2080-05-31 |  |  | 1525d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2074-07-30 | 2080-05-31 | 0
MC5.1.2.7.1.1 - Requirements gathering for HELM charts/ Robin bundles - Interim Version' | 2074-07-30 | 2074-07-30 | 2022-07-01 | 2022-07-02 | 1d | Rakuten | Sandeep Gaur & Hemant |  | Delayed |  |  | Item belongs to external board, Item belongs to external board | Consumer |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2074-07-30 | 2074-07-30 | 0
MC5.1.2.7.1.2 - Requirements gathering for Planning data' | 2074-07-31 | 2074-10-26 |  |  | 64d | Rakuten | Sandeep Gaur & Hemant |  | Delayed |  | 1024 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2074-07-31 | 2074-10-26 | 0
MC5.1.2.7.1.3 - Requirements gathering for CMDB parameters finalization' | 2074-10-29 | 2075-01-24 |  |  | 64d | Rakuten | Sandeep Gaur & Hemant |  | Delayed |  | 1025 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2074-10-29 | 2075-01-24 | 0
MC5.1.2.7.1.4 - Requirements gathering for day-0 configuration parameters' | 2075-01-25 | 2075-04-24 |  |  | 64d | Rakuten | Sandeep Gaur & Hemant |  | Delayed |  | 1026 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2075-01-25 | 2075-04-24 | 0
MC5.1.2.7.1.5 - Requirements gathering for IP schema & Naming Rules Finalization' | 2075-04-25 | 2075-07-23 |  |  | 64d | Rakuten | Sandeep Gaur & Hemant |  | Delayed |  | 1027 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2075-04-25 | 2075-07-23 | 0
MC5.1.2.7.1.6 - Requirements gathering for security model integration' | 2075-07-24 | 2075-10-21 |  |  | 64d | Rakuten | Sandeep Gaur & Hemant |  | Delayed |  | 1028 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2075-07-24 | 2075-10-21 | 0
MC5.1.2.7.1.7 - Requirements gathering for day-1/ day-2 configurations' | 2075-10-22 | 2075-10-22 | 2022-07-01 | 2022-07-02 | 1d | Rakuten | Sandeep Gaur & Hemant |  | Delayed |  | 1029 | MC5.1.2.7.1.3 - Requirements gathering for CMDB parameters finalization, Item belongs to external board, Item belongs to external board' | Consumer |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2075-10-22 | 2075-10-22 | 0
MC5.1.2.7.1.8 - Requirements gathering for PNF Power On Notification Specification' | 2075-10-23 | 2075-10-23 | 2022-07-01 | 2022-07-02 | 1d | Rakuten | Sandeep Gaur & Hemant |  | Completed |  | 1030 | Item belongs to external board, Item belongs to external board | Consumer |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2075-10-23 | 2075-10-23 | 0
MC5.1.2.7.1.9 - Design for Bundle Onboarding to Cluster' | 2075-10-24 | 2075-11-19 |  |  | 19d | Rakuten | Sandeep Gaur & Hemant |  | Not started |  | 1031 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2075-10-24 | 2075-11-19 | 0
MC5.1.2.7.1.10 - Design for Helm Charts Onboarding to Cluster' | 2075-11-20 | 2075-11-20 | 2022-07-03 | 2022-07-04 | 1d | Rakuten | Sandeep Gaur & Hemant |  | Not started |  | 1032 | MC5.1.2.7.1.1 - Requirements gathering for HELM charts/ Robin bundles - Interim Version' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2075-11-20 | 2075-11-20 | 0
MC5.1.2.7.1.11 - Design for Image Onboarding to Cluster' | 2075-11-21 | 2075-12-17 |  |  | 19d | Rakuten | Sandeep Gaur & Hemant |  | Not started |  | 1033 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2075-11-21 | 2075-12-17 | 0
MC5.1.2.7.1.12 - Design for Day 0 - Parsing Logic' | 2075-12-18 | 2076-01-13 |  |  | 19d | Rakuten | Sandeep Gaur & Hemant |  | Not started |  | 1034 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2075-12-18 | 2076-01-13 | 0
MC5.1.2.7.1.13 - Design for Day 0 - Static IP requirements' | 2076-01-14 | 2076-02-07 |  |  | 19d | Rakuten |  |  | Not started |  | 1035 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2076-01-14 | 2076-02-07 | 0
MC5.1.2.7.1.14 - Design for Commissioning Triggers' | 2076-02-10 | 2076-03-05 |  |  | 19d | Rakuten |  |  | Not started |  | 1036 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2076-02-10 | 2076-03-05 | 0
MC5.1.2.7.1.15 - Design for RAN Commander readiness (with RF Planning Inputs)' | 2076-03-06 | 2076-03-06 |  |  | 1d | Rakuten |  |  | Not started |  | 1037 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2076-03-06 | 2076-03-06 | 0
MC5.1.2.7.1.16 - Design for Inventory Reconciliation' | 2076-03-09 | 2076-04-02 |  |  | 19d | Rakuten |  |  | Not started |  | 1038 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2076-03-09 | 2076-04-02 | 0
MC5.1.2.7.1.17 - Design for 5G CMDB - Dynamic Parameters' | 2076-04-03 | 2076-04-29 |  |  | 19d | Rakuten |  |  | Not started |  | 1039 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2076-04-03 | 2076-04-29 | 0
MC5.1.2.7.1.18 - Design for Slicing Support' | 2076-04-30 | 2076-05-26 |  |  | 19d | Rakuten |  |  | Not started |  | 1040 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2076-04-30 | 2076-05-26 | 0
MC5.1.2.7.1.19 - Design for Power On Notification Specification' | 2076-05-27 | 2076-06-22 |  |  | 19d | Rakuten |  |  | Not started |  | 1041 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2076-05-27 | 2076-06-22 | 0
MC5.1.2.7.1.20 - Design for New DNS & DHCP Integration' | 2076-06-23 | 2076-07-17 |  |  | 19d | Rakuten |  |  | Not started |  | 1042 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2076-06-23 | 2076-07-17 | 0
MC5.1.2.7.1.21 - Design for Vault Integration & CA Server Enrollment with CMPV2' | 2076-07-20 | 2076-08-13 |  |  | 19d | Rakuten |  |  | Not started |  | 1043 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2076-07-20 | 2076-08-13 | 0
MC5.1.2.7.1.22 - Development + Dev Testing for Bundle Onboarding to Cluster' | 2076-08-14 | 2076-11-13 |  |  | 66d | Rakuten |  |  | Not started |  | 1044 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2076-08-14 | 2076-11-13 | 0
MC5.1.2.7.1.23 - Dev Testing for Helm Charts Onboarding to Cluster' | 2076-11-16 | 2077-02-15 |  |  | 66d | Rakuten |  |  | Not started |  | 1045 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2076-11-16 | 2077-02-15 | 0
MC5.1.2.7.1.24 - Development + Dev Testing for Image Onboarding to Cluster' | 2077-02-16 | 2077-05-18 |  |  | 66d | Rakuten |  |  | Not started |  | 1046 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2077-02-16 | 2077-05-18 | 0
MC5.1.2.7.1.25 - Development + Dev Testing for Day 0 - Parsing Logic' | 2077-05-19 | 2077-08-18 |  |  | 66d | Rakuten |  |  | Not started |  | 1047 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2077-05-19 | 2077-08-18 | 0
MC5.1.2.7.1.34 - Development + Dev Testing for Power On Notification Specification' | 2077-08-19 | 2077-11-18 |  |  | 66d | Rakuten |  |  | Not started |  | 1048 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2077-08-19 | 2077-11-18 | 0
MC5.1.2.7.1.26 - Development + Dev Testing for Day 0 - Static IP requirements' | 2077-11-19 | 2078-02-18 |  |  | 66d |  |  |  | Not started |  | 1049 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2077-11-19 | 2078-02-18 | 0
MC5.1.2.7.1.27 - Development + Dev Testing for RAN Commander readiness (with RF Planning Inputs)' | 2078-02-21 | 2078-05-23 |  |  | 66d |  |  |  | Not started |  | 1050 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2078-02-21 | 2078-05-23 | 0
MC5.1.2.7.1.28 - Development + Dev Testing for Commissioning Triggers' | 2078-05-24 | 2078-08-23 |  |  | 66d |  |  |  | Not started |  | 1051 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2078-05-24 | 2078-08-23 | 0
MC5.1.2.7.1.29 - Development + Dev Testing for Inventory Reconciliation' | 2078-08-24 | 2078-11-23 |  |  | 66d |  |  |  | Not started |  | 1052 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2078-08-24 | 2078-11-23 | 0
MC5.1.2.7.1.30 - Development + Dev Testing for 5G CMDB - Dynamic Parameters' | 2078-11-24 | 2079-02-23 |  |  | 66d |  |  |  | Not started |  | 1053 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2078-11-24 | 2079-02-23 | 0
MC5.1.2.7.1.31 - Development + Dev Testing for Slicing Support' | 2079-02-24 | 2079-05-26 |  |  | 66d |  |  |  | Not started |  | 1054 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2079-02-24 | 2079-05-26 | 0
MC5.1.2.7.1.32 - Development + Dev Testing for New DNS and DNS Integration' | 2079-05-29 | 2079-08-28 |  |  | 66d |  |  |  | Not started |  | 1055 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2079-05-29 | 2079-08-28 | 0
MC5.1.2.7.1.33 - Development + Dev Testing for DCHP' | 2079-08-29 | 2079-11-28 |  |  | 66d |  |  |  | Not started |  | 1056 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2079-08-29 | 2079-11-28 | 0
STG Deployment & E2E Testing - Bundle & Helm Charts Onboarding - Day 0' | 2079-11-29 | 2080-01-12 |  |  | 33d | Rakuten |  |  | Not started |  | 1057 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2079-11-29 | 2080-01-12 | 0
STG Deployment & E2E Testing - VRAN NF Instantiation' | 2080-01-15 | 2080-02-28 |  |  | 33d | Rakuten |  |  | Not started |  | 1058 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2080-01-15 | 2080-02-28 | 0
STG Deployment & E2E Testing - VRAN - Day 1 Configuration' | 2080-02-29 | 2080-04-15 |  |  | 33d |  |  |  | Not started |  | 1059 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2080-02-29 | 2080-04-15 | 0
STG Deployment & E2E Testing - Day 2 Configuration' | 2080-04-16 | 2080-05-30 |  |  | 33d |  |  |  | Not started |  | 1060 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2080-04-16 | 2080-05-30 | 0
VRAN Automation - Production Deployment' | 2080-05-31 | 2080-05-31 |  |  | 1d |  |  |  | Not started |  | 1061 |  |  | Application Team |  |  | SE&I: OSS & Orchestration |  |  | 2080-05-31 | 2080-05-31 | 0
MC5.1.2.7.2 - Use Case 2: 4G RAN automation' | 2080-06-03 | 2086-07-29 |  |  | 1606d | [5 empty] | 1062 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2080-06-03 | 2086-07-29 | 0
MC5.1.2.7.2.1 - Requirements gathering for HELM charts/ Robin bundles - Interim Version' | 2080-06-03 | 2080-06-03 | 2022-07-01 | 2022-07-02 | 1d | Rakuten | Sandeep Gaur & Hemant |  | In progress |  |  | Item belongs to external board, Item belongs to external board | Consumer |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2080-06-03 | 2080-06-03 | 0
MC5.1.2.7.2.2 - Requirements gathering for Planning data' | 2080-06-04 | 2080-08-30 |  |  | 64d | Rakuten | Sandeep Gaur & Hemant |  | In progress |  | 1064 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2080-06-04 | 2080-08-30 | 0
MC5.1.2.7.2.3 - Requirements gathering for CMDB parameters finalization' | 2080-09-02 | 2080-11-28 |  |  | 64d | Rakuten | Sandeep Gaur & Hemant |  | In progress |  | 1065 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2080-09-02 | 2080-11-28 | 0
MC5.1.2.7.2.4 - Requirements gathering for day-0 configuration parameters' | 2080-11-29 | 2081-02-26 |  |  | 64d | Rakuten | Sandeep Gaur & Hemant |  | In progress |  | 1066 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2080-11-29 | 2081-02-26 | 0
MC5.1.2.7.2.5 - Requirements gathering for IP schema & Naming Rules Finalization' | 2081-02-27 | 2081-05-27 |  |  | 64d | Rakuten | Sandeep Gaur & Hemant |  | In progress |  | 1067 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2081-02-27 | 2081-05-27 | 0
MC5.1.2.7.2.6 - Requirements gathering for security model integration' | 2081-05-28 | 2081-08-25 |  |  | 64d | Rakuten | Sandeep Gaur & Hemant |  | In progress |  | 1068 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2081-05-28 | 2081-08-25 | 0
MC5.1.2.7.2.7 - Requirements gathering for day-1/ day-2 configurations' | 2081-08-26 | 2081-11-21 |  |  | 64d | Rakuten | Sandeep Gaur & Hemant |  | In progress |  | 1069 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2081-08-26 | 2081-11-21 | 0
MC5.1.2.7.2.8 - Requirements gathering for PNF Power On Notification Specification' | 2081-11-24 | 2082-02-20 |  |  | 65d | Rakuten | Sandeep Gaur & Hemant |  | Not started |  | 1070 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2081-11-24 | 2082-02-20 | 0
MC5.1.2.7.2.1.9 - Design for Bundle Onboarding to Cluster' | 2082-02-23 | 2082-02-23 | 2022-07-03 | 2022-07-04 | 1d | Rakuten | Sandeep Gaur & Hemant |  | Not started |  | 1071 | MC5.1.2.7.1.1 - Requirements gathering for HELM charts/ Robin bundles - Interim Version' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2082-02-23 | 2082-02-23 | 0
MC5.1.2.7.2.2.10 - Design for Helm Charts Onboarding to Cluster' | 2082-02-24 | 2082-02-24 | 2022-07-03 | 2022-07-04 | 1d | Rakuten | Sandeep Gaur & Hemant |  | Not started |  | 1072 | MC5.1.2.7.1.1 - Requirements gathering for HELM charts/ Robin bundles - Interim Version' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2082-02-24 | 2082-02-24 | 0
MC5.1.2.7.2.3.11 - Design for Image Onboarding to Cluster' | 2082-02-25 | 2082-02-25 | 2022-07-03 | 2022-07-04 | 1d | Rakuten | Sandeep Gaur & Hemant |  | Not started |  | 1073 | MC5.1.2.7.1.1 - Requirements gathering for HELM charts/ Robin bundles - Interim Version' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2082-02-25 | 2082-02-25 | 0
MC5.1.2.7.2.4.12 - Design for Day 0 - Parsing Logic' | 2082-02-26 | 2082-02-26 |  |  | 1d | Rakuten | Sandeep Gaur & Hemant |  | Not started |  | 1074 | MC5.1.2.7.1.4 - Requirements gathering for day-0 configuration parameters' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2082-02-26 | 2082-02-26 | 0
MC5.1.2.7.2.5.13 - Design for Day 0 - Static IP requirements' | 2082-02-27 | 2082-03-25 |  |  | 19d | Rakuten |  |  | Not started |  | 1075 | MC5.1.2.7.1.4 - Requirements gathering for day-0 configuration parameters' |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2082-02-27 | 2082-03-25 | 0
MC5.1.2.7.2.6.14 - Design for Commissioning Triggers' | 2082-03-26 | 2082-04-21 |  |  | 19d | Rakuten |  |  | Not started |  | 1076 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2082-03-26 | 2082-04-21 | 0
MC5.1.2.7.2.7.15 - Design for RAN Commander readiness (with RF Planning Inputs)' | 2082-04-22 | 2082-05-18 |  |  | 19d | Rakuten |  |  | Not started |  | 1077 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2082-04-22 | 2082-05-18 | 0
MC5.1.2.7.2.8.16 - Design for Inventory Reconciliation' | 2082-05-19 | 2082-06-12 |  |  | 19d | Rakuten |  |  | Not started |  | 1078 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2082-05-19 | 2082-06-12 | 0
MC5.1.2.7.2.1.9.17 - Design for 4G CMDB - Dynamic Parameters' | 2082-06-15 | 2082-07-09 |  |  | 19d | Rakuten |  |  | Not started |  | 1079 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2082-06-15 | 2082-07-09 | 0
MC5.1.2.7.2.3.11.19 - Design for Power On Notification Specification' | 2082-07-10 | 2082-08-05 |  |  | 19d | Rakuten |  |  | Not started |  | 1080 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2082-07-10 | 2082-08-05 | 0
MC5.1.2.7.2.4.12.20 - Design for New DNS & DHCP Integration' | 2082-08-06 | 2082-09-01 |  |  | 19d | Rakuten |  |  | Not started |  | 1081 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2082-08-06 | 2082-09-01 | 0
MC5.1.2.7.2.5.13.21 - Design for Vault Integration & CA Server Enrollment with CMPV2' | 2082-09-02 | 2082-09-28 |  |  | 19d | Rakuten |  |  | Not started |  | 1082 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2082-09-02 | 2082-09-28 | 0
MC5.1.2.7.2.6.14.22 - Development + Dev Testing for Bundle Onboarding to Cluster' | 2082-09-29 | 2082-12-29 |  |  | 66d | Rakuten |  |  | Not started |  | 1083 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2082-09-29 | 2082-12-29 | 0
MC5.1.2.7.2.7.15.23 - Development + Dev Testing for Helm Charts Onboarding to Cluster' | 2082-12-30 | 2083-03-31 |  |  | 66d | Rakuten |  |  | Not started |  | 1084 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2082-12-30 | 2083-03-31 | 0
MC5.1.2.7.2.8.16.24 - Development + Dev Testing for Image Onboarding to Cluster' | 2083-04-01 | 2083-07-01 |  |  | 66d | Rakuten |  |  | Not started |  | 1085 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2083-04-01 | 2083-07-01 | 0
MC5.1.2.7.2.1.9.17.25 - Development + Dev Testing for Day 0 - Parsing Logic' | 2083-07-02 | 2083-10-01 |  |  | 66d | Rakuten |  |  | Not started |  | 1086 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2083-07-02 | 2083-10-01 | 0
MC5.1.2.7.2.2.10.18.26 - Development + Dev Testing for Day 0 - Static IP requirements' | 2083-10-04 | 2084-01-03 |  |  | 66d | Rakuten |  |  | Not started |  | 1087 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2083-10-04 | 2084-01-03 | 0
MC5.1.2.7.2.3.11.19.27 - Development + Dev Testing for RAN Commander readiness (with RF Planning Inputs)' | 2084-01-04 | 2084-04-04 |  |  | 66d | Rakuten |  |  | Not started |  | 1088 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2084-01-04 | 2084-04-04 | 0
MC5.1.2.7.2.3.11.19.28 - Development + Dev Testing for Commissioning Triggers' | 2084-04-05 | 2084-10-18 |  |  | 141d |  |  |  | Not started |  | 1089 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2084-04-05 | 2084-10-18 | 0
MC5.1.2.7.2.3.11.19.29 - Development + Dev Testing for Inventory Reconciliation' | 2084-10-19 | 2085-01-18 |  |  | 66d |  |  |  | Not started |  | 1090 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2084-10-19 | 2085-01-18 | 0
MC5.1.2.7.2.3.11.19.30 - Development + Dev Testing for 4G CMDB - Dynamic Parameters' | 2085-01-19 | 2085-04-20 |  |  | 66d |  |  |  | Not started |  | 1091 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2085-01-19 | 2085-04-20 | 0
MC5.1.2.7.2.3.11.19.32 - Development + Dev Testing for New DNS and DNS Integration' | 2085-04-23 | 2085-07-23 |  |  | 66d |  |  |  | Not started |  | 1092 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2085-04-23 | 2085-07-23 | 0
MC5.1.2.7.2.3.11.19.33 - Development + Dev Testing for DCHP' | 2085-07-24 | 2085-10-23 |  |  | 66d |  |  |  | Not started |  | 1093 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2085-07-24 | 2085-10-23 | 0
MC5.1.2.7.2.3.11.19.34 - Development + Dev Testing for Power On Notification Specification' | 2085-10-24 | 2086-01-23 |  |  | 66d |  |  |  | Not started |  | 1094 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2085-10-24 | 2086-01-23 | 0
MC5.1.2.7.2.3.11.19.35 - STG Deployment & E2E Testing - Bundle & Helm Charts Onboarding - Day 0' | 2086-01-24 | 2086-03-11 |  |  | 33d | [5 empty] | 1095 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2086-01-24 | 2086-03-11 | 0
MC5.1.2.7.2.3.11.19.36 - STG Deployment & E2E Testing - VRAN NF Instantiation' | 2086-03-12 | 2086-04-25 |  |  | 33d |  |  |  | Not started |  | 1096 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2086-03-12 | 2086-04-25 | 0
MC5.1.2.7.2.3.11.19.37 - STG Deployment & E2E Testing - VRAN - Day 1 Configuration' | 2086-04-26 | 2086-06-11 |  |  | 33d |  |  |  | Not started |  | 1097 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2086-04-26 | 2086-06-11 | 0
MC5.1.2.7.2.3.11.19.38 - STG Deployment & E2E Testing - Day 2 Configuration' | 2086-06-12 | 2086-07-26 |  |  | 33d |  |  |  | Not started |  | 1098 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2086-06-12 | 2086-07-26 | 0
MC5.1.2.7.2.3.11.19.39 - VRAN Automation - Production Deployment' | 2086-07-29 | 2086-07-29 |  |  | 1d | [5 empty] | 1099 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2086-07-29 | 2086-07-29 | 0
MC5.1.2.8 - Cloud automation ' | 2086-07-30 | 2088-08-19 |  |  | 538d | [5 empty] | 1100 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2086-07-30 | 2088-08-19 | 0
MC5.1.2.8.1 - Use case 1: Robin Cluster Creation , registration and Configuration' | 2086-07-30 | 2088-08-19 |  |  | 538d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2086-07-30 | 2088-08-19 | 0
MC5.1.2.8.1.1 - External dependency on finalization of Naming schema ' | 2086-07-30 | 2086-07-30 | 2022-02-11 | 2022-02-13 | 1d | Rakuten | Design and ARB |  | in progress |  |  |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2086-07-30 | 2086-07-30 | 0
MC5.1.2.8.1.2 - Requirements Gathering for integration with IPAM' | 2086-07-31 | 2086-10-15 | 2021-11-20 | 2022-02-04 | 55d | Rakuten | Automation |  | Delayed |  | 1103 |  |  | Mostly a 2 weeks activitity Depends On IPAM naming schema details | No | FWA | SE&I: OSS & Orchestration | No |  | 2086-07-31 | 2086-10-15 | 0
MC5.1.2.8.1.3 - Requirements gathering-Day0 and Day 1 Config , DNS inputs , Naming Schema' | 2086-10-16 | 2087-01-24 | 2021-11-17 | 2022-02-25 | 73d | Rakuten | Automation |  | Delayed |  | 1104 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2086-10-16 | 2087-01-24 | 0
MC5.1.2.8.1.4 - Requirements Gathering-Delta between MDCAP 1.6 and MDCAP 1.7 for BMaaS integration' | 2087-01-27 | 2087-02-26 | 2021-11-15 | 2021-12-15 | 23d | Rakuten | Automation |  | Completed |  | 1105 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-01-27 | 2087-02-26 | 0
MC5.1.2.8.1.5 - Requirements Gathering-Security Integration finalization and requirement set up' | 2087-02-27 | 2087-02-27 |  |  | 1d | Rakuten | Eswar , Remi |  | Not started |  | 1106 |  |  | Planned dates are unknown till have the first round of discussions on new DNS with security | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-02-27 | 2087-02-27 | 0
MC5.1.2.8.1.6 - Requirements Gathering-Day 2 Operation finalization and requirement set up' | 2087-02-28 | 2087-03-14 | 2022-03-04 | 2022-03-18 | 11d | Rakuten | Automation |  | Not started |  | 1107 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-02-28 | 2087-03-14 | 0
MC5.1.2.8.1.7 - Site Management - Requirement gathering for Facility Designing'' | 2087-03-17 | 2087-04-28 | 2021-12-20 | 2022-01-31 | 31d | Tech Mahindra Design | Iqbal |  | in progress |  | 1108 |  |  | Mario is SPOC , Knowledge transfer session to be planned | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-03-17 | 2087-04-28 | 0
MC5.1.2.8.1.8 - Site Management - Facility Designing'' | 2087-04-29 | 2087-05-05 | 2022-02-01 | 2022-02-07 | 5d | Tech Mahindra Design | Iqbal |  | in progress |  | 1109 |  |  | Mario is SPOC , Knowledge transfer session to be planned | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-04-29 | 2087-05-05 | 0
MC5.1.2.8.1.9 - External dependency on CP/DP Planning L3 Process' | 2087-05-06 | 2087-05-06 |  |  | 1d | [5 empty] | 1110 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2087-05-06 | 2087-05-06 | 0
MC5.1.2.8.1.10 - Site Management - Requirement gathering for API development for Facility inputs registration' | 2087-05-07 | 2087-05-07 | 2022-04-01 | 2022-04-02 | 1d | Rakuten | Bharath |  | Not started |  | 1111 | Item belongs to external board | Consumer |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-05-07 | 2087-05-07 | 0
MC5.1.2.8.1.11 - Site Management - API development for Facility inputs registration' | 2087-05-08 | 2087-05-08 |  |  | 1d | Rakuten | Bharath |  | Not started |  | 1112 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-05-08 | 2087-05-08 | 0
MC5.1.2.8.1.12 - Site Management - Requirement gathering for POD creation and ATP Trigger' | 2087-05-09 | 2087-05-13 | 2022-11-01 | 2022-11-02 | 3d | Rakuten | Bharath / Eshwar Krishnan |  | in progress |  | 1113 |  |  | Eshwar is POC for ATP | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-05-09 | 2087-05-13 | 0
MC5.1.2.8.1.13 - Site Management - POD creation & ATP Trigger development'' | 2087-05-14 | 2087-05-14 |  |  | 1d | Rakuten | Bharath |  | Not started |  | 1114 |  |  | Eshwar is POC for ATP | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-05-14 | 2087-05-14 | 0
MC5.1.2.8.1.14 - Site Management - Requirement gathering for Mapping of datacenter to robin cluster development' ' | 2087-05-15 | 2087-05-15 | 2022-04-01 | 2022-04-02 | 1d | Tech Mahindra Design | Iqbal and Volkan |  | Not started |  | 1115 | Item belongs to external board | Consumer |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-05-15 | 2087-05-15 | 0
MC5.1.2.8.1.15 - Site Management - Mapping of datacenter to robin cluster development' ' | 2087-05-16 | 2087-05-16 |  |  | 1d | Rakuten | Bharath |  | Not started |  | 1116 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-05-16 | 2087-05-16 | 0
MC5.1.2.8.1.16 - External dependency on Construction/ATP 1A L3 Process' | 2087-05-19 | 2087-05-19 |  |  | 1d | [5 empty] | 1117 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2087-05-19 | 2087-05-19 | 0
MC5.1.2.8.1.17 - Site Management - Scanning of facility barcode changes WF configuration for the RCP connect ' | 2087-05-20 | 2087-05-20 |  |  | 1d | Rakuten | Bharath |  | Not started |  | 1118 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-05-20 | 2087-05-20 | 0
MC5.1.2.8.1.18 - Site Management - Auto-commisioning Trigger Development'' | 2087-05-21 | 2087-06-10 | 2021-12-27 | 2022-01-14 | 15d | Rakuten | Bharath |  | Completed |  | 1119 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-05-21 | 2087-06-10 | 0
MC5.1.2.8.1.19 - Requirement gathering and Design Implementation of Graph DB for cluster automation' | 2087-06-11 | 2087-06-27 | 2022-01-13 | 2022-01-31 | 13d | Rakuten | Automation |  | in progress |  | 1120 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-06-11 | 2087-06-27 | 0
MC5.1.2.8.1.20 - Design-integration of the naming Schema ' | 2087-06-30 | 2087-06-30 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1121 |  |  | It's usually 2 weeks activity , but depending on naming schema may require more effort' | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-06-30 | 2087-06-30 | 0
MC5.1.2.8.1.21 - Design-Integration with IPAM' | 2087-07-01 | 2087-07-01 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1122 |  |  | It's usually 2 weeks activity ' | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-07-01 | 2087-07-01 | 0
MC5.1.2.8.1.22 - External dependency on new DNS Readiness' | 2087-07-02 | 2087-07-02 |  |  | 1d | Rakuten | Security |  |  |  | 1123 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2087-07-02 | 2087-07-02 | 0
MC5.1.2.8.1.23 - Design-Cluster Creation and Registration' | 2087-07-03 | 2087-07-03 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1124 |  |  | Usually it's a 3 weeks activity.Site Manager Trigger is a prerequisit for start of the activity' | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-07-03 | 2087-07-03 | 0
MC5.1.2.8.1.24 - Design-Cluster Configuration' | 2087-07-04 | 2087-07-04 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1125 |  |  | Depends on SM trigger, creation and registration | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-07-04 | 2087-07-04 | 0
MC5.1.2.8.1.25 - Design-Integration with Site Manager' | 2087-07-07 | 2087-07-09 | 2021-11-15 | 2021-11-16 | 3d | Rakuten | Automation |  | Delayed |  | 1126 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-07-07 | 2087-07-09 | 0
MC5.1.2.8.1.26 - Design-Integration of BMaaS with MDCAP 1.7' | 2087-07-10 | 2087-08-04 | 2021-11-25 | 2021-12-20 | 18d | Rakuten | Automation |  | Completed |  | 1127 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-07-10 | 2087-08-04 | 0
MC5.1.2.8.1.27 - Design-Integration with DNS Server' | 2087-08-05 | 2087-08-07 | 2021-11-02 | 2021-11-03 | 3d | Rakuten | Automation |  | Delayed |  | 1128 |  |  | It depends on finalization of new DNS | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-08-05 | 2087-08-07 | 0
MC5.1.2.8.1.28 - Design-Security Integration' | 2087-08-08 | 2087-08-08 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1129 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-08-08 | 2087-08-08 | 0
MC5.1.2.8.1.29 - Design-Defining Workflow assignment on clusters, Servers, Configuration, etc.' | 2087-08-11 | 2087-08-11 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1130 |  |  | It's priority 2 task and can be taken into account later' | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-08-11 | 2087-08-11 | 0
MC5.1.2.8.1.30 - Design-Day 2 Operation (Additions ,Upgrades, etc.)' | 2087-08-12 | 2087-08-12 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1131 |  |  | It's priority 2 task and can be taken into account later' | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-08-12 | 2087-08-12 | 0
MC5.1.2.8.1.31 - Development-Graph DB for cluster automation' | 2087-08-13 | 2087-11-18 | 2021-12-26 | 2022-04-01 | 70d | Rakuten | Automation |  | in progress |  | 1132 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-08-13 | 2087-11-18 | 0
MC5.1.2.8.1.32 - Development-Integration with IPAM' | 2087-11-19 | 2088-01-29 | 2022-02-04 | 2022-04-18 | 52d | Rakuten | Automation |  | Not started |  | 1133 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2087-11-19 | 2088-01-29 | 0
MC5.1.2.8.1.33 - Development-Cluster Creation and Registration' | 2088-01-30 | 2088-03-02 | 2022-04-20 | 2022-05-20 | 23d | Rakuten | Automation |  | Not started |  | 1134 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2088-01-30 | 2088-03-02 | 0
MC5.1.2.8.1.34 - Development-Cluster Configuration' | 2088-03-03 | 2088-04-02 | 2022-04-20 | 2022-05-20 | 23d | Rakuten | Automation |  | Not started |  | 1135 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2088-03-03 | 2088-04-02 | 0
MC5.1.2.8.1.35 - Development-Integration with Site Manager' | 2088-04-05 | 2088-05-05 | 2022-04-20 | 2022-05-20 | 23d | Rakuten | Automation |  | Not started |  | 1136 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2088-04-05 | 2088-05-05 | 0
MC5.1.2.8.1.36 - Development-Integration of BMaaS with MDCAP 1.7' | 2088-05-06 | 2088-06-07 | 2022-04-20 | 2022-05-20 | 23d | Rakuten | Automation |  | Not started |  | 1137 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2088-05-06 | 2088-06-07 | 0
MC5.1.2.8.1.37 - Development-Integration with DNS Server' | 2088-06-08 | 2088-06-22 | 2022-05-23 | 2022-06-06 | 11d | Rakuten | Automation |  | Not started |  | 1138 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2088-06-08 | 2088-06-22 | 0
MC5.1.2.8.1.38 - Development-Security Integration' | 2088-06-23 | 2088-07-07 | 2022-05-23 | 2022-06-06 | 11d | Rakuten | Automation |  | Not started |  | 1139 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2088-06-23 | 2088-07-07 | 0
MC5.1.2.8.1.39 - Development-Defining Workflow assignment on clusters, Servers, Configuration, etc.' | 2088-07-08 | 2088-07-08 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1140 |  |  | The start date and effort or this task To be decided after total number of tasks | No | FWA | SE&I: OSS & Orchestration | No |  | 2088-07-08 | 2088-07-08 | 0
MC5.1.2.8.1.40 - Development-Day 2 Operation (Additions ,Upgrades, etc.)' | 2088-07-09 | 2088-07-09 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1141 |  |  | It's a 4 weeks activity,The start date for this task to be decided after total number of tasks' | No | FWA | SE&I: OSS & Orchestration | No |  | 2088-07-09 | 2088-07-09 | 0
MC5.1.2.8.1.41 - External dependency on Mainz lab Infra readiness' | 2088-07-12 | 2088-07-12 |  |  | 1d | Rakuten | Rollout |  |  |  | 1142 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2088-07-12 | 2088-07-12 | 0
MC5.1.2.8.1.42 - Deployment on Staging Environment-Integration with IPAM' | 2088-07-13 | 2088-07-13 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1143 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-07-13 | 2088-07-13 | 0
MC5.1.2.8.1.43 - Deployment on Staging Environment-Cluster Creation and Registration' | 2088-07-14 | 2088-07-14 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1144 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-07-14 | 2088-07-14 | 0
MC5.1.2.8.1.44 - Deployment on Staging Environment-Cluster Configuration' | 2088-07-15 | 2088-07-15 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1145 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-07-15 | 2088-07-15 | 0
MC5.1.2.8.1.45 - Deployment on Staging Environment-Integration with Site Manager' | 2088-07-16 | 2088-07-16 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1146 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-07-16 | 2088-07-16 | 0
MC5.1.2.8.1.46 - Deployment on Staging Environment-Integration of BMaaS with MDCAP 1.7' | 2088-07-19 | 2088-07-19 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1147 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-07-19 | 2088-07-19 | 0
MC5.1.2.8.1.47 - Deployment on Staging Environment-Integration with DNS Server' | 2088-07-20 | 2088-07-20 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1148 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-07-20 | 2088-07-20 | 0
MC5.1.2.8.1.48 - Deployment on Staging Environment-Security Integration' | 2088-07-21 | 2088-07-21 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1149 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-07-21 | 2088-07-21 | 0
MC5.1.2.8.1.49 - Deployment on Staging Environment-Defining Workflow assignment on clusters, Servers, Configuration, etc.' | 2088-07-22 | 2088-07-22 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1150 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-07-22 | 2088-07-22 | 0
MC5.1.2.8.1.50 - Deployment on Staging Environment-Day 2 Operation (Additions ,Upgrades, etc.)' | 2088-07-23 | 2088-07-23 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1151 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-07-23 | 2088-07-23 | 0
MC5.1.2.8.1.51 - External dependency on CDC 1 Infra readiness' | 2088-07-26 | 2088-07-27 | 2022-06-02 | 2022-06-03 | 2d | Rakuten | Rollout |  |  |  | 1152 | Item belongs to external board | Consumer |  |  | FWA | SE&I: OSS & Orchestration |  |  | 2088-07-26 | 2088-07-27 | 0
MC5.1.2.8.1.52 - External dependency on QA E2E testing' | 2088-07-28 | 2088-07-28 |  |  | 1d | Rakuten | E2E QA |  |  |  | 1153 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2088-07-28 | 2088-07-28 | 0
MC5.1.2.8.1.53 - Deployment on Production Environment-Integration with IPAM' | 2088-07-29 | 2088-07-29 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1154 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-07-29 | 2088-07-29 | 0
MC5.1.2.8.1.54 - External dependency on QA E2E testing' | 2088-07-30 | 2088-07-30 |  |  | 1d | Rakuten | E2E QA |  |  |  | 1155 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2088-07-30 | 2088-07-30 | 0
MC5.1.2.8.1.55 - Deployment on Production Environment-Cluster Creation and Registration' | 2088-08-02 | 2088-08-02 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1156 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-08-02 | 2088-08-02 | 0
MC5.1.2.8.1.56 - External dependency on QA E2E testing' | 2088-08-03 | 2088-08-03 |  |  | 1d | Rakuten | E2E QA |  |  |  | 1157 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2088-08-03 | 2088-08-03 | 0
MC5.1.2.8.1.57 - Deployment on Production Environment-Cluster Configuration' | 2088-08-04 | 2088-08-04 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1158 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-08-04 | 2088-08-04 | 0
MC5.1.2.8.1.58 - External dependency on QA E2E testing' | 2088-08-05 | 2088-08-05 |  |  | 1d | Rakuten | E2E QA |  |  |  | 1159 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2088-08-05 | 2088-08-05 | 0
MC5.1.2.8.1.59 - Deployment on Production Environment-Integration with Site Manager' | 2088-08-06 | 2088-08-06 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1160 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-08-06 | 2088-08-06 | 0
MC5.1.2.8.1.60 - External dependency on QA E2E testing' | 2088-08-09 | 2088-08-09 |  |  | 1d | Rakuten | E2E QA |  |  |  | 1161 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2088-08-09 | 2088-08-09 | 0
MC5.1.2.8.1.61 - Deployment on Production Environment-Integration of BMaaS with MDCAP 1.7' | 2088-08-10 | 2088-08-10 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1162 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-08-10 | 2088-08-10 | 0
MC5.1.2.8.1.62 - External dependency on QA E2E testing' | 2088-08-11 | 2088-08-11 |  |  | 1d | Rakuten | E2E QA |  |  |  | 1163 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2088-08-11 | 2088-08-11 | 0
MC5.1.2.8.1.63 - Deployment on Production Environment-Integration with DNS Server' | 2088-08-12 | 2088-08-12 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1164 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-08-12 | 2088-08-12 | 0
MC5.1.2.8.1.65 - Deployment on Production Environment-Security Integration' | 2088-08-13 | 2088-08-13 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1165 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-08-13 | 2088-08-13 | 0
MC5.1.2.8.1.66 - External dependency on QA E2E testing' | 2088-08-16 | 2088-08-16 |  |  | 1d | Rakuten | E2E QA |  |  |  | 1166 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2088-08-16 | 2088-08-16 | 0
MC5.1.2.8.1.67 - Deployment on Production Environment-Defining Workflow assignment on clusters, Servers, Configuration, etc.' | 2088-08-17 | 2088-08-17 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1167 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-08-17 | 2088-08-17 | 0
MC5.1.2.8.1.68 - External dependency on QA E2E testing' | 2088-08-18 | 2088-08-18 |  |  | 1d | Rakuten | E2E QA |  |  |  | 1168 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2088-08-18 | 2088-08-18 | 0
MC5.1.2.8.1.69 - Deployment on Production Environment-Day 2 Operation (Additions ,Upgrades, etc.)' | 2088-08-19 | 2088-08-19 |  |  | 1d | Rakuten | Automation |  | Not started |  | 1169 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2088-08-19 | 2088-08-19 | 0
MC5.1.2.9 - Transport automation' | 2088-08-20 | 2088-08-20 |  |  | 1d | [5 empty] | 1170 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2088-08-20 | 2088-08-20 | 0
MC5.1.2.9.1 - Use case 1' | 2088-08-20 | 2088-08-20 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2088-08-20 | 2088-08-20 | 0
MC5.1.2.9.1.1 - Automation use cases to be defined'' | 2088-08-20 | 2088-08-20 |  |  | 1d | Rakuten | Automation | [8 empty] | FWA | SE&I: OSS & Orchestration | No |  | 2088-08-20 | 2088-08-20 | 0
MC5.1.2.10 - Core automation' | 2088-08-23 | 2124-11-08 |  |  | 9448d | [5 empty] | 1173 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2088-08-23 | 2124-11-08 | 0
MC5.1.2.10.1 - Use case 1: Onboarding HSS CAT-A application' | 2088-08-23 | 2094-08-10 |  |  | 1557d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2088-08-23 | 2094-08-10 | 0
MC5.1.2.10.1.1 - Requirements gathering for HELM charts/ Robin bundles' | 2088-08-23 | 2088-11-18 |  |  | 64d | Rakuten |  |  | In Progress | [5 empty] | No | FWA | SE&I: OSS & Orchestration | No |  | 2088-08-23 | 2088-11-18 | 0
MC5.1.2.10.1.2 - Requirements gathering for CMDB parameters finalization' | 2088-11-19 | 2089-02-16 |  |  | 64d | Rakuten |  |  | In Progress |  | 1176 |  | Provider |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2088-11-19 | 2089-02-16 | 0
MC5.1.2.10.1.3 - Requirements gathering for day-0 configuration parameters' | 2089-02-17 | 2089-05-17 |  |  | 64d | Rakuten |  |  | In Progress |  | 1177 |  | Provider |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2089-02-17 | 2089-05-17 | 0
MC5.1.2.10.1.4 - Requirements gathering for IP schema finalization' | 2089-05-18 | 2089-08-15 |  |  | 64d | Rakuten |  |  | In Progress |  | 1178 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2089-05-18 | 2089-08-15 | 0
MC5.1.2.10.1.5 - Requirements gathering for host name and application naming convention' | 2089-08-16 | 2089-11-11 |  |  | 64d | Rakuten |  |  | In Progress |  | 1179 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2089-08-16 | 2089-11-11 | 0
MC5.1.2.10.1.6 - Requirements gathering for FQDN registration with DNS' | 2089-11-14 | 2090-02-09 |  |  | 64d | Rakuten |  |  | In Progress |  | 1180 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2089-11-14 | 2090-02-09 | 0
MC5.1.2.10.1.7 - Requirements gathering for security model integration' | 2090-02-10 | 2090-05-10 |  |  | 64d | Rakuten |  |  | Not started |  | 1181 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2090-02-10 | 2090-05-10 | 0
MC5.1.2.10.1.8 - Requirements gathering for Day1 configuration push mechanism' | 2090-05-11 | 2090-08-08 |  |  | 64d | Rakuten |  |  | In Progress |  | 1182 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2090-05-11 | 2090-08-08 | 0
MC5.1.2.10.1.9 - Requirements gathering for day-2 configuration push mechanism' | 2090-08-09 | 2090-11-06 |  |  | 64d | Rakuten |  |  | In Progress |  | 1183 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2090-08-09 | 2090-11-06 | 0
MC5.1.2.10.1.10 - Design of HELM charts/ Robin bundles' | 2090-11-07 | 2090-12-01 |  |  | 19d | Rakuten |  |  | Not started |  | 1184 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2090-11-07 | 2090-12-01 | 0
MC5.1.2.10.1.11 - Design of CMDB parameters' | 2090-12-04 | 2090-12-28 |  |  | 19d | Rakuten |  |  | Not started |  | 1185 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2090-12-04 | 2090-12-28 | 0
MC5.1.2.10.1.12 - Design of day-0 configuration parameters' | 2090-12-29 | 2091-01-24 |  |  | 19d | Rakuten |  |  | Not started |  | 1186 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2090-12-29 | 2091-01-24 | 0
MC5.1.2.10.1.13 - Design of IP schema' | 2091-01-25 | 2091-02-20 |  |  | 19d | Rakuten |  |  | Not started |  | 1187 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2091-01-25 | 2091-02-20 | 0
MC5.1.2.10.1.14 - Design of host name and application naming convention' | 2091-02-21 | 2091-03-19 |  |  | 19d | Rakuten |  |  | Not started |  | 1188 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2091-02-21 | 2091-03-19 | 0
MC5.1.2.10.1.15 - Design of FQDN registration with DNS' | 2091-03-20 | 2091-04-13 |  |  | 19d | Rakuten |  |  | Not started |  | 1189 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2091-03-20 | 2091-04-13 | 0
MC5.1.2.10.1.16 - Design of security model integration' | 2091-04-16 | 2091-05-10 |  |  | 19d | Rakuten |  |  | Not started |  | 1190 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2091-04-16 | 2091-05-10 | 0
MC5.1.2.10.1.17 - Design of day-1 configuration push mechanism' | 2091-05-11 | 2091-06-06 |  |  | 19d | Rakuten |  |  | Not started |  | 1191 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2091-05-11 | 2091-06-06 | 0
MC5.1.2.10.1.18 - Design of day-2 configuration push mechanism' | 2091-06-07 | 2091-07-03 |  |  | 19d | Rakuten |  |  | Not started |  | 1192 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2091-06-07 | 2091-07-03 | 0
MC5.1.2.10.1.19 - Development of HELM charts/ Robin bundles' | 2091-07-04 | 2091-10-01 |  |  | 64d | Rakuten |  |  | Not started |  | 1193 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2091-07-04 | 2091-10-01 | 0
MC5.1.2.10.1.20 - Development of CMDB parameters' | 2091-10-02 | 2091-12-28 |  |  | 64d | Rakuten |  |  | Not started |  | 1194 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2091-10-02 | 2091-12-28 | 0
MC5.1.2.10.1.21 - Development of day-0 configuration parameters' | 2091-12-31 | 2092-03-27 |  |  | 64d | Rakuten |  |  | Not started |  | 1195 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2091-12-31 | 2092-03-27 | 0
MC5.1.2.10.1.22 - Development of IP schema' | 2092-03-28 | 2092-06-25 |  |  | 64d | Rakuten |  |  | Not started |  | 1196 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2092-03-28 | 2092-06-25 | 0
MC5.1.2.10.1.23 - Development of host name and application naming convention' | 2092-06-26 | 2092-09-23 |  |  | 64d | Rakuten |  |  | Not started |  | 1197 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2092-06-26 | 2092-09-23 | 0
MC5.1.2.10.1.24 - Development of FQDN registration with DNS' | 2092-09-24 | 2092-12-22 |  |  | 64d | Rakuten |  |  | Not started |  | 1198 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2092-09-24 | 2092-12-22 | 0
MC5.1.2.10.1.25 - Development of security model integration' | 2092-12-23 | 2093-03-20 |  |  | 64d | Rakuten |  |  | Not started |  | 1199 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2092-12-23 | 2093-03-20 | 0
MC5.1.2.10.1.26 - Development of day-1 configuration push mechanism' | 2093-03-23 | 2093-06-18 |  |  | 64d | Rakuten |  |  | Not started |  | 1200 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2093-03-23 | 2093-06-18 | 0
MC5.1.2.10.1.27 - Development of day-2 configuration push mechanism' | 2093-06-19 | 2093-09-16 |  |  | 64d | Rakuten |  |  | Not started |  | 1201 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2093-06-19 | 2093-09-16 | 0
MC5.1.2.10.1.28 - STG Deployment of HSS App Helm Charts and Robin Bundles & E2E Testing' | 2093-09-17 | 2093-11-03 |  |  | 34d | Rakuten |  |  | Not started |  | 1202 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2093-09-17 | 2093-11-03 | 0
MC5.1.2.10.1.29 - STG Deployment HSS App Instantiation & Day 0 Configuration & E2E Testing' | 2093-11-04 | 2093-12-21 |  |  | 34d | Rakuten |  |  | Not started |  | 1203 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2093-11-04 | 2093-12-21 | 0
MC5.1.2.10.1.30 - STG Deployment of Day 1 & Day 2 Config. Push Mechanism for HSS App & E2E Testing' | 2093-12-22 | 2094-02-05 |  |  | 34d | Rakuten |  |  | Not started |  | 1204 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2093-12-22 | 2094-02-05 | 0
MC5.1.2.10.1.31 - STG Deployment of IP Schema Templates & E2E Testing' | 2094-02-08 | 2094-03-25 |  |  | 34d | Rakuten |  |  | Not started |  | 1205 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2094-02-08 | 2094-03-25 | 0
MC5.1.2.10.1.32 - STG Deployment of host name templates and E2E Testing' | 2094-03-26 | 2094-05-12 |  |  | 34d | Rakuten |  |  | Not started |  | 1206 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2094-03-26 | 2094-05-12 | 0
MC5.1.2.10.1.33 - STG Deployment of Security Module & DNS and E2E Testing' | 2094-05-13 | 2094-06-29 |  |  | 34d | Rakuten |  |  | Not started |  | 1207 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2094-05-13 | 2094-06-29 | 0
MC5.1.2.10.1.34 - Production Deployment of HSS App Helm Charts, Robin Bundles and Day 0 Configuration' | 2094-06-30 | 2094-07-13 |  |  | 10d | Rakuten |  |  | Not started |  | 1208 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2094-06-30 | 2094-07-13 | 0
MC5.1.2.10.1.35 - Production Deployment of Day 1 & Day 2 Config Push Mechanism for HSS App' | 2094-07-14 | 2094-07-27 |  |  | 10d | Rakuten |  |  | Not started |  | 1209 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2094-07-14 | 2094-07-27 | 0
MC5.1.2.10.1.36 - Production Deployment of IP & Naming Templates for HSS App' | 2094-07-28 | 2094-08-10 |  |  | 10d | Rakuten |  |  | Not started |  | 1210 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2094-07-28 | 2094-08-10 | 0
MC5.1.2.10.2 - Use case 2: Onboarding AMF CAT-C application' | 2094-08-11 | 2100-06-11 |  |  | 1523d | [5 empty] | 1211 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2094-08-11 | 2100-06-11 | 0
MC5.1.2.10.2.1 - Requirements gathering for HELM charts/ Robin bundles' | 2094-08-11 | 2094-11-08 |  |  | 64d | Rakuten |  |  | Not started | [5 empty] | No | FWA | SE&I: OSS & Orchestration | No |  | 2094-08-11 | 2094-11-08 | 0
MC5.1.2.10.2.2 - Requirements gathering for CMDB parameters finalization' | 2094-11-09 | 2095-02-04 |  |  | 64d | Rakuten |  |  | Not started |  | 1213 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2094-11-09 | 2095-02-04 | 0
MC5.1.2.10.2.5 - Requirements gathering for day-0 configuration parameters' | 2095-02-07 | 2095-05-05 |  |  | 64d | Rakuten |  |  | Not started |  | 1214 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2095-02-07 | 2095-05-05 | 0
MC5.1.2.10.2.6 - Requirements gathering for IP schema finalization' | 2095-05-06 | 2095-08-03 |  |  | 64d | Rakuten |  |  | Not started |  | 1215 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2095-05-06 | 2095-08-03 | 0
MC5.1.2.10.2.7 - Requirements gathering for host name and application naming convention' | 2095-08-04 | 2095-11-01 |  |  | 64d | Rakuten |  |  | Not started |  | 1216 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2095-08-04 | 2095-11-01 | 0
MC5.1.2.10.2.8 - Requirements gathering for FQDN registration with DNS' | 2095-11-02 | 2096-01-30 |  |  | 64d | Rakuten |  |  | Not started |  | 1217 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2095-11-02 | 2096-01-30 | 0
MC5.1.2.10.2.9 - Requirements gathering for security model integration' | 2096-01-31 | 2096-04-27 |  |  | 64d | Rakuten |  |  | Not started |  | 1218 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2096-01-31 | 2096-04-27 | 0
MC5.1.2.10.2.11 - Requirements gathering for Day1 configuration push mechanism' | 2096-04-30 | 2096-07-26 |  |  | 64d | Rakuten |  |  | Not started |  | 1219 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2096-04-30 | 2096-07-26 | 0
MC5.1.2.10.2.12 - Requirements gathering for day-2 configuration push mechanism' | 2096-07-27 | 2096-10-24 |  |  | 64d | Rakuten |  |  | Not started |  | 1220 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2096-07-27 | 2096-10-24 | 0
MC5.1.2.10.2.13 - Design of HELM charts/ Robin bundles' | 2096-10-25 | 2096-11-20 |  |  | 19d | Rakuten |  |  | Not started |  | 1221 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2096-10-25 | 2096-11-20 | 0
MC5.1.2.10.2.14 - Design of CMDB parameters' | 2096-11-21 | 2096-12-17 |  |  | 19d | Rakuten |  |  | Not started |  | 1222 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2096-11-21 | 2096-12-17 | 0
MC5.1.2.10.2.15 - Design of day-0 configuration parameters' | 2096-12-18 | 2097-01-11 |  |  | 19d | Rakuten |  |  | Not started |  | 1223 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2096-12-18 | 2097-01-11 | 0
MC5.1.2.10.2.16 - Design of IP schema' | 2097-01-14 | 2097-02-07 |  |  | 19d | Rakuten |  |  | Not started |  | 1224 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2097-01-14 | 2097-02-07 | 0
MC5.1.2.10.2.17 - Design of host name and application naming convention' | 2097-02-08 | 2097-03-06 |  |  | 19d | Rakuten |  |  | Not started |  | 1225 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2097-02-08 | 2097-03-06 | 0
MC5.1.2.10.2.18 - Design of FQDN registration with DNS' | 2097-03-07 | 2097-04-02 |  |  | 19d | Rakuten |  |  | Not started |  | 1226 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2097-03-07 | 2097-04-02 | 0
MC5.1.2.10.2.20 - Design of security model integration' | 2097-04-03 | 2097-04-29 |  |  | 19d | Rakuten |  |  | Not started |  | 1227 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2097-04-03 | 2097-04-29 | 0
MC5.1.2.10.2.21 - Design of day-1 configuration push mechanism' | 2097-04-30 | 2097-05-24 |  |  | 19d | Rakuten |  |  | Not started |  | 1228 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2097-04-30 | 2097-05-24 | 0
MC5.1.2.10.2.22 - Design of day-2 configuration push mechanism' | 2097-05-27 | 2097-06-20 |  |  | 19d | Rakuten |  |  | Not started |  | 1229 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2097-05-27 | 2097-06-20 | 0
MC5.1.2.10.2.23 - Development of HELM charts/ Robin bundles' | 2097-06-21 | 2097-09-18 |  |  | 64d | Rakuten |  |  | Not started |  | 1230 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2097-06-21 | 2097-09-18 | 0
MC5.1.2.10.2.24 - Development of CMDB parameters' | 2097-09-19 | 2097-12-17 |  |  | 64d | Rakuten |  |  | Not started |  | 1231 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2097-09-19 | 2097-12-17 | 0
MC5.1.2.10.2.25 - Development of day-0 configuration parameters' | 2097-12-18 | 2098-03-17 |  |  | 64d | Rakuten |  |  | Not started |  | 1232 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2097-12-18 | 2098-03-17 | 0
MC5.1.2.10.2.26 - Development of IP schema' | 2098-03-18 | 2098-06-13 |  |  | 64d | Rakuten |  |  | Not started |  | 1233 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2098-03-18 | 2098-06-13 | 0
MC5.1.2.10.2.27 - Development of host name and application naming convention' | 2098-06-16 | 2098-09-11 |  |  | 64d | Rakuten |  |  | Not started |  | 1234 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2098-06-16 | 2098-09-11 | 0
MC5.1.2.10.2.28 - Development of FQDN registration with DNS' | 2098-09-12 | 2098-12-10 |  |  | 64d | Rakuten |  |  | Not started |  | 1235 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2098-09-12 | 2098-12-10 | 0
MC5.1.2.10.2.29 - Development of security model integration' | 2098-12-11 | 2099-03-10 |  |  | 64d | Rakuten |  |  | Not started |  | 1236 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2098-12-11 | 2099-03-10 | 0
MC5.1.2.10.2.30 - Development of day-1 configuration push mechanism' | 2099-03-11 | 2099-06-08 |  |  | 64d | Rakuten |  |  | Not started |  | 1237 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2099-03-11 | 2099-06-08 | 0
MC5.1.2.10.2.31 - Development of day-2 configuration push mechanism' | 2099-06-09 | 2099-09-04 |  |  | 64d | Rakuten |  |  | Not started |  | 1238 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2099-06-09 | 2099-09-04 | 0
MC5.1.2.10.2.32 - STG Deployment of AMF App Helm Charts and Robin Bundles & E2E Testing' | 2099-09-07 | 2099-10-22 |  |  | 34d | Rakuten |  |  | Not started |  | 1239 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2099-09-07 | 2099-10-22 | 0
MC5.1.2.10.2.33 - STG Deployment AMF App Instantiation & Day 0 Configuration & E2E Testing' | 2099-10-23 | 2099-12-09 |  |  | 34d | Rakuten |  |  | Not started |  | 1240 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2099-10-23 | 2099-12-09 | 0
MC5.1.2.10.2.34 - STG Deployment of Day 1 & Day 2 Config. Push Mechanism for AMF App & E2E Testing' | 2099-12-10 | 2100-01-26 |  |  | 34d | Rakuten |  |  | Not started |  | 1241 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2099-12-10 | 2100-01-26 | 0
MC5.1.2.10.2.35 - STG Deployment of IP Schema Templates & E2E Testing' | 2100-01-27 | 2100-03-15 |  |  | 34d | Rakuten |  |  | Not started |  | 1242 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2100-01-27 | 2100-03-15 | 0
MC5.1.2.10.2.36 - STG Deployment of host name templates and E2E Testing' | 2100-03-16 | 2100-04-30 |  |  | 34d | Rakuten |  |  | Not started |  | 1243 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2100-03-16 | 2100-04-30 | 0
MC5.1.2.10.2.37 - Production Deployment of AMF App Helm Charts, Robin Bundles and Day 0 Configuration' | 2100-05-03 | 2100-05-14 |  |  | 10d | Rakuten |  |  | Not started |  | 1244 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2100-05-03 | 2100-05-14 | 0
MC5.1.2.10.2.38 - Production Deployment of Day 1 & Day 2 Config Push Mechanism for AMF App' | 2100-05-17 | 2100-05-28 |  |  | 10d | Rakuten |  |  | Not started |  | 1245 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2100-05-17 | 2100-05-28 | 0
MC5.1.2.10.2.39 - Production Deployment of IP & Naming Templates for AMF App' | 2100-05-31 | 2100-06-11 |  |  | 10d | Rakuten |  |  | Not started |  | 1246 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2100-05-31 | 2100-06-11 | 0
MC5.1.2.10.3 - Use case 3: Onboarding CRDL CAT-D application' | 2100-06-14 | 2107-01-13 |  |  | 1719d | [5 empty] | 1247 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2100-06-14 | 2107-01-13 | 0
MC5.1.2.10.3.1 - Requirements gathering for HELM charts/ Robin bundles' | 2100-06-14 | 2100-09-09 |  |  | 64d | Rakuten |  |  | In progress | [5 empty] | No |  | SE&I: OSS & Orchestration |  |  | 2100-06-14 | 2100-09-09 | 0
MC5.1.2.10.3.2 - Requirements gathering for CMDB parameters finalization' | 2100-09-10 | 2100-12-08 |  |  | 64d | Rakuten |  |  | Not started |  | 1249 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2100-09-10 | 2100-12-08 | 0
MC5.1.2.10.3.3 - Requirements gathering for day-0 configuration parameters' | 2100-12-09 | 2101-03-08 |  |  | 64d | Rakuten |  |  | Not started |  | 1250 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2100-12-09 | 2101-03-08 | 0
MC5.1.2.10.3.4 - Requirements gathering for IP schema finalization' | 2101-03-09 | 2101-06-06 |  |  | 64d | Rakuten |  |  | Not started |  | 1251 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2101-03-09 | 2101-06-06 | 0
MC5.1.2.10.3.5 - Requirements gathering for host name and application naming convention' | 2101-06-07 | 2101-11-29 |  |  | 126d | Rakuten |  |  | In Progress |  | 1252 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2101-06-07 | 2101-11-29 | 0
MC5.1.2.10.3.6 - Requirements gathering for FQDN registration with DNS' | 2101-11-30 | 2102-02-27 |  |  | 64d | Rakuten |  |  | In Progress |  | 1253 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2101-11-30 | 2102-02-27 | 0
MC5.1.2.10.3.7 - Requirements gathering for security model integration' | 2102-02-28 | 2102-05-26 |  |  | 64d | Rakuten |  |  | Not started |  | 1254 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2102-02-28 | 2102-05-26 | 0
MC5.1.2.10.3.8 - Requirements gathering for day-1 configuration push mechanism' | 2102-05-29 | 2102-08-24 |  |  | 64d | Rakuten |  |  | In Progress |  | 1255 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2102-05-29 | 2102-08-24 | 0
MC5.1.2.10.3.9 - Requirements gathering for day-2 configuration push mechanism' | 2102-08-25 | 2102-11-22 |  |  | 64d | Rakuten |  |  | In Progress |  | 1256 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2102-08-25 | 2102-11-22 | 0
MC5.1.2.10.3.10 - Design of HELM charts/ Robin bundles' | 2102-11-23 | 2102-12-19 |  |  | 19d | Rakuten |  |  | Not started |  | 1257 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2102-11-23 | 2102-12-19 | 0
MC5.1.2.10.3.11 - Design of CMDB parameters' | 2102-12-20 | 2103-01-15 |  |  | 19d | Rakuten |  |  | Not started |  | 1258 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2102-12-20 | 2103-01-15 | 0
MC5.1.2.10.3.12 - Design of day-0 configuration parameters' | 2103-01-16 | 2103-02-09 |  |  | 19d | Rakuten |  |  | Not started |  | 1259 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2103-01-16 | 2103-02-09 | 0
MC5.1.2.10.3.13 - Design of IP schema' | 2103-02-12 | 2103-03-08 |  |  | 19d | Rakuten |  |  | Not started |  | 1260 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2103-02-12 | 2103-03-08 | 0
MC5.1.2.10.3.14 - Design of host name and application naming convention' | 2103-03-09 | 2103-07-03 |  |  | 83d | Rakuten |  |  | Not started |  | 1261 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2103-03-09 | 2103-07-03 | 0
MC5.1.2.10.3.15 - Design of FQDN registration with DNS' | 2103-07-04 | 2103-07-30 |  |  | 19d | Rakuten |  |  | Not started |  | 1262 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2103-07-04 | 2103-07-30 | 0
MC5.1.2.10.3.16 - Design of security model integration' | 2103-07-31 | 2103-07-31 |  |  | 1d | Rakuten |  |  | Not started |  | 1263 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2103-07-31 | 2103-07-31 | 0
MC5.1.2.10.3.17 - Design of day-1 configuration push mechanism' | 2103-08-01 | 2103-08-27 |  |  | 19d | Rakuten |  |  | Not started |  | 1264 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2103-08-01 | 2103-08-27 | 0
MC5.1.2.10.3.18 - Design of day-2 configuration push mechanism' | 2103-08-28 | 2103-09-21 |  |  | 19d | Rakuten |  |  | Not started |  | 1265 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2103-08-28 | 2103-09-21 | 0
MC5.1.2.10.3.19 - Development of HELM charts/ Robin bundles' | 2103-09-24 | 2104-04-22 |  |  | 152d | Rakuten |  |  | Not started |  | 1266 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2103-09-24 | 2104-04-22 | 0
MC5.1.2.10.3.20 - Development of CMDB parameters' | 2104-04-23 | 2104-07-21 |  |  | 64d | Rakuten |  |  | Not started |  | 1267 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2104-04-23 | 2104-07-21 | 0
MC5.1.2.10.3.21 - Development of day-0 configuration parameters' | 2104-07-22 | 2104-10-17 |  |  | 64d | Rakuten |  |  | Not started |  | 1268 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2104-07-22 | 2104-10-17 | 0
MC5.1.2.10.3.22 - Development of IP schema' | 2104-10-20 | 2105-01-15 |  |  | 64d | Rakuten |  |  | Not started |  | 1269 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2104-10-20 | 2105-01-15 | 0
MC5.1.2.10.3.23 - Development of host name and application naming convention' | 2105-01-16 | 2105-04-15 |  |  | 64d | Rakuten |  |  | Not started |  | 1270 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2105-01-16 | 2105-04-15 | 0
MC5.1.2.10.3.24 - Development of FQDN registration with DNS' | 2105-04-16 | 2105-07-14 |  |  | 64d | Rakuten |  |  | Not started |  | 1271 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2105-04-16 | 2105-07-14 | 0
MC5.1.2.10.3.25 - Development of security model integration' | 2105-07-15 | 2105-10-12 |  |  | 64d | Rakuten |  |  | Not started |  | 1272 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2105-07-15 | 2105-10-12 | 0
MC5.1.2.10.3.26 - Development of day-1 configuration push mechanism' | 2105-10-13 | 2106-01-08 |  |  | 64d | Rakuten |  |  | Not started |  | 1273 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2105-10-13 | 2106-01-08 | 0
MC5.1.2.10.3.27 - Development of day-2 configuration push mechanism' | 2106-01-11 | 2106-04-08 |  |  | 64d | Rakuten |  |  | Not started |  | 1274 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2106-01-11 | 2106-04-08 | 0
MC5.1.2.10.3.28 - STG Deployment of CRDL App Helm Charts and Robin Bundles & E2E Testing' | 2106-04-09 | 2106-05-26 |  |  | 34d | Rakuten |  |  | Not started |  | 1275 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2106-04-09 | 2106-05-26 | 0
MC5.1.2.10.3.29 - STG Deployment CRDL App Instantiation & Day 0 Configuration & E2E Testing' | 2106-05-27 | 2106-07-13 |  |  | 34d | Rakuten |  |  | Not started |  | 1276 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2106-05-27 | 2106-07-13 | 0
MC5.1.2.10.3.30 - STG Deployment of Day 1 & Day 2 Config. Push Mechanism for CRDL App & E2E Testing' | 2106-07-14 | 2106-08-30 |  |  | 34d | Rakuten |  |  | Not started |  | 1277 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2106-07-14 | 2106-08-30 | 0
MC5.1.2.10.3.31 - STG Deployment of IP Schema Templates & E2E Testing' | 2106-08-31 | 2106-10-15 |  |  | 34d | Rakuten |  |  | Not started |  | 1278 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2106-08-31 | 2106-10-15 | 0
MC5.1.2.10.3.32 - STG Deployment of host name templates and E2E Testing' | 2106-10-18 | 2106-12-02 |  |  | 34d | Rakuten |  |  | Not started |  | 1279 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2106-10-18 | 2106-12-02 | 0
MC5.1.2.10.3.33 - Production Deployment of CRDL App Helm Charts, Robin Bundles and Day 0 Configuration' | 2106-12-03 | 2106-12-16 |  |  | 10d | Rakuten |  |  | Not started |  | 1280 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2106-12-03 | 2106-12-16 | 0
MC5.1.2.10.3.34 - Production Deployment of Day 1 & Day 2 Config Push Mechanism for CRDL App' | 2106-12-17 | 2106-12-30 |  |  | 10d | Rakuten |  |  | Not started |  | 1281 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2106-12-17 | 2106-12-30 | 0
MC5.1.2.10.3.35 - Production Deployment of IP & Naming Templates for CRDL App' | 2106-12-31 | 2107-01-13 |  |  | 10d | Rakuten |  |  | Not started |  | 1282 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2106-12-31 | 2107-01-13 | 0
MC5.1.2.10.4 - Use case 4: Onboarding MCO CAT-E application' | 2107-01-14 | 2113-03-07 |  |  | 1603d | [5 empty] | 1283 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2107-01-14 | 2113-03-07 | 0
MC5.1.2.10.4.1 - Requirements gathering for HELM charts/ Robin bundles' | 2107-01-14 | 2107-07-08 |  |  | 126d | Rakuten |  |  | In Progress | [5 empty] | No |  | SE&I: OSS & Orchestration |  |  | 2107-01-14 | 2107-07-08 | 0
MC5.1.2.10.4.2 - Requirements gathering for CMDB parameters finalization' | 2107-07-11 | 2108-01-02 |  |  | 126d | Rakuten |  |  | Not started |  | 1285 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2107-07-11 | 2108-01-02 | 0
MC5.1.2.10.4.3 - Requirements gathering for day-0 configuration parameters' | 2108-01-03 | 2108-03-30 |  |  | 64d | Rakuten |  |  | Not started |  | 1286 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2108-01-03 | 2108-03-30 | 0
MC5.1.2.10.4.4 - Requirements gathering for IP schema finalization' | 2108-04-02 | 2108-06-28 |  |  | 64d | Rakuten |  |  | Not started |  | 1287 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2108-04-02 | 2108-06-28 | 0
MC5.1.2.10.4.5 - Requirements gathering for host name and application naming convention' | 2108-06-29 | 2108-09-26 |  |  | 64d | Rakuten |  |  | In Progress |  | 1288 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2108-06-29 | 2108-09-26 | 0
MC5.1.2.10.4.6 - Requirements gathering for FQDN registration with DNS' | 2108-09-27 | 2108-12-25 |  |  | 64d | Rakuten |  |  | In Progress |  | 1289 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2108-09-27 | 2108-12-25 | 0
MC5.1.2.10.4.7 - Requirements gathering for security model integration' | 2108-12-26 | 2109-03-25 |  |  | 64d | Rakuten |  |  | Not started |  | 1290 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2108-12-26 | 2109-03-25 | 0
MC5.1.2.10.4.8 - Requirements gathering for day-1 configuration push mechanism' | 2109-03-26 | 2109-06-21 |  |  | 64d | Rakuten |  |  | Not started |  | 1291 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2109-03-26 | 2109-06-21 | 0
MC5.1.2.10.4.9 - Requirements gathering for day-2 configuration push mechanism' | 2109-06-24 | 2109-09-19 |  |  | 64d | Rakuten |  |  | Not started |  | 1292 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2109-06-24 | 2109-09-19 | 0
MC5.1.2.10.4.10 - Design of HELM charts/ Robin bundles' | 2109-09-20 | 2110-01-14 |  |  | 83d | Rakuten |  |  | Not started |  | 1293 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2109-09-20 | 2110-01-14 | 0
MC5.1.2.10.4.11 - Design of CMDB parameters' | 2110-01-15 | 2110-01-15 |  |  | 1d | Rakuten |  |  | Not started |  | 1294 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2110-01-15 | 2110-01-15 | 0
MC5.1.2.10.4.12 - Design of day-0 configuration parameters' | 2110-01-16 | 2110-01-16 |  |  | 1d | Rakuten |  |  | Not started |  | 1295 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2110-01-16 | 2110-01-16 | 0
MC5.1.2.10.4.13 - Design of IP schema' | 2110-01-17 | 2110-02-12 |  |  | 19d | Rakuten |  |  | Not started |  | 1296 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2110-01-17 | 2110-02-12 | 0
MC5.1.2.10.4.14 - Design of host name and application naming convention' | 2110-02-13 | 2110-02-13 |  |  | 1d | Rakuten |  |  | Not started |  | 1297 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2110-02-13 | 2110-02-13 | 0
MC5.1.2.10.4.15 - Design of FQDN registration with DNS' | 2110-02-14 | 2110-02-14 |  |  | 1d | Rakuten |  |  | Not started |  | 1298 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2110-02-14 | 2110-02-14 | 0
MC5.1.2.10.4.16 - Design of security model integration' | 2110-02-17 | 2110-02-17 |  |  | 1d | Rakuten |  |  | Not started |  | 1299 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2110-02-17 | 2110-02-17 | 0
MC5.1.2.10.4.17 - Design of day-1 configuration push mechanism' | 2110-02-18 | 2110-03-14 |  |  | 19d | Rakuten |  |  | Not started |  | 1300 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2110-02-18 | 2110-03-14 | 0
MC5.1.2.10.4.18 - Design of day-2 configuration push mechanism' | 2110-03-17 | 2110-03-17 |  |  | 1d | Rakuten |  |  | Not started |  | 1301 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2110-03-17 | 2110-03-17 | 0
MC5.1.2.10.4.19 - Development of HELM charts/ Robin bundles' | 2110-03-18 | 2110-06-13 |  |  | 64d | Rakuten |  |  | Not started |  | 1302 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2110-03-18 | 2110-06-13 | 0
MC5.1.2.10.4.20 - Development of CMDB parameters' | 2110-06-16 | 2110-09-11 |  |  | 64d | Rakuten |  |  | Not started |  | 1303 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2110-06-16 | 2110-09-11 | 0
MC5.1.2.10.4.21 - Development of day-0 configuration parameters' | 2110-09-12 | 2110-12-10 |  |  | 64d | Rakuten |  |  | Not started |  | 1304 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2110-09-12 | 2110-12-10 | 0
MC5.1.2.10.4.22 - Development of IP schema' | 2110-12-11 | 2111-03-10 |  |  | 64d | Rakuten |  |  | Not started |  | 1305 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2110-12-11 | 2111-03-10 | 0
MC5.1.2.10.4.23 - Development of host name and application naming convention' | 2111-03-11 | 2111-06-08 |  |  | 64d | Rakuten |  |  | Not started |  | 1306 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2111-03-11 | 2111-06-08 | 0
MC5.1.2.10.4.24 - Development of FQDN registration with DNS' | 2111-06-09 | 2111-09-04 |  |  | 64d | Rakuten |  |  | Not started |  | 1307 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2111-06-09 | 2111-09-04 | 0
MC5.1.2.10.4.25 - Development of security model integration' | 2111-09-07 | 2111-12-03 |  |  | 64d | Rakuten |  |  | Not started |  | 1308 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2111-09-07 | 2111-12-03 | 0
MC5.1.2.10.4.26 - Development of day-1 configuration push mechanism' | 2111-12-04 | 2112-03-02 |  |  | 64d | Rakuten |  |  | Not started |  | 1309 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2111-12-04 | 2112-03-02 | 0
MC5.1.2.10.4.27 - Development of day-2 configuration push mechanism' | 2112-03-03 | 2112-05-31 |  |  | 64d | Rakuten |  |  | Not started |  | 1310 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2112-03-03 | 2112-05-31 | 0
MC5.1.2.10.4.28 - STG Deployment of MCO App Helm Charts and Robin Bundles & E2E Testing' | 2112-06-01 | 2112-07-18 |  |  | 34d | Rakuten |  |  | Not started |  | 1311 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2112-06-01 | 2112-07-18 | 0
MC5.1.2.10.4.29 - STG Deployment HSS App Instantiation & Day 0 Configuration & E2E Testing' | 2112-07-19 | 2112-09-02 |  |  | 34d | Rakuten |  |  | Not started |  | 1312 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2112-07-19 | 2112-09-02 | 0
MC5.1.2.10.4.30 - STG Deployment of Day 1 & Day 2 Config. Push Mechanism for HSS App & E2E Testing' | 2112-09-05 | 2112-10-20 |  |  | 34d | Rakuten |  |  | Not started |  | 1313 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2112-09-05 | 2112-10-20 | 0
MC5.1.2.10.4.31 - STG Deployment of IP Schema Templates & E2E Testing' | 2112-10-21 | 2112-12-07 |  |  | 34d | Rakuten |  |  | Not started |  | 1314 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2112-10-21 | 2112-12-07 | 0
MC5.1.2.10.4.32 - STG Deployment of host name templates and E2E Testing' | 2112-12-08 | 2113-01-24 |  |  | 34d | Rakuten |  |  | Not started |  | 1315 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2112-12-08 | 2113-01-24 | 0
MC5.1.2.10.4.33 - Production Deployment of HSS App Helm Charts, Robin Bundles and Day 0 Configuration' | 2113-01-25 | 2113-02-07 |  |  | 10d | Rakuten |  |  | Not started |  | 1316 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2113-01-25 | 2113-02-07 | 0
MC5.1.2.10.4.34 - Production Deployment of Day 1 & Day 2 Config Push Mechanism for HSS App' | 2113-02-08 | 2113-02-21 |  |  | 10d | Rakuten |  |  | Not started |  | 1317 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2113-02-08 | 2113-02-21 | 0
MC5.1.2.10.4.35 - Production Deployment of IP & Naming Templates for HSS App' | 2113-02-22 | 2113-03-07 |  |  | 10d | Rakuten |  |  | Not started |  | 1318 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2113-02-22 | 2113-03-07 | 0
MC5.1.2.10.5 - Use case 5: Onboarding MCTIL Management application' | 2113-03-08 | 2119-01-06 |  |  | 1523d | [5 empty] | 1319 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2113-03-08 | 2119-01-06 | 0
MC5.1.2.10.5.1 - Requirements gathering for HELM charts/ Robin bundles' | 2113-03-08 | 2113-06-05 |  |  | 64d | Rakuten |  |  | In Progress | [5 empty] | No |  | SE&I: OSS & Orchestration |  |  | 2113-03-08 | 2113-06-05 | 0
MC5.1.2.10.5.2 - Requirements gathering for CMDB parameters finalization' | 2113-06-06 | 2113-09-01 |  |  | 64d | Rakuten |  |  | Not started |  | 1321 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2113-06-06 | 2113-09-01 | 0
MC5.1.2.10.5.3 - Requirements gathering for day-0 configuration parameters' | 2113-09-04 | 2113-11-30 |  |  | 64d | Rakuten |  |  | Not started |  | 1322 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2113-09-04 | 2113-11-30 | 0
MC5.1.2.10.5.4 - Requirements gathering for IP schema finalization' | 2113-12-01 | 2114-02-28 |  |  | 64d | Rakuten |  |  | Not started |  | 1323 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2113-12-01 | 2114-02-28 | 0
MC5.1.2.10.5.5 - Requirements gathering for host name and application naming convention' | 2114-03-01 | 2114-05-29 |  |  | 64d | Rakuten |  |  | In Progress |  | 1324 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2114-03-01 | 2114-05-29 | 0
MC5.1.2.10.5.6 - Requirements gathering for FQDN registration with DNS' | 2114-05-30 | 2114-08-27 |  |  | 64d | Rakuten |  |  | In Progress |  | 1325 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2114-05-30 | 2114-08-27 | 0
MC5.1.2.10.5.7 - Requirements gathering for security model integration' | 2114-08-28 | 2114-11-23 |  |  | 64d | Rakuten |  |  | Not started |  | 1326 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2114-08-28 | 2114-11-23 | 0
MC5.1.2.10.5.8 - Requirements gathering for day-1 configuration push mechanism' | 2114-11-26 | 2115-02-21 |  |  | 64d | Rakuten |  |  | In Progress |  | 1327 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2114-11-26 | 2115-02-21 | 0
MC5.1.2.10.5.9 - Requirements gathering for day-2 configuration push mechanism' | 2115-02-22 | 2115-05-22 |  |  | 64d | Rakuten |  |  | In Progress |  | 1328 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2115-02-22 | 2115-05-22 | 0
MC5.1.2.10.5.10 - Design of HELM charts/ Robin bundles' | 2115-05-23 | 2115-06-18 |  |  | 19d | Rakuten |  |  | Not started |  | 1329 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2115-05-23 | 2115-06-18 | 0
MC5.1.2.10.5.11 - Design of CMDB parameters' | 2115-06-19 | 2115-07-15 |  |  | 19d | Rakuten |  |  | Not started |  | 1330 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2115-06-19 | 2115-07-15 | 0
MC5.1.2.10.5.12 - Design of day-0 configuration parameters' | 2115-07-16 | 2115-08-09 |  |  | 19d | Rakuten |  |  | Not started |  | 1331 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2115-07-16 | 2115-08-09 | 0
MC5.1.2.10.5.13 - Design of IP schema' | 2115-08-12 | 2115-09-05 |  |  | 19d | Rakuten |  |  | Not started |  | 1332 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2115-08-12 | 2115-09-05 | 0
MC5.1.2.10.5.14 - Design of host name and application naming convention' | 2115-09-06 | 2115-10-02 |  |  | 19d | Rakuten |  |  | Not started |  | 1333 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2115-09-06 | 2115-10-02 | 0
MC5.1.2.10.5.15 - Design of FQDN registration with DNS' | 2115-10-03 | 2115-10-29 |  |  | 19d | Rakuten |  |  | Not started |  | 1334 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2115-10-03 | 2115-10-29 | 0
MC5.1.2.10.5.16 - Design of security model integration' | 2115-10-30 | 2115-11-25 |  |  | 19d | Rakuten |  |  | Not started |  | 1335 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2115-10-30 | 2115-11-25 | 0
MC5.1.2.10.5.17 - Design of day-1 configuration push mechanism' | 2115-11-26 | 2115-12-20 |  |  | 19d | Rakuten |  |  | Not started |  | 1336 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2115-11-26 | 2115-12-20 | 0
MC5.1.2.10.5.18 - Design of day-2 configuration push mechanism' | 2115-12-23 | 2116-01-16 |  |  | 19d | Rakuten |  |  | Not started |  | 1337 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2115-12-23 | 2116-01-16 | 0
MC5.1.2.10.5.19 - Development of HELM charts/ Robin bundles' | 2116-01-17 | 2116-04-15 |  |  | 64d | Rakuten |  |  | Not started |  | 1338 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2116-01-17 | 2116-04-15 | 0
MC5.1.2.10.5.20 - Development of CMDB parameters' | 2116-04-16 | 2116-07-14 |  |  | 64d | Rakuten |  |  | Not started |  | 1339 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2116-04-16 | 2116-07-14 | 0
MC5.1.2.10.5.21 - Development of day-0 configuration parameters' | 2116-07-15 | 2116-10-12 |  |  | 64d | Rakuten |  |  | Not started |  | 1340 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2116-07-15 | 2116-10-12 | 0
MC5.1.2.10.5.22 - Development of IP schema' | 2116-10-13 | 2117-01-08 |  |  | 64d | Rakuten |  |  | Not started |  | 1341 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2116-10-13 | 2117-01-08 | 0
MC5.1.2.10.5.23 - Development of host name and application naming convention' | 2117-01-11 | 2117-04-08 |  |  | 64d | Rakuten |  |  | Not started |  | 1342 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2117-01-11 | 2117-04-08 | 0
MC5.1.2.10.5.24 - Development of FQDN registration with DNS' | 2117-04-09 | 2117-07-07 |  |  | 64d | Rakuten |  |  | Not started |  | 1343 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2117-04-09 | 2117-07-07 | 0
MC5.1.2.10.5.25 - Development of security model integration' | 2117-07-08 | 2117-10-05 |  |  | 64d | Rakuten |  |  | Not started |  | 1344 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2117-07-08 | 2117-10-05 | 0
MC5.1.2.10.5.26 - Development of day-1 configuration push mechanism' | 2117-10-06 | 2118-01-03 |  |  | 64d | Rakuten |  |  | Not started |  | 1345 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2117-10-06 | 2118-01-03 | 0
MC5.1.2.10.5.27 - Development of day-2 configuration push mechanism' | 2118-01-04 | 2118-04-01 |  |  | 64d | Rakuten |  |  | Not started |  | 1346 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2118-01-04 | 2118-04-01 | 0
MC5.1.2.10.5.28 - STG Deployment of HSS App Helm Charts and Robin Bundles & E2E Testing' | 2118-04-04 | 2118-05-19 |  |  | 34d | Rakuten |  |  | Not started |  | 1347 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2118-04-04 | 2118-05-19 | 0
MC5.1.2.10.5.29 - STG Deployment HSS App Instantiation & Day 0 Configuration & E2E Testing' | 2118-05-20 | 2118-07-06 |  |  | 34d | Rakuten |  |  | Not started |  | 1348 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2118-05-20 | 2118-07-06 | 0
MC5.1.2.10.5.30 - STG Deployment of Day 1 & Day 2 Config. Push Mechanism for HSS App & E2E Testing' | 2118-07-07 | 2118-08-23 |  |  | 34d | Rakuten |  |  | Not started |  | 1349 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2118-07-07 | 2118-08-23 | 0
MC5.1.2.10.5.31 - STG Deployment of IP Schema Templates & E2E Testing' | 2118-08-24 | 2118-10-10 |  |  | 34d | Rakuten |  |  | Not started |  | 1350 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2118-08-24 | 2118-10-10 | 0
MC5.1.2.10.5.32 - STG Deployment of host name templates and E2E Testing' | 2118-10-11 | 2118-11-25 |  |  | 34d | Rakuten |  |  | Not started |  | 1351 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2118-10-11 | 2118-11-25 | 0
MC5.1.2.10.5.33 - Production Deployment of HSS App Helm Charts, Robin Bundles and Day 0 Configuration' | 2118-11-28 | 2118-12-09 |  |  | 10d | Rakuten |  |  | Not started |  | 1352 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2118-11-28 | 2118-12-09 | 0
MC5.1.2.10.5.34 - Production Deployment of Day 1 & Day 2 Config Push Mechanism for HSS App' | 2118-12-12 | 2118-12-23 |  |  | 10d | Rakuten |  |  | Not started |  | 1353 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2118-12-12 | 2118-12-23 | 0
MC5.1.2.10.5.35 - Production Deployment of IP & Naming Templates for HSS App' | 2118-12-26 | 2119-01-06 |  |  | 10d | Rakuten |  |  | Not started |  | 1354 |  |  |  | Yes |  | SE&I: OSS & Orchestration |  |  | 2118-12-26 | 2119-01-06 | 0
MC5.1.2.10.6 - Use case 6: Onboarding mCAS Management application' | 2119-01-09 | 2124-11-08 |  |  | 1523d | [5 empty] | 1355 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2119-01-09 | 2124-11-08 | 0
MC5.1.2.10.6.1 - Requirements gathering for HELM charts/ Robin bundles' | 2119-01-09 | 2119-04-06 |  |  | 64d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2119-01-09 | 2119-04-06 | 0
MC5.1.2.10.6.2 - Requirements gathering for CMDB parameters finalization' | 2119-04-07 | 2119-07-05 |  |  | 64d | [5 empty] | 1357 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2119-04-07 | 2119-07-05 | 0
MC5.1.2.10.6.3 - Requirements gathering for day-0 configuration parameters' | 2119-07-06 | 2119-10-03 |  |  | 64d | [5 empty] | 1358 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2119-07-06 | 2119-10-03 | 0
MC5.1.2.10.6.4 - Requirements gathering for IP schema finalization' | 2119-10-04 | 2120-01-01 |  |  | 64d | [5 empty] | 1359 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2119-10-04 | 2120-01-01 | 0
MC5.1.2.10.6.5 - Requirements gathering for host name and application naming convention' | 2120-01-02 | 2120-03-29 |  |  | 64d | [5 empty] | 1360 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2120-01-02 | 2120-03-29 | 0
MC5.1.2.10.6.6 - Requirements gathering for FQDN registration with DNS' | 2120-04-01 | 2120-06-27 |  |  | 64d | [5 empty] | 1361 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2120-04-01 | 2120-06-27 | 0
MC5.1.2.10.6.7 - Requirements gathering for security model integration' | 2120-06-28 | 2120-09-25 |  |  | 64d | [5 empty] | 1362 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2120-06-28 | 2120-09-25 | 0
MC5.1.2.10.6.8 - Requirements gathering for day-1 configuration push mechanism' | 2120-09-26 | 2120-12-24 |  |  | 64d | [5 empty] | 1363 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2120-09-26 | 2120-12-24 | 0
MC5.1.2.10.6.9 - Requirements gathering for day-2 configuration push mechanism' | 2120-12-25 | 2121-03-24 |  |  | 64d | [5 empty] | 1364 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2120-12-25 | 2121-03-24 | 0
MC5.1.2.10.6.10 - Design of HELM charts/ Robin bundles' | 2121-03-25 | 2121-04-18 |  |  | 19d | [5 empty] | 1365 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2121-03-25 | 2121-04-18 | 0
MC5.1.2.10.6.11 - Design of CMDB parameters' | 2121-04-21 | 2121-05-15 |  |  | 19d | [5 empty] | 1366 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2121-04-21 | 2121-05-15 | 0
MC5.1.2.10.6.12 - Design of day-0 configuration parameters' | 2121-05-16 | 2121-06-11 |  |  | 19d | [5 empty] | 1367 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2121-05-16 | 2121-06-11 | 0
MC5.1.2.10.6.13 - Design of IP schema' | 2121-06-12 | 2121-07-08 |  |  | 19d | [5 empty] | 1368 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2121-06-12 | 2121-07-08 | 0
MC5.1.2.10.6.14 - Design of host name and application naming convention' | 2121-07-09 | 2121-08-04 |  |  | 19d | [5 empty] | 1369 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2121-07-09 | 2121-08-04 | 0
MC5.1.2.10.6.15 - Design of FQDN registration with DNS' | 2121-08-05 | 2121-08-29 |  |  | 19d | [5 empty] | 1370 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2121-08-05 | 2121-08-29 | 0
MC5.1.2.10.6.16 - Design of security model integration' | 2121-09-01 | 2121-09-25 |  |  | 19d | [5 empty] | 1371 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2121-09-01 | 2121-09-25 | 0
MC5.1.2.10.6.17 - Design of day-1 configuration push mechanism' | 2121-09-26 | 2121-10-22 |  |  | 19d | [5 empty] | 1372 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2121-09-26 | 2121-10-22 | 0
MC5.1.2.10.6.18 - Design of day-2 configuration push mechanism' | 2121-10-23 | 2121-11-18 |  |  | 19d | [5 empty] | 1373 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2121-10-23 | 2121-11-18 | 0
MC5.1.2.10.6.19 - Development of HELM charts/ Robin bundles' | 2121-11-19 | 2122-02-16 |  |  | 64d | [5 empty] | 1374 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2121-11-19 | 2122-02-16 | 0
MC5.1.2.10.6.20 - Development of CMDB parameters' | 2122-02-17 | 2122-05-15 |  |  | 64d | [5 empty] | 1375 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2122-02-17 | 2122-05-15 | 0
MC5.1.2.10.6.21 - Development of day-0 configuration parameters' | 2122-05-18 | 2122-08-13 |  |  | 64d | [5 empty] | 1376 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2122-05-18 | 2122-08-13 | 0
MC5.1.2.10.6.22 - Development of IP schema' | 2122-08-14 | 2122-11-11 |  |  | 64d | [5 empty] | 1377 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2122-08-14 | 2122-11-11 | 0
MC5.1.2.10.6.23 - Development of host name and application naming convention' | 2122-11-12 | 2123-02-09 |  |  | 64d | [5 empty] | 1378 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2122-11-12 | 2123-02-09 | 0
MC5.1.2.10.6.24 - Development of FQDN registration with DNS' | 2123-02-10 | 2123-05-10 |  |  | 64d | [5 empty] | 1379 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2123-02-10 | 2123-05-10 | 0
MC5.1.2.10.6.25 - Development of security model integration' | 2123-05-11 | 2123-08-06 |  |  | 64d | [5 empty] | 1380 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2123-05-11 | 2123-08-06 | 0
MC5.1.2.10.6.26 - Development of day-1 configuration push mechanism' | 2123-08-09 | 2123-11-04 |  |  | 64d | [5 empty] | 1381 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2123-08-09 | 2123-11-04 | 0
MC5.1.2.10.6.27 - Development of day-2 configuration push mechanism' | 2123-11-05 | 2124-02-02 |  |  | 64d | [5 empty] | 1382 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2123-11-05 | 2124-02-02 | 0
MC5.1.2.10.6.28 - STG Deployment of HSS App Helm Charts and Robin Bundles & E2E Testing' | 2124-02-03 | 2124-03-21 |  |  | 34d | [5 empty] | 1383 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2124-02-03 | 2124-03-21 | 0
MC5.1.2.10.6.29 - STG Deployment HSS App Instantiation & Day 0 Configuration & E2E Testing' | 2124-03-22 | 2124-05-08 |  |  | 34d | [5 empty] | 1384 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2124-03-22 | 2124-05-08 | 0
MC5.1.2.10.6.30 - STG Deployment of Day 1 & Day 2 Config. Push Mechanism for HSS App & E2E Testing' | 2124-05-09 | 2124-06-23 |  |  | 34d | [5 empty] | 1385 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2124-05-09 | 2124-06-23 | 0
MC5.1.2.10.6.31 - STG Deployment of IP Schema Templates & E2E Testing' | 2124-06-26 | 2124-08-10 |  |  | 34d | [5 empty] | 1386 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2124-06-26 | 2124-08-10 | 0
MC5.1.2.10.6.32 - STG Deployment of host name templates and E2E Testing' | 2124-08-11 | 2124-09-27 |  |  | 34d | [5 empty] | 1387 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2124-08-11 | 2124-09-27 | 0
MC5.1.2.10.6.33 - Production Deployment of HSS App Helm Charts, Robin Bundles and Day 0 Configuration' | 2124-09-28 | 2124-10-11 |  |  | 10d | [5 empty] | 1388 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2124-09-28 | 2124-10-11 | 0
MC5.1.2.10.6.34 - Production Deployment of Day 1 & Day 2 Config Push Mechanism for HSS App' | 2124-10-12 | 2124-10-25 |  |  | 10d | [5 empty] | 1389 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2124-10-12 | 2124-10-25 | 0
MC5.1.2.10.6.35 - Production Deployment of IP & Naming Templates for HSS App' | 2124-10-26 | 2124-11-08 |  |  | 10d | [5 empty] | 1390 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2124-10-26 | 2124-11-08 | 0
MC5.1.2.11 - BSS M2 Enablement Use case 1 : Service Incident' | 2124-11-09 | 2128-08-13 |  |  | 982d | [5 empty] | 1391 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2124-11-09 | 2128-08-13 | 0
MC5.1.2.11.1 - Use case 1 : Service Incident' | 2124-11-09 | 2127-03-12 |  |  | 610d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2124-11-09 | 2127-03-12 | 0
MC5.1.2.11.1.1 - Service Incident - design document for Ticket Management'' | 2124-11-09 | 2124-11-17 | 2021-12-01 | 2021-12-09 | 7d | Rakuten | Tapas |  | Completed |  |  |  |  | design has been shared with 1&1 and waiting their feedback | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2124-11-09 | 2124-11-17 | 0
MC5.1.2.11.1.2 - Service Incident - Service Desk Ticket Mgmt - 1&1 BSS team to provide API to open incident/ticket' ' | 2124-11-20 | 2124-11-22 | 2021-12-09 | 2021-12-10 | 3d | 1&1 | BSS |  | In progress |  | 1394 |  |  | BSS Team | No | FWA | SE&I: OSS & Orchestration | No |  | 2124-11-20 | 2124-11-22 | 0
MC5.1.2.11.1.3 - Service Incident - Service Desk Ticket Mgmt - 1&1 to provide feedback about ticket API exposed by Rakuten'' | 2124-11-23 | 2124-11-27 | 2021-12-09 | 2021-12-10 | 3d | 1&1 | BSS |  | In progress |  | 1395 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2124-11-23 | 2124-11-27 | 0
MC5.1.2.11.1.4 - Service Incident - Update design document for Ticket Management based on 1&1 Feedback' | 2124-11-28 | 2124-12-11 | 2022-02-07 | 2022-02-20 | 10d | Rakuten | Tapas |  | Not started |  | 1396 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2124-11-28 | 2124-12-11 | 0
MC5.1.2.11.1.5 - Dependency on 'MG5.2.6 - Enable ITSM capabilities with MVP features'' | 2124-12-12 | 2124-12-12 |  |  | 1d | Rakuten | Tapas |  | Not started |  | 1397 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2124-12-12 | 2124-12-12 | 0
MC5.1.2.11.1.6 - External Dependency Service Desk Ticket master management for service desk applications configuration on Mainzlab (staging Env.)' | 2124-12-13 | 2124-12-13 |  |  | 1d | Rakuten | PMO |  |  |  | 1398 |  | Consumer | Application deployment is the prerequisit. |  |  | SE&I: OSS & Orchestration | No |  | 2124-12-13 | 2124-12-13 | 0
MC5.1.2.11.1.7 - Service Incident - Stablish Connectivity between Service desk Application and Service Now and Exchange APIs on Ticket management (Sand Box)' | 2124-12-14 | 2125-01-04 | 2022-02-21 | 2022-03-14 | 16d | 1&1 , Rakuten | BSS , SE&I: OSS & Orchestration |  | Not started |  | 1399 |  |  | Start date depends on inputs and Sprint cadance | No | FWA | SE&I: OSS & Orchestration | No |  | 2124-12-14 | 2125-01-04 | 0
MC5.1.2.11.1.8 - Service Incident - Push Tickets from Service desk to Service Now and Dev Testing (Sand Box)' | 2125-01-05 | 2125-01-26 | 2022-02-21 | 2022-03-14 | 16d | Rakuten | Tapas |  | Not started |  | 1400 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2125-01-05 | 2125-01-26 | 0
MC5.1.2.11.1.9 - Service Incident - Stablish Connectivity between Service desk Application and Service Now and Exchange APIs Mainz Lab' | 2125-01-29 | 2125-02-19 | 2022-03-14 | 2022-04-04 | 16d | Rakuten | Tapas |  | Not started |  | 1401 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2125-01-29 | 2125-02-19 | 0
MC5.1.2.11.1.10 - Service Incident - Push Tickets from Service desk to Service Now and Dev Testing on Mainz Lab' | 2125-02-20 | 2125-03-27 | 2022-03-14 | 2022-04-18 | 26d | Rakuten | Tapas |  | Not started |  | 1402 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2125-02-20 | 2125-03-27 | 0
MC5.1.2.11.1.11 - External dependency on QA E2E testing' | 2125-03-28 | 2125-03-28 |  |  | 1d | Rakuten | E2E QA |  |  |  | 1403 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2125-03-28 | 2125-03-28 | 0
MC5.1.2.11.1.12 - External Dependency Service Desk Ticket master management for service desk applications configuration' | 2125-03-29 | 2125-03-29 |  |  | 1d | Rakuten | PMO |  |  |  | 1404 |  | Consumer | Application deployment is the prerequisit. |  |  | SE&I: OSS & Orchestration | No |  | 2125-03-29 | 2125-03-29 | 0
MC5.1.2.11.1.13 - Service Incident - Stablish Connectivity between Service desk Application and Service Now and Exchange APIs in production'' | 2125-03-30 | 2125-03-30 |  |  | 1d | Rakuten | Tapas |  | Not started |  | 1405 |  |  | Start date after QA testing completion . End date: 1 Weeks Afte QA testing Completion date | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2125-03-30 | 2125-03-30 | 0
MC5.1.2.11.1.14 - Service Incident - Push Tickets from Service desk to Service Now and Dev Testing on Production' | 2125-04-02 | 2125-04-02 |  |  | 1d | Rakuten | Tapas |  | Not started |  | 1406 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2125-04-02 | 2125-04-02 | 0
MC5.1.2.11.1.15 - Service Incident - design document for Change Management'' | 2125-04-03 | 2125-05-24 | 2021-12-01 | 2022-01-22 | 38d | Rakuten | Satish Behera |  | In progress |  | 1407 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2125-04-03 | 2125-05-24 | 0
MC5.1.2.11.1.16 - Service Incident - Service Desk Ticket Mgmt - 1&1 BSS team to provide API to open Change Request' ' | 2125-05-25 | 2125-05-25 |  |  | 1d | 1&1 | BSS |  | In progress |  | 1408 |  |  | BSS Team | No | FWA | SE&I: OSS & Orchestration | No |  | 2125-05-25 | 2125-05-25 | 0
MC5.1.2.11.1.17 - Service Incident - Service Desk Ticket Mgmt - 1&1 to provide feedback about ticket API exposed by Rakuten'' | 2125-05-28 | 2125-05-28 |  |  | 1d | 1&1 | BSS |  | In progress |  | 1409 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2125-05-28 | 2125-05-28 | 0
MC5.1.2.11.1.18 - Service Incident - Update design document for Change Management based on 1&1 Feedback' | 2125-05-29 | 2125-05-29 |  |  | 1d | Rakuten | Tapas |  | Not started |  | 1410 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2125-05-29 | 2125-05-29 | 0
MC5.1.2.11.1.19 - Service Incident - Stablish Connectivity between Service desk Application and Service Now and Exchange APIs on Change Management (Sand Box)' | 2125-05-30 | 2125-05-30 |  |  | 1d | 1&1 , Rakuten | BSS , SE&I: OSS & Orchestration |  | Not started |  | 1411 |  |  | Start date depends on inputs and Sprint cadance | No | FWA | SE&I: OSS & Orchestration | No |  | 2125-05-30 | 2125-05-30 | 0
MC5.1.2.11.1.20 - Service Incident - Push Tickets from Service desk to Service Now on Change Management and Dev Testing (Sand Box)' | 2125-05-31 | 2125-05-31 |  |  | 1d | Rakuten | Tapas |  | Not started |  | 1412 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2125-05-31 | 2125-05-31 | 0
MC5.1.2.11.1.21 - Service Incident - Stablish Connectivity between Service desk Application and Service Now and Exchange on Change Management APIs Mainz Lab' | 2125-06-01 | 2125-06-01 |  |  | 1d | Rakuten | Tapas |  | Not started |  | 1413 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2125-06-01 | 2125-06-01 | 0
MC5.1.2.11.1.22 - Service Incident - Push Tickets from Service desk to Service Now on Change Management and Dev Testing on Mainz Lab' | 2125-06-04 | 2125-06-04 |  |  | 1d | Rakuten | Tapas |  | Not started |  | 1414 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2125-06-04 | 2125-06-04 | 0
MC5.1.2.11.1.23 - External dependency on QA E2E testing' | 2125-06-05 | 2125-06-05 |  |  | 1d | Rakuten | E2E QA |  |  |  | 1415 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2125-06-05 | 2125-06-05 | 0
MC5.1.2.11.1.24 - Service Incident - Stablish Connectivity between Service desk Application and Service Now and Exchange APIs on Change Management in production'' | 2125-06-06 | 2125-06-06 |  |  | 1d | Rakuten | Tapas |  | Not started |  | 1416 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2125-06-06 | 2125-06-06 | 0
MC5.1.2.11.1.25 - Service Incident - Push Tickets from Service desk to Service Now and Dev Testing on Change Management on Production' | 2125-06-07 | 2125-06-07 |  |  | 1d | Rakuten | Tapas |  | Not started |  | 1417 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2125-06-07 | 2125-06-07 | 0
MC5.1.2.11.1.26 - 'Service Incident - Clarification of scope of requirements for Performance and Fault Management'' | 2125-06-08 | 2125-08-30 | 2021-11-01 | 2022-01-21 | 60d | Rakuten | Shankar |  | Completed |  | 1418 |  |  | E2E requirement clarification/documents & definition of business logics awaited BSS team SIIFSR027,SIIFSR003 SIIFSR011 SIIFSR012 SIIFSR013 SIIFSR014 SIIFSR023 SIIFSR005/7.4 SIIFSR004/7.3 | No | FWA | SE&I: OSS & Orchestration | No |  | 2125-06-08 | 2125-08-30 | 0
MC5.1.2.11.1.27 - Service Incident - Fault & Performance Monitoring - RAN to provide alarms/counters/KPIs/formulas'' | 2125-08-31 | 2125-09-14 | 2022-03-01 | 2022-03-15 | 11d | Rakuten | Sandeep Gaur & Hemant |  | In progress |  | 1419 | Item belongs to external board, Item belongs to external board | Consumer | Check with Luca what is the ask | No | FWA | SE&I: OSS & Orchestration | No |  | 2125-08-31 | 2125-09-14 | 0
MC5.1.2.11.1.28 - Service Incident - Fault & Performance Monitoring - Core to provide alarms/counters/KPIs'' | 2125-09-17 | 2125-10-01 | 2021-11-01 | 2021-11-15 | 11d | Rakuten | Core engineering |  | In progress |  | 1420 |  |  | Shankar and azad to review the inputs with FCAPS team | No | FWA | SE&I: OSS & Orchestration | No |  | 2125-09-17 | 2125-10-01 | 0
MC5.1.2.11.1.29 - Service Incident - Design document for Performance and Fault Management'' | 2125-10-02 | 2125-11-13 | 2022-01-04 | 2022-02-15 | 31d | Rakuten | Shankar |  | In progress |  | 1421 |  |  | Shankar and azad to review the inputs with FCAPS team | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2125-10-02 | 2125-11-13 | 0
MC5.1.2.11.1.30 - Review the FCAPS integration dev testing results for RAN Monitoring ' | 2125-11-14 | 2125-11-14 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1422 |  |  | these must finish before 20 March | No |  | SE&I: OSS & Orchestration |  |  | 2125-11-14 | 2125-11-14 | 0
MC5.1.2.11.1.31 - Review the FCAPS integration dev testing results for Core Monitoring ' | 2125-11-15 | 2125-11-15 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1423 |  |  | '-'' | No |  | SE&I: OSS & Orchestration |  |  | 2125-11-15 | 2125-11-15 | 0
MC5.1.2.11.1.32 - Development of FM and PM features (SandBox)' | 2125-11-16 | 2125-11-30 |  |  | 11d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1424 |  |  | Sprint starts 21-March ' | No |  | SE&I: OSS & Orchestration |  |  | 2125-11-16 | 2125-11-30 | 0
MC5.1.2.11.1.33 - Development of FM and PM features (Staging)' | 2125-12-03 | 2125-12-03 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1425 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2125-12-03 | 2125-12-03 | 0
MC5.1.2.11.1.34 - QA E2E testing' | 2125-12-04 | 2125-12-04 |  |  | 1d | Rakuten | E2E QA |  |  |  | 1426 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2125-12-04 | 2125-12-04 | 0
MC5.1.2.11.1.35 - Development of FM and PM features (Production)' | 2125-12-05 | 2125-12-05 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1427 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2125-12-05 | 2125-12-05 | 0
MC5.1.2.11.1.36 - Service Incident - design document for probing'' | 2125-12-06 | 2126-03-01 | 2022-01-04 | 2022-03-30 | 62d | Rakuten | Petrit |  | Not started |  | 1428 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2125-12-06 | 2126-03-01 | 0
MC5.1.2.11.1.37 - Service Incident - Probing: features from RADCOM readiness (development & integration)' | 2126-03-04 | 2126-07-31 | 2021-12-01 | 2022-04-30 | 108d | Rakuten | Petrit |  | In progress |  | 1429 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2126-03-04 | 2126-07-31 | 0
MC5.1.2.11.1.38 - Service Incident - Information of Provisioning of traces from Altiostar'' | 2126-08-01 | 2126-12-30 | 2021-12-01 | 2022-04-30 | 108d | Altiostar |  |  | In progress |  | 1430 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2126-08-01 | 2126-12-30 | 0
MC5.1.2.11.1.39 - Service Incident - Design document for RAN Commander'' | 2126-12-31 | 2127-02-27 | 2021-12-01 | 2022-01-28 | 43d | Rakuten | Bharath |  | In progress |  | 1431 |  |  | Pending input from 1&1 | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2126-12-31 | 2127-02-27 | 0
MC5.1.2.11.1.40 - Service Incident - Approval of 1&1' | 2127-02-28 | 2127-03-07 |  |  | 6d | 1&1 | BSS |  | Not started |  | 1432 |  |  |  | No |  | SE&I: OSS & Orchestration |  |  | 2127-02-28 | 2127-03-07 | 0
MC5.1.2.11.1.41 - Service Incident - Configuration and Add plan layer into Ran Commander' | 2127-03-10 | 2127-03-10 |  |  | 1d | Rakuten | SE&I: OSS & Orchestration |  | In progress |  | 1433 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2127-03-10 | 2127-03-10 | 0
MC5.1.2.11.1.42 - External dependency on QA E2E testing' | 2127-03-11 | 2127-03-11 |  |  | 1d | Rakuten | E2E QA |  |  |  | 1434 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2127-03-11 | 2127-03-11 | 0
MC5.1.2.11.1.43 - Service Incident - Deployment of Coverage Check Features and Integrations of RAN Commander in production'' | 2127-03-12 | 2127-03-12 |  |  | 1d | Rakuten |  |  | Not started |  | 1435 |  |  | Start date after QA testing completion . End date: 3 Weeks Afte QA testing Completion date | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2127-03-12 | 2127-03-12 | 0
MC5.1.2.11.2 - Use case 2 : Coverage check Phase 1' | 2127-03-13 | 2128-08-13 |  |  | 372d | [5 empty] | 1436 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2127-03-13 | 2128-08-13 | 0
MC5.1.2.11.2.1 - Coverage check Phase 1 - Retrieve the planned coverage layer data from RAN team'' | 2127-03-13 | 2127-04-09 | 2021-12-20 | 2022-01-15 | 20d | Rakuten | RAN Engineering |  | Completed | [5 empty] | No | FWA | SE&I: OSS & Orchestration | No |  | 2127-03-13 | 2127-04-09 | 0
MC5.1.2.11.2.2 - Coverage check Phase 1 - Retrieve the sites plan data from RAN team'' | 2127-04-10 | 2127-05-07 | 2021-12-20 | 2022-01-15 | 20d | Rakuten | RAN Engineering |  | Completed |  | 1438 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2127-04-10 | 2127-05-07 | 0
MC5.1.2.11.2.3 - Coverage check Phase 1 - Retrieve the downlink throughput planned layer data from RAN team'' | 2127-05-08 | 2127-06-04 | 2021-12-20 | 2022-01-15 | 20d | Rakuten | RAN Engineering |  | Completed |  | 1439 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2127-05-08 | 2127-06-04 | 0
MC5.1.2.11.2.4 - Coverage check Phase 1 - Retrieve the uplink throughput planned layer data from RAN team'' | 2127-06-05 | 2127-07-02 | 2021-12-20 | 2022-01-15 | 20d | Rakuten | RAN Engineering |  | Completed |  | 1440 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2127-06-05 | 2127-07-02 | 0
MC5.1.2.11.2.5 - Coverage check Phase 1 - Retrieve the best cell coverage plot data from RAN team'' | 2127-07-03 | 2127-07-30 | 2021-12-20 | 2022-01-15 | 20d | Rakuten | RAN Engineering |  | Completed |  | 1441 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2127-07-03 | 2127-07-30 | 0
MC5.1.2.11.2.6 - Coverage check Phase 1 - design document for Coverage check Phase 1 capabilities, outdoor bandwidth KPIs inclduing aggregation and the API for neighboring cells'' | 2127-07-31 | 2127-09-17 | 2022-01-15 | 2022-03-05 | 35d | Rakuten | Bharath |  | In progress |  | 1442 |  |  | 1&1 review ongoing | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2127-07-31 | 2127-09-17 | 0
MC5.1.2.11.2.7 - Coverage check Phase 1 - design document for indoor, remaining outdoor and capacity KPIs including their aggregation'' | 2127-09-18 | 2127-11-05 | 2022-01-15 | 2022-03-05 | 35d | Rakuten | Bharath |  | In progress |  | 1443 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2127-09-18 | 2127-11-05 | 0
MC5.1.2.11.2.8 - Coverage check Phase 1 - development (development + dev testing) the planned coverage layer data integration'' | 2127-11-06 | 2127-12-31 | 2022-03-05 | 2022-04-30 | 40d | Rakuten | Bharath |  | Not started |  | 1444 |  |  |  | No | FWA | SE&I: OSS & Orchestration | No |  | 2127-11-06 | 2127-12-31 | 0
MC5.1.2.11.2.9 - Coverage check Phase 1 - Integrate the coverage layer into RAN Commander'' | 2128-01-01 | 2128-02-25 | 2022-03-05 | 2022-04-30 | 40d | Rakuten | Bharath |  | Not started |  | 1445 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2128-01-01 | 2128-02-25 | 0
MC5.1.2.11.2.10 - Coverage check Phase 1 - Integrate the sites plan data into RAN Commander'' | 2128-02-26 | 2128-04-21 | 2022-03-05 | 2022-04-30 | 40d | Rakuten | Bharath |  | Not started |  | 1446 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2128-02-26 | 2128-04-21 | 0
MC5.1.2.11.2.11 - Coverage check Phase 1 - API aggregation development' | 2128-04-22 | 2128-06-16 | 2022-03-05 | 2022-04-30 | 40d | Rakuten | Bharath |  | In progress |  | 1447 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2128-04-22 | 2128-06-16 | 0
MC5.1.2.11.2.12 - Deployment & integration of Coverage check Phase 1 features in Mainz Lab'' | 2128-06-17 | 2128-08-11 | 2022-03-05 | 2022-04-30 | 40d | Rakuten | Bharath |  | In progress |  | 1448 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2128-06-17 | 2128-08-11 | 0
MC5.1.2.11.2.13 - External dependency on QA E2E testing' | 2128-08-12 | 2128-08-12 |  |  | 1d | Rakuten | E2E QA |  |  |  | 1449 |  | Consumer |  |  |  | SE&I: OSS & Orchestration |  |  | 2128-08-12 | 2128-08-12 | 0
MC5.1.2.11.2.14 - Coverage check - Deployment of Coverage check Phase 1 Features and Integrations of RAN Commander in production'' | 2128-08-13 | 2128-08-13 |  |  | 1d | Rakuten | Bharath |  | Not started |  | 1450 |  |  | Start date after QA testing completion . End date: 3 Weeks Afte QA testing Completion date | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2128-08-13 | 2128-08-13 | 0
MC5.1.2.12 - Integration readiness between RCP applications and Versatel OSS' | 2128-08-16 | 2132-05-21 |  |  | 983d | [5 empty] | 1451 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2128-08-16 | 2132-05-21 | 0
MC5.1.2.12.1 - Fault Management Integration Approach & Documentation' | 2128-08-16 | 2128-10-15 | 2021-12-15 | 2022-02-15 | 45d | Rakuten | Federico |  | In progress |  |  |  |  | Prioritized for FUT FWA | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2128-08-16 | 2128-10-15 | 0
MC5.1.2.12.2 - Performance Management Integration Approach & Documentation' | 2128-10-18 | 2128-11-19 | 2022-01-12 | 2022-02-15 | 25d | Rakuten | Federico |  | In progress |  | 1453 |  |  | Prioritized for FUT FWA | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2128-10-18 | 2128-11-19 | 0
MC5.1.2.12.3 - Inventory Management & Topology Integration Approach & Documentation' | 2128-11-22 | 2128-12-30 | 2022-01-19 | 2022-02-28 | 29d | Rakuten | Federico |  | In progress |  | 1454 |  |  | Interface design discussions driven by Planning team (based on requirements from Build-to-Monitor modules); Prioritized for FUT FWA' | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2128-11-22 | 2128-12-30 | 0
MC5.1.2.12.4 - Ticket Management Integration Approach & Documentation' | 2128-12-31 | 2129-02-03 | 2022-02-09 | 2022-03-15 | 25d | Rakuten | Federico |  | In progress |  | 1455 |  |  | Prioritized for FUT FWA | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2128-12-31 | 2129-02-03 | 0
MC5.1.2.12.5 - Change Management Integration Approach & Documentation' | 2129-02-04 | 2129-03-01 | 2022-02-18 | 2022-03-15 | 18d | Rakuten | Federico |  | In progress |  | 1456 |  |  | Prioritized for FUT FWA | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2129-02-04 | 2129-03-01 | 0
MC5.1.2.12.6 - Knowledge Management Integration Approach & Documentation' | 2129-03-02 | 2129-04-04 | 2022-02-28 | 2022-03-31 | 24d | Rakuten | Federico |  | Not started |  | 1457 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2129-03-02 | 2129-04-04 | 0
MC5.1.2.12.7 - Access/Identity Management Integration Approach & Documentation' | 2129-04-05 | 2129-04-18 | 2022-03-28 | 2022-04-08 | 10d | Rakuten | Federico |  | Not started |  | 1458 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2129-04-05 | 2129-04-18 | 0
MC5.1.2.12.8 - Provisioning & Operational Automation Integration Approach & Documentation' | 2129-04-19 | 2129-05-11 | 2022-03-09 | 2022-03-31 | 17d | Rakuten | Federico |  | Not started |  | 1459 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2129-04-19 | 2129-05-11 | 0
MC5.1.2.12.9 - Design and development' | 2129-05-12 | 2131-05-14 |  |  | 523d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1460 |  |  | Depending on Process definition and operational requirements |  | FWA | SE&I: OSS & Orchestration | No |  | 2129-05-12 | 2131-05-14 | 0
MC5.1.2.12.9.1 Fault Management Integration: Development | 2129-05-12 | 2129-09-09 |  |  | 87d | Rakuten | [10 empty] | SE&I: OSS & Orchestration |  |  | 2129-05-12 | 2129-09-09 | 0
MC5.1.2.12.9.1.1 StableNet-RCP SNMP Interface (incl. heartbeat monitoring)' | 2129-05-12 | 2129-07-11 |  |  | 43d | Rakuten | [10 empty] | SE&I: OSS & Orchestration |  |  | 2129-05-12 | 2129-07-11 | 0
MC5.1.2.12.9.1.2 StableNet-RCP REST API Interface for reconciliation' | 2129-07-12 | 2129-09-08 |  |  | 43d | Rakuten |  |  |  |  | 1463 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2129-07-12 | 2129-09-08 | 0
MC5.1.2.12.9.1.3 Dependency to third-party: 1&1 Versatel's StableNet readiness ' | 2129-09-09 | 2129-09-09 |  |  | 1d | 1&1 |  |  |  |  | 1464 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2129-09-09 | 2129-09-09 | 0
MC5.1.2.12.9.2 Performance Management Integration: Development | 2129-09-12 | 2129-11-10 |  |  | 44d | Rakuten |  |  |  |  | 1465 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2129-09-12 | 2129-11-10 | 0
MC5.1.2.12.9.2.1 StableNet-RCP REST API Interface (incl. reconciliation)' | 2129-09-12 | 2129-11-09 |  |  | 43d | Rakuten | [10 empty] | SE&I: OSS & Orchestration |  |  | 2129-09-12 | 2129-11-09 | 0
MC5.1.2.12.9.2.2 Dependency to third-party: 1&1 Versatel's StableNet readiness ' | 2129-11-10 | 2129-11-10 |  |  | 1d | 1&1 |  |  |  |  | 1467 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2129-11-10 | 2129-11-10 | 0
MC5.1.2.12.9.3 Ticket Management Integration: Development | 2129-11-11 | 2130-05-10 |  |  | 129d | Rakuten |  |  |  |  | 1468 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2129-11-11 | 2130-05-10 | 0
MC5.1.2.12.9.3.1 API(s) to create/update tickets / ticket details in 1&1 Versatel ticket management system from Rakuten RCP ticket management system [via eBonding] | 2129-11-11 | 2130-01-10 |  |  | 43d | Rakuten | [10 empty] | SE&I: OSS & Orchestration |  |  | 2129-11-11 | 2130-01-10 | 0
MC5.1.2.12.9.3.2 API(s) to create/update tickets / ticket details in Rakuten RCP ticket management system from 1&1 Versatel ticket management system [via eBonding] | 2130-01-11 | 2130-03-10 |  |  | 43d | Rakuten |  |  |  |  | 1470 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2130-01-11 | 2130-03-10 | 0
MC5.1.2.12.9.3.3 Reconciliation/resynchronization mechanism for provided interfaces | 2130-03-13 | 2130-05-10 |  |  | 43d | Rakuten |  |  |  |  | 1471 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2130-03-13 | 2130-05-10 | 0
MC5.1.2.12.9.4 Change Management Integration: Development | 2130-05-11 | 2131-01-05 |  |  | 172d | [5 empty] | 1472 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2130-05-11 | 2131-01-05 | 0
MC5.1.2.12.9.4.1 API(s) to create/update CR/SR (+ CR/SR details) in 1&1 Versatel CR/SR management system from Rakuten RCP CR/SR management system ' | 2130-05-11 | 2130-07-10 |  |  | 43d | Rakuten | [10 empty] | SE&I: OSS & Orchestration |  |  | 2130-05-11 | 2130-07-10 | 0
MC5.1.2.12.9.4.2 API(s) to create/update CR/SR (+ CR/SR details) in Rakuten RCP CR/SR management system from 1&1 Versatel CR/SR management system' | 2130-07-11 | 2130-09-07 |  |  | 43d | Rakuten |  |  |  |  | 1474 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2130-07-11 | 2130-09-07 | 0
MC5.1.2.12.9.4.3 Reconciliation/resynchronization mechanism for provided interfaces | 2130-09-08 | 2130-11-07 |  |  | 43d | Rakuten |  |  |  |  | 1475 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2130-09-08 | 2130-11-07 | 0
MC5.1.2.12.9.4.4 Heartbeat monitoring mechanism for agreed interfaces (if applicable) | 2130-11-08 | 2131-01-05 |  |  | 43d | Rakuten |  |  |  |  | 1476 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2130-11-08 | 2131-01-05 | 0
MC5.1.2.12.9.5 Ext. Depedency: Process / Operational procedure & req. definition | 2131-01-08 | 2131-01-08 |  |  | 1d | Rakuten |  |  |  |  | 1477 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2131-01-08 | 2131-01-08 | 0
MC5.1.2.12.9.6 Inventory Management & Topology Integration: Development | 2131-01-09 | 2131-01-10 |  |  | 2d | Rakuten |  |  |  |  | 1478 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2131-01-09 | 2131-01-10 | 0
MC5.1.2.12.9.6.1 Dependency: Planning Team for FNT-RCP Site Manager interface ' | 2131-01-09 | 2131-01-09 |  |  | 1d | Rakuten | [10 empty] | SE&I: OSS & Orchestration |  |  | 2131-01-09 | 2131-01-09 | 0
MC5.1.2.12.9.6.2 Ext. Dependency: 1&1 Versatel FNT Readiness | 2131-01-10 | 2131-01-10 |  |  | 1d | Altiostar |  |  |  |  | 1480 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2131-01-10 | 2131-01-10 | 0
MC5.1.2.12.9.7 Configuration Management Integration: Development | 2131-01-11 | 2131-03-13 |  |  | 44d | [5 empty] | 1481 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2131-01-11 | 2131-03-13 | 0
MC5.1.2.12.9.8 Knowledge Management Integration: Development | 2131-03-14 | 2131-05-14 |  |  | 44d | [5 empty] | 1482 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2131-03-14 | 2131-05-14 | 0
MC5.1.2.12.10 - Deployment' | 2131-05-15 | 2132-05-21 |  |  | 267d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1483 |  |  | Depending on Process definition and operational requirements |  | FWA | SE&I: OSS & Orchestration | No |  | 2131-05-15 | 2132-05-21 | 0
MC5.1.2.12.10.1 Fault Management Integration: Deployment | 2131-05-15 | 2131-07-13 |  |  | 44d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2131-05-15 | 2131-07-13 | 0
MC5.1.2.12.10.1.1 StableNet-RCP SNMP Interface (incl. heartbeat monitoring)' | 2131-05-15 | 2131-06-13 |  |  | 22d | Rakuten | [10 empty] | SE&I: OSS & Orchestration |  |  | 2131-05-15 | 2131-06-13 | 0
MC5.1.2.12.10.1.2 StableNet-RCP REST API Interface for reconciliation' | 2131-06-14 | 2131-07-13 |  |  | 22d | Rakuten |  |  |  |  | 1486 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2131-06-14 | 2131-07-13 | 0
MC5.1.2.12.10.2 Performance Management Integration: Deployment | 2131-07-16 | 2131-08-14 |  |  | 22d | Rakuten |  |  |  |  | 1487 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2131-07-16 | 2131-08-14 | 0
MC5.1.2.12.10.2.1 StableNet-RCP REST API Interface (incl. reconciliation)' | 2131-07-16 | 2131-08-14 |  |  | 22d | Rakuten | [10 empty] | SE&I: OSS & Orchestration |  |  | 2131-07-16 | 2131-08-14 | 0
MC5.1.2.12.10.3 Ticket Management Integration: Deployment | 2131-08-15 | 2131-11-14 |  |  | 66d | Rakuten |  |  |  |  | 1489 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2131-08-15 | 2131-11-14 | 0
MC5.1.2.12.10.3.1 API(s) to create/update tickets / ticket details in 1&1 Versatel ticket management system from Rakuten RCP ticket management system [via eBonding] | 2131-08-15 | 2131-09-13 |  |  | 22d | Rakuten | [10 empty] | SE&I: OSS & Orchestration |  |  | 2131-08-15 | 2131-09-13 | 0
MC5.1.2.12.10.3.2 API(s) to create/update tickets / ticket details in Rakuten RCP ticket management system from 1&1 Versatel ticket management system [via eBonding] | 2131-09-14 | 2131-10-15 |  |  | 22d | Rakuten |  |  |  |  | 1491 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2131-09-14 | 2131-10-15 | 0
MC5.1.2.12.10.3.3 Reconciliation/resynchronization mechanism for provided interfaces | 2131-10-16 | 2131-11-14 |  |  | 22d | Rakuten |  |  |  |  | 1492 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2131-10-16 | 2131-11-14 | 0
MC5.1.2.12.10.4 Change Management Integration: Deployment | 2131-11-15 | 2132-03-17 |  |  | 88d | Rakuten |  |  |  |  | 1493 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2131-11-15 | 2132-03-17 | 0
MC5.1.2.12.10.4.1 API(s) to create/update CR/SR (+ CR/SR details) in 1&1 Versatel CR/SR management system from Rakuten RCP CR/SR management system ' | 2131-11-15 | 2131-12-14 |  |  | 22d | Rakuten | [10 empty] | SE&I: OSS & Orchestration |  |  | 2131-11-15 | 2131-12-14 | 0
MC5.1.2.12.10.4.2 API(s) to create/update CR/SR (+ CR/SR details) in Rakuten RCP CR/SR management system from 1&1 Versatel CR/SR management system' | 2131-12-17 | 2132-01-15 |  |  | 22d | Rakuten |  |  |  |  | 1495 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2131-12-17 | 2132-01-15 | 0
MC5.1.2.12.10.4.3 Reconciliation/resynchronization mechanism for provided interfaces | 2132-01-16 | 2132-02-14 |  |  | 22d | Rakuten |  |  |  |  | 1496 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2132-01-16 | 2132-02-14 | 0
MC5.1.2.12.10.4.4 Heartbeat monitoring mechanism for agreed interfaces (if applicable) | 2132-02-15 | 2132-03-17 |  |  | 22d | Rakuten |  |  |  |  | 1497 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2132-02-15 | 2132-03-17 | 0
MC5.1.2.12.10.5. Inventory Management & Topology Integration: Deployment | 2132-03-18 | 2132-03-18 |  |  | 1d | Rakuten |  |  |  |  | 1498 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2132-03-18 | 2132-03-18 | 0
MC5.1.2.12.10.5.1 Dependency: Planning Team for FNT-RCP Site Manager interface ' | 2132-03-18 | 2132-03-18 |  |  | 1d | Rakuten | [5 empty] | MC5.1.2.14.12.5 - Tested & Go Live' |  |  |  |  | SE&I: OSS & Orchestration |  |  | 2132-03-18 | 2132-03-18 | 0
MC5.1.2.12.10.6 Configuration Management Integration: Deployment | 2132-03-19 | 2132-04-18 |  |  | 23d | [5 empty] | 1500 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2132-03-19 | 2132-04-18 | 0
MC5.1.2.12.10.7 Knowledge Management Integration: Deployment | 2132-04-21 | 2132-05-21 |  |  | 23d | [5 empty] | 1501 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2132-04-21 | 2132-05-21 | 0
MC5.1.2.13 - Integration readiness between RCP applications and 3rd party Operation Integration' | 2132-05-22 | 2132-10-24 |  |  | 112d | [5 empty] | 1502 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2132-05-22 | 2132-10-24 | 0
MC5.1.2.13.1 - Approach and requirements definition' | 2132-05-22 | 2132-10-21 | 2021-11-01 | 2022-03-31 | 109d | Rakuten |  |  | Not started | [6 empty] | FWA | SE&I: OSS & Orchestration | No |  | 2132-05-22 | 2132-10-21 | 0
MC5.1.2.13.2 - Design and development' | 2132-10-22 | 2132-10-24 | 2022-03-31 | 2022-04-01 | 3d | Rakuten | SE&I: OSS & Orchestration |  | Not started |  | 1504 |  |  |  |  | FWA | SE&I: OSS & Orchestration | No |  | 2132-10-22 | 2132-10-24 | 0
MC5.1.2.7.2.4.12.20.28 - Development + Dev Testing for Inventory Reconciliation' | 2132-10-27 | 2133-01-26 |  |  | 66d | Rakuten |  |  | Not started |  | 1505 |  |  |  | Yes | FWA | SE&I: OSS & Orchestration | No |  | 2132-10-27 | 2133-01-26 | 0
MC5.1.2.14 - Integration readiness between RCP applications, 3rd party inventory tools and 3rd party Rollout Integration' | 2133-01-27 | 2133-11-23 |  |  | 215d | [5 empty] | 1506 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-01-27 | 2133-11-23 | 0
MC5.1.2.14.0 - Approach and initial requirements definition' | 2133-01-27 | 2133-06-26 | 2021-11-01 | 2022-03-31 | 109d | Rakuten | Dominik |  | Not started | [6 empty] | FWA | SE&I: OSS & Orchestration | No |  | 2133-01-27 | 2133-06-26 | 0
MC5.1.2.14.1 - Rakuten-Versatel: API RCP-FNT FR01: Friendly Sites' | 2133-06-29 | 2133-06-29 |  |  | 1d | [5 empty] | 1508 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-06-29 | 2133-06-29 | 0
MC5.1.2.14.1.1 - Parameters Shared' | 2133-06-29 | 2021-11-05 | 1970-01-01 | 2021-11-05 | 13528d | [11 empty] | SE&I: OSS & Orchestration
MC5.1.2.14.1.2 - Fields Confirmed' | 2133-06-29 | 2021-11-19 | 1970-01-01 | 2021-11-19 | 13538d | [5 empty] | 1510 | [5 empty] | SE&I: OSS & Orchestration
MC5.1.2.14.1.3 - Sample Query Shared' | 2133-06-29 | 2021-11-26 | 1970-01-01 | 2021-11-26 | 13543d | [5 empty] | 1511 | [5 empty] | SE&I: OSS & Orchestration
MC5.1.2.14.1.4 - Developed' | 2133-06-29 | 2022-01-14 | 1970-01-01 | 2022-01-14 | 13578d | [5 empty] | 1512 | [5 empty] | SE&I: OSS & Orchestration
MC5.1.2.14.1.5 - Tested & Go Live' | 2133-06-29 | 2133-06-29 |  |  | 1d | [5 empty] | 1513 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-06-29 | 2133-06-29 | 0
MC5.1.2.14.2 - Rakuten-Versatel: API RCP-FNT RF01: Nominals & HL Transport Planning' | 2133-06-30 | 2133-07-06 |  |  | 5d | [5 empty] | 1514 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-06-30 | 2133-07-06 | 0
MC5.1.2.14.2.1 - Parameters Shared' | 2133-06-30 | 2133-06-30 |  | 2022-01-28 | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-06-30 | 2133-06-30 | 0
MC5.1.2.14.2.2 - Fields Confirmed' | 2133-07-01 | 2133-07-01 |  | 2022-02-04 | 1d | [5 empty] | 1516 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-01 | 2133-07-01 | 0
MC5.1.2.14.2.3 - Sample Query Shared' | 2133-07-02 | 2133-07-02 |  |  | 1d | [5 empty] | 1517 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-02 | 2133-07-02 | 0
MC5.1.2.14.2.4 - Developed' | 2133-07-03 | 2133-07-03 |  |  | 1d | [5 empty] | 1518 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-03 | 2133-07-03 | 0
MC5.1.2.14.2.5 - Tested & Go Live' | 2133-07-06 | 2133-07-06 |  |  | 1d | [5 empty] | 1519 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-06 | 2133-07-06 | 0
MC5.1.2.14.3 - Rakuten-Versatel: API RCP-FNT RF03: Final Candidate & Executable Order' | 2133-07-07 | 2133-07-13 |  |  | 5d | [5 empty] | 1520 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-07 | 2133-07-13 | 0
MC5.1.2.14.3.1 - Parameters Shared' | 2133-07-07 | 2133-07-07 |  | 2022-02-18 | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-07 | 2133-07-07 | 0
MC5.1.2.14.3.2- Fields Confirmed' | 2133-07-08 | 2133-07-08 |  |  | 1d | [5 empty] | 1522 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-08 | 2133-07-08 | 0
MC5.1.2.14.3.3- Sample Query Shared' | 2133-07-09 | 2133-07-09 |  |  | 1d | [5 empty] | 1523 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-09 | 2133-07-09 | 0
MC5.1.2.14.3.4- Developed' | 2133-07-10 | 2133-07-10 |  |  | 1d | [5 empty] | 1524 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-10 | 2133-07-10 | 0
MC5.1.2.14.3.5 - Tested & Go Live' | 2133-07-13 | 2133-07-13 |  |  | 1d | [5 empty] | 1525 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-13 | 2133-07-13 | 0
MC5.1.2.14.4 - Rakuten-Versatel: API RCP-FNT RF04: EP Design' | 2133-07-14 | 2133-07-20 |  |  | 5d | [5 empty] | 1526 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-14 | 2133-07-20 | 0
MC5.1.2.14.4.1 - Parameters Shared' | 2133-07-14 | 2133-07-14 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-14 | 2133-07-14 | 0
MC5.1.2.14.4.2 - Fields Confirmed' | 2133-07-15 | 2133-07-15 |  |  | 1d | [5 empty] | 1528 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-15 | 2133-07-15 | 0
MC5.1.2.14.4.3 - Sample Query Shared' | 2133-07-16 | 2133-07-16 |  |  | 1d | [5 empty] | 1529 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-16 | 2133-07-16 | 0
MC5.1.2.14.4.4 - Developed' | 2133-07-17 | 2133-07-17 |  |  | 1d | [5 empty] | 1530 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-17 | 2133-07-17 | 0
MC5.1.2.14.4.5 - Tested & Go Live' | 2133-07-20 | 2133-07-20 |  |  | 1d | [5 empty] | 1531 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-20 | 2133-07-20 | 0
MC5.1.2.14.5 - Rakuten-Versatel: API RCP-FNT RF05 STOB' | 2133-07-21 | 2133-07-27 |  |  | 5d | [5 empty] | 1532 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-21 | 2133-07-27 | 0
MC5.1.2.14.5.1 - Parameters Shared' | 2133-07-21 | 2133-07-21 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-21 | 2133-07-21 | 0
MC5.1.2.14.5.2 - Fields Confirmed' | 2133-07-22 | 2133-07-22 |  |  | 1d | [5 empty] | 1534 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-22 | 2133-07-22 | 0
MC5.1.2.14.5.3 - Sample Query Shared' | 2133-07-23 | 2133-07-23 |  |  | 1d | [5 empty] | 1535 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-23 | 2133-07-23 | 0
MC5.1.2.14.5.4 - Developed' | 2133-07-24 | 2133-07-24 |  |  | 1d | [5 empty] | 1536 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-24 | 2133-07-24 | 0
MC5.1.2.14.5.5- Tested & Go Live' | 2133-07-27 | 2133-07-27 |  |  | 1d | [5 empty] | 1537 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-27 | 2133-07-27 | 0
MC5.1.2.14.6 - Rakuten-Versatel: API RCP-FNT FR03: Transport approvals & LLD' | 2133-07-28 | 2133-08-03 |  |  | 5d | [5 empty] | 1538 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-28 | 2133-08-03 | 0
MC5.1.2.14.6.1 - Parameters Shared' | 2133-07-28 | 2133-07-28 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-28 | 2133-07-28 | 0
MC5.1.2.14.6.2 - Fields Confirmed' | 2133-07-29 | 2133-07-29 |  |  | 1d | [5 empty] | 1540 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-29 | 2133-07-29 | 0
MC5.1.2.14.6.3 - Sample Query Shared' | 2133-07-30 | 2133-07-30 |  |  | 1d | [5 empty] | 1541 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-30 | 2133-07-30 | 0
MC5.1.2.14.6.4 - Developed' | 2133-07-31 | 2133-07-31 |  |  | 1d | [5 empty] | 1542 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-07-31 | 2133-07-31 | 0
MC5.1.2.14.6.5 - Tested & Go Live' | 2133-08-03 | 2133-08-03 |  |  | 1d | [5 empty] | 1543 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-03 | 2133-08-03 | 0
MC5.1.2.14.7 - Rakuten-Versatel: API RCP-FNT FR81: Equipment Library' | 2133-08-04 | 2133-08-10 |  |  | 5d | [5 empty] | 1544 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-04 | 2133-08-10 | 0
MC5.1.2.21.1 - Parameters Shared' | 2133-08-04 | 2133-08-04 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-04 | 2133-08-04 | 0
MC5.1.2.14.7.2 - Fields Confirmed' | 2133-08-05 | 2133-08-05 |  |  | 1d | [5 empty] | 1546 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-05 | 2133-08-05 | 0
MC5.1.2.14.7.3 - Sample Query Shared' | 2133-08-06 | 2133-08-06 |  |  | 1d | [5 empty] | 1547 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-06 | 2133-08-06 | 0
MC5.1.2.14.7.4 - Developed' | 2133-08-07 | 2133-08-07 |  |  | 1d | [5 empty] | 1548 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-07 | 2133-08-07 | 0
MC5.1.2.14.7.5 - Tested & Go Live' | 2133-08-10 | 2133-08-10 |  |  | 1d | [5 empty] | 1549 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-10 | 2133-08-10 | 0
MC5.1.2.14.8 - Rakuten-Versatel: API RCP-FNT FR82: New & existing CU/DU' | 2133-08-11 | 2133-08-17 |  |  | 5d | [5 empty] | 1550 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-11 | 2133-08-17 | 0
MC5.1.2.14.8.1 - Parameters Shared' | 2133-08-11 | 2133-08-11 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-11 | 2133-08-11 | 0
MC5.1.2.14.8.2 - Fields Confirmed' | 2133-08-12 | 2133-08-12 |  |  | 1d | [5 empty] | 1552 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-12 | 2133-08-12 | 0
MC5.1.2.14.8.3 - Sample Query Shared' | 2133-08-13 | 2133-08-13 |  |  | 1d | [5 empty] | 1553 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-13 | 2133-08-13 | 0
MC5.1.2.14.8.4 - Developed' | 2133-08-14 | 2133-08-14 |  |  | 1d | [5 empty] | 1554 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-14 | 2133-08-14 | 0
MC5.1.2.14.8.5 - Tested & Go Live' | 2133-08-17 | 2133-08-17 |  |  | 1d | [5 empty] | 1555 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-17 | 2133-08-17 | 0
MC5.1.2.14.9 - Rakuten-Versatel: API RCP-FNT FR83: HLD Transport' | 2133-08-18 | 2133-08-24 |  |  | 5d | [5 empty] | 1556 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-18 | 2133-08-24 | 0
MC5.1.2.14.9.1 - Parameters Shared' | 2133-08-18 | 2133-08-18 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-18 | 2133-08-18 | 0
MC5.1.2.14.9.2 - Fields Confirmed' | 2133-08-19 | 2133-08-19 |  |  | 1d | [5 empty] | 1558 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-19 | 2133-08-19 | 0
MC5.1.2.14.9.3 - Sample Query Shared' | 2133-08-20 | 2133-08-20 |  |  | 1d | [5 empty] | 1559 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-20 | 2133-08-20 | 0
MC5.1.2.14.9.4 - Developed' | 2133-08-21 | 2133-08-21 |  |  | 1d | [5 empty] | 1560 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-21 | 2133-08-21 | 0
MC5.1.2.14.9.5 - Tested & Go Live' | 2133-08-24 | 2133-08-24 |  |  | 1d | [5 empty] | 1561 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-24 | 2133-08-24 | 0
MC5.1.2.14.10 - Rakuten-Versatel: API RCP-FNT RF81: CP/DP Arch. Model' | 2133-08-25 | 2133-08-31 |  |  | 5d | [5 empty] | 1562 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-25 | 2133-08-31 | 0
MC5.1.2.14.10.1 - Parameters Shared' | 2133-08-25 | 2133-08-25 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-25 | 2133-08-25 | 0
MC5.1.2.14.10.2 - Fields Confirmed' | 2133-08-26 | 2133-08-26 |  |  | 1d | [5 empty] | 1564 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-26 | 2133-08-26 | 0
MC5.1.2.14.10.3 - Sample Query Shared' | 2133-08-27 | 2133-08-27 |  |  | 1d | [5 empty] | 1565 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-27 | 2133-08-27 | 0
MC5.1.2.14.10.4 - Developed' | 2133-08-28 | 2133-08-28 |  |  | 1d | [5 empty] | 1566 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-28 | 2133-08-28 | 0
MC5.1.2.14.10.5 - Tested & Go Live' | 2133-08-31 | 2133-08-31 |  |  | 1d | [5 empty] | 1567 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-08-31 | 2133-08-31 | 0
MC5.1.2.14.11 - Rakuten-Versatel: API RCP-FNT FR84: LLD Transport' | 2133-09-01 | 2133-09-07 |  |  | 5d | [5 empty] | 1568 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-01 | 2133-09-07 | 0
MC5.1.2.14.11.1 - Parameters Shared' | 2133-09-01 | 2133-09-01 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-01 | 2133-09-01 | 0
MC5.1.2.14.11.2 - Fields Confirmed' | 2133-09-02 | 2133-09-02 |  |  | 1d | [5 empty] | 1570 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-02 | 2133-09-02 | 0
MC5.1.2.14.11.3 - Sample Query Shared' | 2133-09-03 | 2133-09-03 |  |  | 1d | [5 empty] | 1571 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-03 | 2133-09-03 | 0
MC5.1.2.14.11.4 - Developed' | 2133-09-04 | 2133-09-04 |  |  | 1d | [5 empty] | 1572 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-04 | 2133-09-04 | 0
MC5.1.2.14.11.5 - Tested & Go Live' | 2133-09-07 | 2133-09-07 |  |  | 1d | [5 empty] | 1573 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-07 | 2133-09-07 | 0
MC5.1.2.14.12 - Rakuten-Versatel: API FNT-RCP SM- RCP IM FR80: Inventory Attributes for FM&PM' | 2133-09-08 | 2133-09-14 |  |  | 5d | [5 empty] | 1574 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-08 | 2133-09-14 | 0
MC5.1.2.14.12.1 - Parameters Shared' | 2133-09-08 | 2133-09-08 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-08 | 2133-09-08 | 0
MC5.1.2.14.12.2- Fields Confirmed' | 2133-09-09 | 2133-09-09 |  |  | 1d | [5 empty] | 1576 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-09 | 2133-09-09 | 0
MC5.1.2.14.12.3- Sample Query Shared' | 2133-09-10 | 2133-09-10 |  |  | 1d | [5 empty] | 1577 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-10 | 2133-09-10 | 0
MC5.1.2.14.12.4 - Developed' | 2133-09-11 | 2133-09-11 |  |  | 1d | [5 empty] | 1578 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-11 | 2133-09-11 | 0
MC5.1.2.14.12.5 - Tested & Go Live' | 2133-09-14 | 2133-09-14 |  |  | 1d | [5 empty] | 1579 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-14 | 2133-09-14 | 0
MC5.1.2.14.13 - Rakuten-Vantage: API RCP-TIMS RT01: RFDS S1-3' | 2133-09-15 | 2133-09-21 |  |  | 5d | [5 empty] | 1580 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-15 | 2133-09-21 | 0
MC5.1.2.14.13.1 - Parameters Shared' | 2133-09-15 | 2133-09-15 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-15 | 2133-09-15 | 0
MC5.1.2.14.13.2 - Fields Confirmed' | 2133-09-16 | 2133-09-16 |  |  | 1d | [5 empty] | 1582 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-16 | 2133-09-16 | 0
MC5.1.2.14.13.3 - Sample Query Shared' | 2133-09-17 | 2133-09-17 |  |  | 1d | [5 empty] | 1583 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-17 | 2133-09-17 | 0
MC5.1.2.14.13.4 - Developed' | 2133-09-18 | 2133-09-18 |  |  | 1d | [5 empty] | 1584 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-18 | 2133-09-18 | 0
MC5.1.2.14.13.5 - Tested & Go Live' | 2133-09-21 | 2133-09-21 |  |  | 1d | [5 empty] | 1585 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-21 | 2133-09-21 | 0
MC5.1.2.14.14 - Rakuten-Vantage: API RCP-TIMS TR01: Feedback RFDS S1-3' | 2133-09-22 | 2133-09-28 |  |  | 5d | [5 empty] | 1586 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-22 | 2133-09-28 | 0
MC5.1.2.14.14.1 - Parameters Shared' | 2133-09-22 | 2133-09-22 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-22 | 2133-09-22 | 0
MC5.1.2.14.14.2 - Fields Confirmed' | 2133-09-23 | 2133-09-23 |  |  | 1d | [5 empty] | 1588 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-23 | 2133-09-23 | 0
MC5.1.2.14.14.3 - Sample Query Shared' | 2133-09-24 | 2133-09-24 |  |  | 1d | [5 empty] | 1589 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-24 | 2133-09-24 | 0
MC5.1.2.14.14.4 - Developed' | 2133-09-25 | 2133-09-25 |  |  | 1d | [5 empty] | 1590 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-25 | 2133-09-25 | 0
MC5.1.2.14.14.5 - Tested & Go Live' | 2133-09-28 | 2133-09-28 |  |  | 1d | [5 empty] | 1591 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-28 | 2133-09-28 | 0
MC5.1.2.14.15 - Rakuten-Vantage: API RCP-TIMS RT03: Feedback As-Is CAD' | 2133-09-29 | 2133-10-05 |  |  | 5d | [5 empty] | 1592 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-29 | 2133-10-05 | 0
MC5.1.2.14.15.1 - Parameters Shared' | 2133-09-29 | 2133-09-29 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-29 | 2133-09-29 | 0
MC5.1.2.14.15.2 - Fields Confirmed' | 2133-09-30 | 2133-09-30 |  |  | 1d | [5 empty] | 1594 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-09-30 | 2133-09-30 | 0
MC5.1.2.14.15.3 - Sample Query Shared' | 2133-10-01 | 2133-10-01 |  |  | 1d | [5 empty] | 1595 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-01 | 2133-10-01 | 0
MC5.1.2.14.15.4 - Developed' | 2133-10-02 | 2133-10-02 |  |  | 1d | [5 empty] | 1596 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-02 | 2133-10-02 | 0
MC5.1.2.14.15.5 - Tested & Go Live' | 2133-10-05 | 2133-10-05 |  |  | 1d | [5 empty] | 1597 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-05 | 2133-10-05 | 0
MC5.1.2.14.16 - Rakuten-Vantage: API RCP-TIMS TR02: As-Is CAD, EP, AP' | 2133-10-06 | 2133-10-12 |  |  | 5d | [5 empty] | 1598 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-06 | 2133-10-12 | 0
MC5.1.2.14.16.1 - Parameters Shared' | 2133-10-06 | 2133-10-06 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-06 | 2133-10-06 | 0
MC5.1.2.14.16.2 - Fields Confirmed' | 2133-10-07 | 2133-10-07 |  |  | 1d | [5 empty] | 1600 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-07 | 2133-10-07 | 0
MC5.1.2.14.16.3 - Sample Query Shared' | 2133-10-08 | 2133-10-08 |  |  | 1d | [5 empty] | 1601 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-08 | 2133-10-08 | 0
MC5.1.2.14.16.4 - Developed' | 2133-10-09 | 2133-10-09 |  |  | 1d | [5 empty] | 1602 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-09 | 2133-10-09 | 0
MC5.1.2.14.16.5 - Tested & Go Live' | 2133-10-12 | 2133-10-12 |  |  | 1d | [5 empty] | 1603 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-12 | 2133-10-12 | 0
MC5.1.2.14.17 - Rakuten-Vantage: API RCP-TIMS TR03: Transmission TSS' | 2133-10-13 | 2133-10-19 |  |  | 5d | [5 empty] | 1604 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-13 | 2133-10-19 | 0
MC5.1.2.14.17.1 - Parameters Shared' | 2133-10-13 | 2133-10-13 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-13 | 2133-10-13 | 0
MC5.1.2.14.17.2 - Fields Confirmed' | 2133-10-14 | 2133-10-14 |  |  | 1d | [5 empty] | 1606 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-14 | 2133-10-14 | 0
MC5.1.2.14.17.3 - Sample Query Shared' | 2133-10-15 | 2133-10-15 |  |  | 1d | [5 empty] | 1607 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-15 | 2133-10-15 | 0
MC5.1.2.14.17.4 - Developed' | 2133-10-16 | 2133-10-16 |  |  | 1d | [5 empty] | 1608 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-16 | 2133-10-16 | 0
MC5.1.2.14.17.5 - Tested & Go Live' | 2133-10-19 | 2133-10-19 |  |  | 1d | [5 empty] | 1609 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-19 | 2133-10-19 | 0
MC5.1.2.14.18 - Rakuten-Vantage: API RCP-TIMS TR03: STOB, permits, radio inst. & pas. exec. plan' | 2133-10-20 | 2133-10-26 |  |  | 5d | [5 empty] | 1610 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-20 | 2133-10-26 | 0
MC5.1.2.14.18.1 - Parameters Shared' | 2133-10-20 | 2133-10-20 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-20 | 2133-10-20 | 0
MC5.1.2.14.18.2 - Fields Confirmed' | 2133-10-21 | 2133-10-21 |  |  | 1d | [5 empty] | 1612 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-21 | 2133-10-21 | 0
MC5.1.2.14.18.3 - Sample Query Shared' | 2133-10-22 | 2133-10-22 |  |  | 1d | [5 empty] | 1613 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-22 | 2133-10-22 | 0
MC5.1.2.14.18.4 - Developed' | 2133-10-23 | 2133-10-23 |  |  | 1d | [5 empty] | 1614 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-23 | 2133-10-23 | 0
MC5.1.2.14.18.5 - Tested & Go Live' | 2133-10-26 | 2133-10-26 |  |  | 1d | [5 empty] | 1615 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-26 | 2133-10-26 | 0
MC5.1.2.14.19 - Rakuten-Vantage: API RCP-TIMS TR05: GEE ' | 2133-10-27 | 2133-11-02 |  |  | 5d | [5 empty] | 1616 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-27 | 2133-11-02 | 0
MC5.1.2.14.19.1 - Parameters Shared' | 2133-10-27 | 2133-10-27 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-27 | 2133-10-27 | 0
MC5.1.2.14.19.2 - Fields Confirmed' | 2133-10-28 | 2133-10-28 |  |  | 1d | [5 empty] | 1618 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-28 | 2133-10-28 | 0
MC5.1.2.14.19.3 - Sample Query Shared' | 2133-10-29 | 2133-10-29 |  |  | 1d | [5 empty] | 1619 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-29 | 2133-10-29 | 0
MC5.1.2.14.19.4 - Developed' | 2133-10-30 | 2133-10-30 |  |  | 1d | [5 empty] | 1620 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-10-30 | 2133-10-30 | 0
MC5.1.2.14.19.5 - Tested & Go Live' | 2133-11-02 | 2133-11-02 |  |  | 1d | [5 empty] | 1621 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-02 | 2133-11-02 | 0
MC5.1.2.14.20 - Rakuten-Vantage: API RCP-TIMS RT02: Feedback TSS / EP' | 2133-11-03 | 2133-11-09 |  |  | 5d | [5 empty] | 1622 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-03 | 2133-11-09 | 0
MC5.1.2.14.20.1 - Parameters Shared' | 2133-11-03 | 2133-11-03 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-03 | 2133-11-03 | 0
MC5.1.2.14.20.2 - Fields Confirmed' | 2133-11-04 | 2133-11-04 |  |  | 1d | [5 empty] | 1624 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-04 | 2133-11-04 | 0
MC5.1.2.14.20.3 - Sample Query Shared' | 2133-11-05 | 2133-11-05 |  |  | 1d | [5 empty] | 1625 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-05 | 2133-11-05 | 0
MC5.1.2.14.20.4 - Developed' | 2133-11-06 | 2133-11-06 |  |  | 1d | [5 empty] | 1626 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-06 | 2133-11-06 | 0
MC5.1.2.14.20.5 - Tested & Go Live' | 2133-11-09 | 2133-11-09 |  |  | 1d | [5 empty] | 1627 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-09 | 2133-11-09 | 0
MC5.1.2.14.21 - Rakuten-Vantage: API RCP-TIMS RT04: Dropped Candidates' | 2133-11-10 | 2133-11-16 |  |  | 5d | [5 empty] | 1628 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-10 | 2133-11-16 | 0
MC5.1.2.14.21.1 - Parameters Shared' | 2133-11-10 | 2133-11-10 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-10 | 2133-11-10 | 0
MC5.1.2.14.21.2 - Fields Confirmed' | 2133-11-11 | 2133-11-11 |  |  | 1d | [5 empty] | 1630 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-11 | 2133-11-11 | 0
MC5.1.2.14.21.3 - Sample Query Shared' | 2133-11-12 | 2133-11-12 |  |  | 1d | [5 empty] | 1631 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-12 | 2133-11-12 | 0
MC5.1.2.14.21.4 - Developed' | 2133-11-13 | 2133-11-13 |  |  | 1d | [5 empty] | 1632 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-13 | 2133-11-13 | 0
MC5.1.2.14.21.5 - Tested & Go Live' | 2133-11-16 | 2133-11-16 |  |  | 1d | [5 empty] | 1633 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-16 | 2133-11-16 | 0
MC5.1.2.14.22 - Rakuten-Vantage: API RCP-TIMS: Reporting API' | 2133-11-17 | 2133-11-23 |  |  | 5d | [5 empty] | 1634 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-17 | 2133-11-23 | 0
MC5.1.2.14.22.1 - Parameters Shared' | 2133-11-17 | 2133-11-17 |  |  | 1d | [11 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-17 | 2133-11-17 | 0
MC5.1.2.14.22.2- Fields Confirmed' | 2133-11-18 | 2133-11-18 |  |  | 1d | [5 empty] | 1636 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-18 | 2133-11-18 | 0
MC5.1.2.14.22.3 - Sample Query Shared' | 2133-11-19 | 2133-11-19 |  |  | 1d | [5 empty] | 1637 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-19 | 2133-11-19 | 0
MC5.1.2.14.22.4 - Developed' | 2133-11-20 | 2133-11-20 |  |  | 1d | [5 empty] | 1638 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-20 | 2133-11-20 | 0
MC5.1.2.14.22.5 - Tested & Go Live' | 2133-11-23 | 2133-11-23 |  |  | 1d | [5 empty] | 1639 | [5 empty] | SE&I: OSS & Orchestration |  |  | 2133-11-23 | 2133-11-23 | 0